## 1st June 2017
Proposed Solution - 7 NEDs + 2 VNBDs with Extended Minimum Switching
Confirmation Processes around Project Nexus Implementation Date
Non Effective Days (amber shading). The [24th May] is the last day SPA and SPR files can be sent to the iGT. 7 Non-Effective days are required, with 2 additional 'hyper-care' Non-Effective Days Note the diagram only shows the confirmation file to show when D is. Other SPA files e.g. objection files are subject to the same outage
Note: change of shipper timescales show the minimum timescale, longer timescales are available
Arrow shows the D+10 opening meter reading submission timescale. A supply point registration can go live in the iGT systems and the read can be provided to either the iGT (by 23rd May) or Xoserve (from 1st June onwards)
| S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M
| 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
|  |  | RQ | RQ | RQ | CO | CO | D
Opening read provision from D (read taken between D-5 and D+5, to be submitted by D+10) | M: RQ; T: RQ; W: RQ; T: CO; F: CO; S: D
|  |  | RQ | RQ | RQ | CO | CO |  |  | D
|  |  | RQ | RQ | RQ | RQ | CO |  |  | CO | D
|  |  | RQ | RQ | RQ | RQ | RQ |  |  | CO | CO | D
|  |  | RQ | RQ | RQ | RQ | RQ |  |  | RQ | CO | CO | D
|  |  | RQ | RQ | RQ | RQ | RQ |  |  | RQ | RQ | CO | CO | D
| CFR |  | RQ | RQ | RQ | RQ | RQ |  |  | RQ | RQ | RQ | CO | CO | D
|  | CFR | RQ | RQ | RQ | RQ | RQ |  |  | RQ | RQ | RQ | CO | CO |  | D
|  |  | CFR | RQ | RQ | RQ | RQ |  |  | RQ | RQ | RQ | CO | CO |  |  | D
|  |  |  | CFR | RQ | RQ | RQ |  |  | RQ | RQ | RQ | RQ | CO |  |  | CO | D
[5 empty] | CFR | RQ | RQ |  |  | RQ | RQ | RQ | RQ | RQ |  |  | CO | CO | D
[6 empty] | CFR | RQ |  |  | RQ | RQ | RQ | RQ | RQ |  |  | RQ | CO | CO | D
[7 empty] | CFR |  |  | RQ | RQ | RQ | RQ | RQ |  |  | RQ | CO | CO |  | D
[8 empty] | CFR |  | RQ | RQ | RQ | RQ | RQ |  |  | RQ | CO | CO |  |  | D
[9 empty] | CFR | RQ | RQ | RQ | RQ | RQ |  |  | RQ | CO | CO |  |  |  | D
[10 empty] | CFR | RQ | RQ | RQ | RQ |  |  | RQ | CO | CO |  |  |  |  | D
[11 empty] | CFR | RQ | RQ | RQ |  |  | RQ | CO | CO | [5 empty] | D
[12 empty] | CFR | RQ | RQ |  |  | RQ | CO | CO | [6 empty] | D
| T: CFR; F: RQ; M: RQ; T: CO; W: CO; T: D | CDs added | Total CDs
| T: CFR; F: RQ; M: RQ; T: CO; W: CO; F: D | +1 | 15
| T: CFR; F: RQ; M: RQ; T: CO; W: CO; S: D | +2 | 16
| T: CFR; F: RQ; M: RQ; T: CO; W: CO; S: D | +3 | 17
| T: CFR; F: RQ; M: RQ; T: CO; W: CO; M: D | +4 | 18
| F: CFR; M: RQ; T: RQ; W: CO; M: CO; T: D | +4 | 18
| M: CFR; T: RQ; W: RQ; M: CO; T: CO; W: D | +2 | 16
| T: CFR; W: RQ; M: RQ; T: CO; W: CO; T: D | +2 | 16
[19 empty] | CFR | [11 empty] | RQ | RQ | CO | CO | D
[19 empty] | CFR | [11 empty] | RQ | RQ | RQ | CO | CO | D
[19 empty] | CFR | [11 empty] | RQ | RQ | RQ | CO | CO |  | D
[19 empty] | CFR | [11 empty] | RQ | RQ | RQ | CO | CO |  |  | D
[19 empty] | CFR | [11 empty] | RQ | RQ | RQ | RQ | CO |  |  | CO | D
[19 empty] | CFR | [11 empty] | RQ | RQ | RQ | RQ | RQ |  |  | CO | CO | D
[27 empty] | CFR |  |  |  | RQ | RQ | RQ | RQ | RQ |  |  | RQ | CO | CO | D
[28 empty] | CFR |  |  | RQ | RQ | RQ | RQ | RQ |  |  | RQ | RQ | CO | CO | D
[29 empty] | CFR |  | RQ | RQ | RQ | RQ | RQ |  |  | RQ | RQ | RQ | CO | CO | D
Non Effective Days - No Code Communications and System Not Effective
NED - Code Comms allowed, BDs not to increment
NEDs that would have been non SBSBDs
[20 empty] | RQ | Additional RQ days created by extending switching timeline
Illustration - 7 NEDs + 2 VNBDs without Extended Minimum Switching
Confirmation Processes around Project Nexus Implementation Date | [45 empty] | Count of RQ Days
Non Effective Days (amber shading). The [24th May] is the last day SPA and SPR files can be sent to the iGT. 7 Non-Effective days are required, with 2 additional 'hyper-care' Non-Effective Days Note the diagram only shows the confirmation file to show when D is. Other SPA files e.g. objection files are subject to the same outage
Note: change of shipper timescales show the minimum timescale, longer timescales are available
Arrow shows the D+10 opening meter reading submission timescale. A supply point registration can go live in the iGT systems and the read can be provided to either the iGT (by 23rd May) or Xoserve (from 1st June onwards)
| S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M
| 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
|  |  | RQ | RQ | RQ | CO | CO | D
Opening read provision from D (read taken between D-5 and D+5, to be submitted by D+10) | M: RQ; T: RQ; W: RQ; T: CO; F: CO; S: D
|  |  | RQ | RQ | RQ | CO | CO |  |  | D
|  |  | RQ | RQ | RQ | RQ | CO |  |  | CO | D
|  |  | RQ | RQ | RQ | RQ | RQ |  |  | CO | CO | D
|  |  | RQ | RQ | RQ | RQ | RQ |  |  | RQ | CO | CO | D
| M: RQ; T: RQ; W: RQ; T: RQ; F: RQ; M: RQ; T: RQ; W: CO; T: CO; F: D | 7
| S: CFR; M: RQ; T: RQ; W: RQ; T: RQ; F: RQ; M: RQ; T: RQ; W: RQ; T: CO; F: CO; S: D | 8
| S: CFR; M: RQ; T: RQ; W: RQ; T: RQ; F: RQ; M: RQ; T: RQ; W: RQ; T: CO; F: CO; S: D | 8
| M: CFR; T: RQ; W: RQ; T: RQ; F: RQ; M: RQ; T: RQ; W: RQ; T: CO; F: CO; M: D | 7
| T: CFR; W: RQ; T: RQ; F: RQ; M: RQ; T: RQ; W: RQ; T: RQ; F: CO; M: CO; T: D | 7
| W: CFR; T: RQ; F: RQ; M: RQ; T: RQ; W: RQ; T: RQ; F: RQ; M: CO; T: CO; W: D | 7
| T: CFR; F: RQ; M: RQ; T: RQ; W: RQ; T: RQ; F: RQ; M: RQ; T: CO; W: CO; T: D | 7
| F: CFR; M: RQ; T: RQ; W: RQ; T: RQ; F: RQ; M: RQ; T: CO; W: CO; F: D | 6
| S: CFR; M: RQ; T: RQ; W: RQ; T: RQ; F: RQ; M: RQ; T: CO; W: CO; S: D | 6
| S: CFR; M: RQ; T: RQ; W: RQ; T: RQ; F: RQ; M: RQ; T: CO; W: CO; S: D | 6
| M: CFR; T: RQ; W: RQ; T: RQ; F: RQ; M: RQ; T: CO; W: CO; M: D | 5
| T: CFR; W: RQ; T: RQ; F: RQ; M: RQ; T: CO; W: CO; T: D | 4
| W: CFR; T: RQ; F: RQ; M: RQ; T: CO; W: CO; W: D | 3
| T: CFR; F: RQ; M: RQ; T: CO; W: CO; T: D | 2
| F: CFR; M: RQ; T: CO; W: CO; F: D | 1
| S: CFR; M: RQ; T: CO; W: CO; S: D | 1
| S: CFR; M: RQ; T: CO; W: CO; S: D | 1
| M: CFR; T: CO; W: CO; M: D | 0
| T: CFR; W: CO; M: CO; T: D | 0
| W: CFR; M: CO; T: CO; W: D | 0
| W: CFR; M: RQ; T: CO; W: CO; T: D | 1
| W: CFR; M: RQ; T: RQ; W: CO; T: CO; F: D | 2
| W: CFR; M: RQ; T: RQ; W: RQ; T: CO; F: CO; S: D | 3
| W: CFR; M: RQ; T: RQ; W: RQ; T: CO; F: CO; S: D | 3
| W: CFR; M: RQ; T: RQ; W: RQ; T: CO; F: CO; M: D | 3
| W: CFR; M: RQ; T: RQ; W: RQ; T: RQ; F: CO; M: CO; T: D | 4
| W: CFR; M: RQ; T: RQ; W: RQ; T: RQ; F: RQ; M: CO; T: CO; W: D | 5
| T: CFR; M: RQ; T: RQ; W: RQ; T: RQ; F: RQ; M: RQ; T: CO; W: CO; T: D | 6
| F: CFR; M: RQ; T: RQ; W: RQ; T: RQ; F: RQ; M: RQ; T: RQ; W: CO; T: CO; F: D | 7
| S: CFR; M: RQ; T: RQ; W: RQ; T: RQ; F: RQ; M: RQ; T: RQ; W: RQ; T: CO; F: CO; S: D | 8
Non Effective Days - No Code Communications and System Not Effective
NED - Code Comms allowed, BDs not to increment
NEDs that would have been non SBSBDs

## Version Control
version | date | comment | author
1FA | 20161007 | baseline | DA
1.1FA | 20161013 | - amendment to text to reflect last submission date is 24th May (previous version erroneeously stated 23rd May). - amendment to line 34, amended confirmation submission timescale - amendment to count of calendar days to switch (cell AV36 and AW36) - amendment to calculate calendar days column AW | DA