## IGT086 June Release
| Action | Timeframe | Start Date | End Date | January | February | March | April | May | Notes
UNC | UNC 0604 Work Stream Meetings | See Below | 2017-01-06
| WG Report Sent to Panel | 1BD | 2017-02-16
| DMR Issued for Consultation | 15BD | 2017-02-16
| UNC Panel Decision | 1BD | 2017-03-16
| FGO Go Live (UNC) | - | 2017-04-01 | [6 empty] | FGO Go live is 1st April 2017 for UNC Parties
IGT UNC | IGT UNC Work Stream Meetings | See Below | 2017-01-05
| Produce WG Report | 5BD | 2017-02-21 | 2017-02-28
| WG sign off/approve WG Report |  | 2017-03-07 | 2017-03-07
| Submit Modification & WG Report | 1BD | 2017-03-08 | 2017-03-08
| Panel | - | 2017-03-15 | 2017-03-15
| Produce DMR | 3BD | 2017-03-15 | 2017-03-17
| DMR Consultation | 15BD | 2017-03-20 | 2017-04-07
| Produce FMR | 1BD | 2017-04-10 | 2017-04-10 | [5 empty] | Reduced timeframe due to Bank Holidays in this period and need to provide 5 BD ahead of Panel
| Panel Meeting for Voting | - | 2017-04-19 | 2017-04-19
| Update FMR with Panel Recommendation | 1BD | 2017-04-20 | 2017-04-20 | [5 empty] | Panel to agree shorter implementation than 2 months
| Submit FMR to Ofgem | - | 2017-04-20 | 2017-04-20 | [5 empty] | FMR to be submitted to Panel same day as Panel vote
| Ofgem Determination Window | 25 BDs | 2017-04-21 | 2017-05-25
| Implementation Period | tbc | From Ofgem Decision | 01/06/2017* | [5 empty] | Length of implementation period will be driven by date of Ogem decision
| FGO Go Live (IGT UNC) | - | 01/06/2017* | 01/06/2017* | [5 empty] | FGO Go live is NEXUS Go Live for IGT UNC Parties
FGO Workstream Dates
* | If NEXUS is delayed, FGO implementation for IGT UNC will also be delayed to the revised NEXUS Go Live date | UNC | IGT UNC
|  | 2017-01-06 | 2017-01-05
|  | 2017-01-16 | 07/02/2017**
** | Note conflict of dates between IGT UNC workstream and final UNC0604 work stream meetings | 2017-01-31 | 2017-03-07
|  | 2017-02-07 | 2017-04-04
IGT UNC
Drafting period
IGT UNC Drafting
Preparation Period