## Issues Log
Principles
Focus on what Xoserve will be providing under SSP and not which matches between IGT UNC and UNC
Where 2 paragraphs are identical but are not relevant to SSP, do not point across.
Pointing to approach to be at a paragraph level rather than whole section
Where IGT UNC refers to another clause in the IGT UNC, make sure IGT UNC ref still exists or points to the UNC
IGTAD and NExA table require new definitions rather than keeping old and explaining their replacement in the Code preamble
Where bits are kept in IGT UNC, review is needed to amend multiple supply points.
Part | Paragraph | Raised by | Comment | Response | Action Complete?
CI | General |  | C1.3 of the IGT UNC is Called Daily Read Requirement & C1 5 Supply Point Classifcation. This ties to UNC G1.5 & M6.2 respectively but there are cross overs in content
| 1.2 | SL | 1.2 should stay in IGT UNC as sets out one user per supply point rule | ok | Y
| 2.2 (e) |  | This needs to be updated to list the 3 types of AQ (opening, fixed, rolling)
| 3 |  | Daily read equipment needs further review as could be defined in UNC (is refered to in part D)
| 5.5 |  | to be pointed across but define "days" not business days
| 6.1 | AP | 6.1 needs a way of carving out infill
| 6.1 |  | this section needs to refer to the x3 types of AQ and link to UNC for rolling AQ where possible
| 6.3(a) |  | SOQ is not defined using the same term in the UNC so need to identify this and undertsand if this acheieves the same thing as SOQ - is this held by Xoserve? |  |  | AM/CW
IGTs will still undertake annual review of NExA table and Xoserve will provide the information to do this. Text needs to reflect this.
| 6.6 |  | 6.6 can be removed as follows GDN process | Removed | Y
| 8.1.2 |  | 8.1.2 can be removed as won't over ride IGT UNC arrangements. However changes needed to iGTAD to link them together | Will require IGTAD update to link in termination notices together or at least for NG to check/notify the IGTs | Y
| 10.4 |  | 10.4 can be removed as class 1 will be DM mandatory so the clause will not be applicable post NEXUS | Removed | Y
| 19 |  | Not clear what this is trying to achieve. Doesn't appear in UNC so unlikely to be needed. | RDL to review as looks like poor layout/draffting
CIV | 2.4.3 |  | need to check with Xoserve that closing read for withdrawal is required under IGT UNC CIV 2.4.2(d)(iii) |  |  | AM
| 7 |  | Need to check with Xoserve whether they are involved in the re-establishment business process as would appear to be setting out additional charges GT can recover where it becomes aware that supply point is not isloated and can offtake gas (may need future mod to point across in the future) |  |  | AM
CV | 2 |  | One off connections under Code require nomination but in practice uses a one line PSR as an IGT to Shipper process. Code implies this should be Shipper driven but haven't anticipated this and Xoserve don't have thismapped out. Need to discuss collectively |  |  | 039/Xoserve
D | 2.7 |  | point to UNC M4 |  | Y
| 3 |  | Contractual terms for provision of metering so needs to stay in IGT UNC |  | Y
| 5 |  | How does clamping work in terms of flows and can Xoserve support this? |  |  | For Xoserve to answer
| 6 |  | Not for this mod but tis section needs review
| 7.1(b) |  | Does UK link set out file format for transporter notification to Shipper for transporter installed meter and do Xoserve send this on behalf of the transporter? - M3.2.1(b) (for Xoserve to answer). |  |  | For Xoserve to answer
E | 1.5.2 |  | Daily read Equipment is now refered to as "Transporter" Daily read Equipment - why is this? Is this so that it refers to class one specifically? |  |  | Chris Warner
| 11 |  | This points to data ownership under K25 so needs to be retained in IGT UNC
F | 4
6
7.2/7.3
9
I
K | 25 |  | Liabilities to stay in IGT UNC but needs to be tweaked to include UK Link
Need change to IGTAD so GDN notifies IGT via Xoserve if a Shipper is terminated. Need to understand what flows Xoserve send to GDNs so can also be sent to IGTs.
Part | Paragraph | Raised by | Comment | Response | Action Complete?
TPD G | 1.6.16 |  | Has 1.6.16 (and 1.6.6) been correctly removed under 0440 regarding Aqs which are deemed to be incorrect
TPD M | 5 |  | Need RDL to look at drafting as will point across IGT UNC E3 but under the UNC, some references to transporter will mean the IGT but others (particularly around class 1) will need to mean the GDN.
| 5.10.3 |  | This isn't in the IGT UNC as would appear to be relating to non-transporter owned meters. Could be included but made clear that doesn't apply to IGT installed meters. May not be supported as is a new obligation so could be introduced as a future modification in the future.
TPD | all |  | Does IGT UNC need to explaint that any references to "Total System" under UNC also includes IGT supply points?
General
|  |  | Do Xoserve keep history of meter reads for a supply point? |  |  | Xoserve
|  |  | Need to understand IGTS definition and how this relates to CSEP supply point so can refer using correct terminology |  |  | Chris Warner
|  |  | Why is IGT reconciliation set out in E1.3.1(c)(ii) where as GDN obligation is M5.10.7 |  |  | Chris Warner