## Issues Log
Principles
Focus on what Xoserve will be providing under SSP and not which matches between IGT UNC and UNC
Where 2 paragraphs are identical but are not relevant to SSP, do not point across.
Pointing to approach to be at a paragraph level rather than whole section
Where IGT UNC refers to another clause in the IGT UNC, make sure IGT UNC ref still exists or points to the UNC
IGTAD and NExA table require new definitions rather than keeping old and explaining their replacement in the Code preamble
Where bits are kept in IGT UNC, review is needed to amend multiple supply points.
Part | Paragraph | Raised by | Comment | Response | Action Complete?
A | 2 |  | This could be where RDL new draffting on overview and interpretation sits in the IGT UNC | Complete under A5 | Yes
| 2.1 |  | Look at removing as this will no longer be applicable (check how bulk confirmations are referenced however) | Keep in as there may be some areas which are stil used such as PSR process. Where currently there is the option to deviate to the "Manual" under SSP, all references have been removed | Yes | GH
| 4 |  | NExA description needs review i.e. should all refs be updated to IGTAD or should this simply say "or future replacement documents". | IGTAD reference used | Yes
|  |  | Plain Elnglish Summary required | Now drafted - to be instered at beginning of Code but as non-legally binding text | Yes | GH/SL
Part | Paragraph | Raised by | Comment | Response | Action Complete?
B | 3 | GH | Needs tidying up as still refers to LMNs | Drafting updated | Yes | GH
Part | Paragraph | Raised by | Comment | Response | Action Complete?
CI | General |  | C1 3 of the IGT UNC is Called Daily Read Requirement & C1 5 Supply Point Classifcation. This ties to UNC G1.5 & M6.2 respectively but there are cross overs in content | CI 3 renamed classes of supply point and this part carved out of CI 5 | Y
| 1.2 | SL | 1.2 should stay in IGT UNC as sets out one user per supply point rule | ok | Y
| 2.2 | JK | Should “entry SOQ” also be listed as a required field? | This can be calculated by Shippers who have access to load factors. Not all IGTs store this in their systems currently so would suggest that this is subject to a separate change proposal so it can be evaluated in its own right.
| 2.8-2.12 |  | 2.8-2.12 may need to be removed pending section D and E drafting as the IGT is unlikely to beupdating the supply point register with meter info | Agreed to retain at meeting #24. This is an operational process between the IGT and the Shipper and Parts D and E do not overwrite these paragraphs | Y
| 3 |  | Daily read equipment needs further review as could be defined in UNC (is refered to in part D) | CI 3.5(b) has been drafted to make it clear that the equipment and responsibilities are those of the GDN | Y | GH/RDL
| 3.6 |  | Will LDZ CSEP Ancillary Agreement still be correct terminology? | Yes - NEXA definition needs to be amended however | Y | RDL/AM
| 5.5 |  | to be pointed across but define "days" not business days | Complete | Y | AM/CW
| 6.1 | AP | 6.1 needs a way of carving out infill | Draft content now added to text | Y | GH
| 6.1 |  | this section needs to refer to the x3 types of AQ and link to UNC for rolling AQ where possible | Draft content now added to text | Y | AM
| 6.2 & 6.3 | JK | May be an issue with infill with the current drafting as may be swept up with NExA table. | Additional text added as follows: "and is not subject to a surcharge under paragraph 5 of Special Condition 1of the Pipeline Operator’s Licence" | Y | GH
| 6.3 |  | Not clear why this is needed? UNC process should pick this up? Also risk that this may undermine the AQ to which IGT charges are based. | Agreed at meeting #24 to retain as is not captured elsewhere | Y
| 6.4 |  | SOQ is not defined using the same term in the UNC so need to identify this and undertsand if this acheieves the same thing as SOQ - is this held by Xoserve? | Defintion updated to align with UNC ("Supply Point Capacity") | Y
|  |  | 3 types of AQ need to be listed | Added as per email from AM oin 04/06/14 | Y | To be taken forwards outside of IGT039
|  |  | 3 types of SOQ may need to be listed | Waiting for Xoserve to confirm - 2 types required and both are now added to CI and M | Y
| 6.5(b) |  | IGTs will still undertake annual review of NExA table and Xoserve will provide the information to do this. Text needs to reflect this. | Draft content now added to text | Y
| 6.4 |  | IGT AQ review procedures needs to be amended to report procedures |  | Y
| 6.6 |  | 6.6 can be removed as follows GDN process | Removed | Y
| 8.1.2 |  | 8.1.2 can be removed as won't over ride IGT UNC arrangements. However changes needed to iGTAD to link them together | 8.1.2 has been removed. Proposal is to update IGTAD to link in termination notices together or at least for NG to check/notify the IGTs.
| 9.1 |  | See note - should TPD G2.2.4 be excluded? | Yes | Y | c
| 10.4 |  | 10.4 can be removed as class 1 will be DM mandatory so the clause will not be applicable post NEXUS | Removed | Y | RDL
| 12 |  | RDL to consider | Parts of text pointed to the UNC | Y |  | UK link covers this off
| 13 |  | RDL to revise opening paragraph drafting |  | Y
| 14.6-8 |  | Need to check if is DM or class 1 | class 1 | Y
| 18 |  | Removed from UNC and not replaced - have emailed CW to ask why | Now mirrored in IGT UNC | Y
| 19 |  | Not clear what this is trying to achieve. Doesn't appear in UNC so unlikely to be needed. | RDL to review as looks like poor layout/draffting - deleted | Y
AM
CII |  |  | points across but 5.6.3 refers to "total system" | Needs to be covered off under UNC terminology section | Yes
CIV | 2.4.3 |  | need to check with Xoserve that closing read for withdrawal is required under IGT UNC CIV 2.4.2(d)(iii) | No - process to mirror GDN/UNC process | Y | GH/RDL - DONE
| 3.1 |  | Need to check if reference to E6 in 3.1 is required - depends on what Part E drafting looks like] | Reference removed because E6 points across. | yes | 039/Xoserve
| 7 |  | Need to check with Xoserve whether they are involved in the re-establishment business process | Xoserve have confirmed their involvement in the process so have pointed across as will be dealt with in the same way | Y
|  |  | May need to retain this as sets out when IGTs can charge for re-establishment. Could redefine GDN transportation charges in UNC but may be best to retain in IGT UNC? | Has been retained for simplicity so as not to try to redefine definitions within the UNC definition | Y
CV | 1-3 |  | Can paras 1-3 point to UNC? Will this impact contractual standing? | Retained in IGT UNC as a mixture of obligations and SSP process. Further complication that some of the definitions if pointed across won't work as the definitions themselves have defined terms within | Y
| 2 |  | One off connections under Code require nomination but in practice uses a one line PSR as an IGT to Shipper process. Code implies this should be Shipper driven but haven't anticipated this and Xoserve don't have thismapped out. Need to discuss collectively | Xoserve have confirmed that the process in the BRD will be able to support one off connection process | Y
D | 2.7 |  | point to UNC M4 |  | Y
| 3 |  | Contractual terms for provision of metering so needs to stay in IGT UNC |  | Y
| 5 |  | How does clamping work in terms of flows and can Xoserve support this? | agreed to align with GDN process | Y | Chris Warner
| 6 |  | Not for this mod but tis section needs review
| 7.1(b) |  | Does UK link set out file format for transporter notification to Shipper for transporter installed meter and do Xoserve send this on behalf of the transporter? - M3.2.1(b) (for Xoserve to answer). | clarified under 7.2 | Y | AM
GH
E | 1 |  | Carve out for M5.1.1 and M5.1.3 for transporter definition but not actually referred to in text | Was missed out from previous iteration so new E1.3 added to apply M5.1 | Y | GH/RDL
| 1.5.2 |  | Daily read Equipment is now refered to as "Transporter" Daily read Equipment - why is this? Is this so that it refers to class one specifically? | Yes | Y | GH/SL
| 18 |  | This points to data ownership under K25 so needs to be retained in IGT UNC | Retained and tweaked to extend to 3rd party systems operated on behalf of the IGT
| 14 |  | Points across but includes userpays under 5.13.14© and 5.13.17 for agreed opening reads and EOMRs - Point to user pays but will be recovered by Xoserve under NCUP contract. Likely that charge will be 0. | all ok. Is covered off under para 13 which is correct. | Y
| 14 | JK | Query on whether "Meter Fit Report" will be the .CD file and whether this coul dbe referenced to avoid confusion |  |  | AM
| 14 |  | Likely this will now use existing user pays mechanism so reference to NCUP can be removed. However, Activity under M5.13.14(d) points to sub para (b) which will be carried out by the GDN. GH to revise text to carve out this instance of Transporter in the IGT UNC drafting that points across.. | Complete and redefinition added for Transporter term under E1.2 | Y | GH
F | 11.1-11.3 | JK | Review of paras required as may no lonnger be required | 13.1 & 13.2 removed, 13.3 tweaked and kept as a reminder. 13.4 retained. | Y | GH/SL
I |  |  | references to NEXA - how will this be defined? i.e. IGTAD or simply amend NEXA definition to include future replacement docs | New IGTAD Definition added to Part M | Y | RDL
K | 25 |  | Liabilities to stay in IGT UNC but needs to be tweaked to include UK Link | Looking at clause 26 I the current draffting is ok going forwards as is about general liabilities | Y
| 25.1 |  | Needs tweaking to refer to UK link but Xoserve are acting as the IGT agent and so this also needs to be backed off in the iASA. | k25.1 25.1 updated to extend to 3rd party systems operated on behalf of the IGT | Y
| 34 |  | May need reference to UK Link | Para 34 relates to notices and communication "other than one which is given as a System Communication". "Systems Communication" definition has been expanded to include UK Link so is now ok | Y | CW
Part | Paragraph | Raised by | Comment | Response | Action Complete? | RDL, DNE IN GENERAL LANGUAGE Part A, para 5.
TPD G | 1.6.16 |  | Has 1.6.16 (and 1.6.6) been correctly removed under 0440 regarding Aqs which are deemed to be incorrect | Was changes under 0432 | N/A
TPD M | 5 |  | Need RDL to look at drafting as will point across IGT UNC E3 but under the UNC, some references to transporter will mean the IGT but others (particularly around class 1) will need to mean the GDN. | specific carve out for Large Transporter activities - rest of Ttransporter references will be covered off under preamble which is to be draffted by RDL | Y
| 5.10.1 |  | Read Date should be Meter Read Date? - compare 5.10.3 | CW confirmed current drafting is ok in UNC | Y
| 5.10.3 |  | This isn't in the IGT UNC as would appear to be relating to non-transporter owned meters. Could be included but made clear that doesn't apply to IGT installed meters. May not be supported as is a new obligation so could be introduced as a future modification in the future. | This isn't an issue as currently must reads are carried out for both IGT and 3rd party meters so this isn't a change to current arrangements | - | Xoserve
TPD | all |  | Does IGT UNC need to explaint that any references to "Total System" under UNC also includes IGT supply points? | Will be captured in preamble in Section A of IGT UNC | Y
Chris Warner
Chris Warner
General
Do Xoserve keep history of meter reads for a supply point?
Need to understand IGTS definition and how this relates to CSEP supply point so can refer using correct terminology
Why is IGT reconciliation set out in E1.3.1(c)(ii) where as GDN obligation is M5.10.7