## Sheet1
Issue | Details | Date Raised | Meeting Reference | Action Required | Last Update | Comments
iGT Meter Point Creation Process | Following discussions between iGTs and Xoserve, it has become apparent that a Shipper, other than the PSR Shipper, is able to take over ownership of a meter point without the PSR Shipper necessarily being informed. This results in the first Shipper registration on Xoserve’s system may not be the Elected Shipper. | 2016-03-01 | Modification Workstream 16-03 | Guidance to be provided on this issue and the proper process to be followed in the Meter point creation process and industry flows. | 2016-05-03 | Paul Orsler (Xoserve) to continue investigating this issue regarding iGT Meter Point Creation Process and industry flows, and produce a further report.
Interaction and communication with the Project Nexus Transition Progress Group (TPG) | Do issue relating to TPG groups go straight to the TPG or are they to be discussed within iGT UNC Workstreams. | 2016-04-03 | Modification Workstream 16-04 | Determine where TPG issues should be directed to | 2016-05-03 | On Non effective days issues there has been progress made, which will be discussed on the TPG work Group on the 17th of May 2016.
RGMA and its medium of transmission: | Understand whether iGTs would be mandated to send RGMA flows (ONJOB/ONUPD), and by what means iGTs would be expected to send flows (i.e. IX or alternative) | 2016-04-03 | Modification Workstream 16-04 | Relates to IX directories and there is an outstanding issue on how this will be performed. | 2016-05-03 | Slides have been drafted and will be shared once they have been signed-off internally by Xoserve.
Processing for in-flight queries during the on-effective window before Project Nexus go-live | Some queries could potentially be stuck inflight following the non-effective days period and go live of SSP | 2016-04-03 | Modification Workstream 16-05 | Determine how in-flight queries will be managed during the non-effective days window and communicate this approach with all iGT UNC parties | 2016-05-03 | This issue is being discussed in the Transition Progress Group (TPG) discussions. Updates are to be provided to the iGT UNC when available.