## Introduction
Forward Work Plan
Background
Ofgem published its final proposals for the Code Governance Review Phase 3 (CGR3) in March 2016. One of the proposals makes recommendations for Code Administrators to develop a forward work plan, to enable Code Administrators to manage change at a strategic level.
The objective of this Forward Work Plan is to coordinate the project management of ‘major’ industry change, through on-going oversight of the end-to-end delivery of significant programmes and central systems changes.
Scope
The scope of the Forward Work Plan is based on the annually agreed areas. The areas for 2017 are listed below: * Smart metering * Half Hourly Settlement * European harmonisation * Faster and more reliable switching
Disclosure
The information has been provided by Code Administratrators, to help inform Code Panels and the energy industry, and does not necessarily reflect the view of specific Code Panels. Note the version history below for details of Code Administrators who were not able to provide data for this plan.
Need more information?
For more information regarding a specific change, please contact the responsible Code Administrator:
Code Administrator | Code
ElectraLink Ltd | Distribution Connection Use of System Agreement (DCUSA)
Supply Point Administrator Agreement (SPAA)
ELEXON | Balancing and Settlement Code (BSC)
Energy Networks Association | Distribution Code
Gemserv | iGT Uniform Network Code (IGT UNC)
Master Registration Agreement (MRA)
Smart Energy Code (SEC)
Joint Office of Gas Transporters | Uniform Network Code (UNC)
National Grid | Connection and Use of System Code (CUSC)
Grid Code
System Operator – Transmission Owner Code (STC)
Version History: Forward Work Plan V1.0
This Forward Work Plan contains change updates for March 2017 and offers a best view as of 12 April 2017.
Please be aware that no updates were provided for the MRA or iGT UNC for the above period. As such, this version does not include changes for those Codes. For information relating to the forward view under the MRA or iGT UNC, please contact the respective Code Administrator.

## Headlines
Headlines
The Forward Work Plan headlines provide an overview of the key updates around the priority areas. The headlines are provided when and as they arise.
Area timelines and status
| Code | Change Ref | Title | A1 | A2 | A3 | A4 | A5 | Timeline Ref | S | Raised | S | Imp Decision | S | Imp Date | Assessment Duration | Implementation Duration | Progression State | RAG Status | Commentary | Drivers
Milestones
| Status | Smart Metering status | Smart metering timeline and status | [5 empty] | A1. Smart metering | C | 2011-04-01 | E | 2020-12-31 |  |  | 3562 | -44196 |  | AT RISK | 22 out of 32 live changes are at risk, as well as four milestones due to the DCC go-live delay. This gives smart metering an overall 'at risk' status. | Government policy
| Status | Elective HH Settlement status | Elective Half Hourly Settlement timeline and status | [5 empty] | A2. Elective HH Settlement | C | 2014-04-04 | C | 2017-06-29 |  |  | 1182 | -42915 |  | AT RISK | 7 out of 18 live changes are at risk. This gives elective HH Settlement an overall 'at risk' status. | Ofgem
| Status | Mandatory Half Hourly Settlement status | Mandatory Half Hourly Settlement timeline | [5 empty] | A2. Mandatory HH Settlement | C | 2016-11-11 | E | 2018-06-30 |  |  | 596 | -43281 |  | AT RISK | All changes to enable mandatory HH Settlement should be in place by the first half of 2018. Currently there is only one change planned to enable mandatory HH Settlement. This gives mandatory HH Settlement an overall 'at risk' status. ACTION: Code bodies to consider when to raise changes to enable mandatory HH Settlement. | Ofgem
| Overall Status | European Harmonisation status | European Harmonisation timeline and status | [5 empty] | A3. European harmonisation |  |  | E | 401769 |  |  | 401769 | -401769 |  | AT RISK
| Status | Faster switching status | Faster switching timeline and status | [5 empty] | A4. Faster and more reliable switching | C | 2014-06-16 | E | 2019-01-01 |  |  | 1660 | -43466 |  | ON TRACK | 1 out of 4 live changes are 'on track', this gives faster switching an overall 'on track' status. Ofgem view is for new arrangements to go live in 2019. | -
Area 1. Smart Metering
* No updates provided
Area 2. Half Hourly Settlement
* Ofgem publish their latest update on Half Hourly Settlement. The update confirmed that the SCR is likely to be launched in Q1 2017-18, with a parallel Request for Information. * BSC Modification P272 'Mandatory Half Hourly Settlement for Profile Classes 5-8' was implemented on 1 April 2017. P271 makes HH Settlement mandatory for all Metering Systems within PCs 5-8 (where capable metering has been installed), as the Proposer believes that the use of Non Half Hourly (NHH) data is not as accurate and masks individual customer behaviour.
Area 3. European Harmonisation
* No updates provided
Area 4. Faster Switching
* No updates provided
Area 5. Code Specific
* The new UK Link system being delivered under Project Nexus is on track to go-live on 01 June 2017. There are a number of associated and transitional modifications in place to facilitate the changeover from existing arrangements. Simultaneously settlement-related activities currently performed offline by iGTs will be included within the scope of UK Link and therefore iGTs will become subject to related provisions in the UNC. Please contact the Joint Office for more information. * Ofgem published its final version of its work programme, following its consultation. Includes its Simplification Plan 2017-18.
All changes to enable mandatory HH Settlement should be in place by the first half of 2018. Currently there is only one change planned to enable mandatory HH Settlement. However, it is anticpated that a SGR will be adopted to facilitate mandatory HH Settlement.

## Horizon (All)
Horizon Scanning
Horizon scanning provides provides a high level snap shot of the key legislative and regulatory changes expected to impact the industry. The changes are represented in terms of impact, certainty and anticipated implementation.
1 -2 years
2- 5 years
5 years +
Firm deliverables
Deliverables in definitition
Deliverables undefined
Policy undefined
Ones to watch
BREXIT
(L) (Medium)
UK General Election (2020)
(L) (Medium)
Smart meter roll out complete
(I) (Medium)
Faster Switching and Centralised Registration
(I) (High)
NEXUS Ph2
(I) (High)
FGO Ph2 Imp. (Q2 17)
(I) (Medium)
EU CAM (Am & Inc)
(R) (Medium)
Priority Svs Register
(R) (Medium)
EU Tariff Code
(R) (High)
Alternative Sources of Gas
(I) (Low)
Gemini Rewrite
(I) (High)
Gas Settlement Evolution
(R) (High)
RAASP
(I) (High)
Pan-EU harmonisation complete
(I) (HIgh)
EU Reform
(R) (High)
CMA
(R) (High)
KEY
Industry impacted:
Industry-wide change
Electricity
Gas
Driver of change:
(I) - Industry
(L) - Legislation
(R) - Regulatory
Level of impact:
(High)
(Medium)
(Low)
Mandatory HH Settlement
(R) (High)
NEXUS Ph2 (2018)
(I) (High)
Tariff Reform (2019)
(R) (Medium)
Erroneous Transfers (Medium)

## Commentary 2+ yrs
This sheet sets out the changes identified in the 2-5 years timescale on the Horizon
Horizon item | What is it? | Which Codes might be affected? | What happens next? | For more information
Nexus Phase 2 | During specification and build of the new UK Link systems under Project Nexus, a number of 'further requirements' were identified by the UNC Workgroup that participants believed would add value if made available. These were too late to be included in the inital release and were therefore compiled into a Requirements Log that was to be subject to more detailed assessment in due course. | UNC iGT UNC | It is anticipated that further UNC modifications would be required to enable the changes identified. No work is anticipated on this until after the current Nexus deliverables - Phase 1 and RAASP - are more certain in H1 2017. | The Requirements Log can be viewed here: http://www.gasgovernance.co.uk/nexus/090816 A diagram showing how the various UNC modifications interact to form Project Nexus is available here: http://www.gasgovernance.co.uk/sites/default/files/Nexus%20Modification%20interactions%20v2.0_0.pdf
Alternative Sources of Gas | This is an early-planning placeholder to focus some thinking about how the various future sources - e.g. shale, LNG, biomethane - might impact on the operation of GB's gas networks. | UNC iGT UNC | tbc | http://www2.nationalgrid.com/UK/Industry-information/Future-of-Energy/Gas/
Gemini Rewrite | Gemini provides GB's gas nominations, trades, energy balancing and entry/exit capacity processes and invoicing. The operating system behind the central Gemini system (operated by Xoserve on behalf of National Grid Gas) has been in use since 2005 and will require replacement or refreshing. | UNC | tbc | http://www.xoserve.com/index.php/our-systems/gemini/
UK General Election 2020 | Potential change of emphasis in Energy Policy leading to strengthening of Retail reform, acceleration of alternative sources of energy, penetration of electric vehicles etc | ALL | tbc
Brexit | UK exit from the EU is not currently expected to have a significant impact on GB Codes. Working assumption for the industry is that GB will continue to access the Single Energy Market, meaning that existing interconnection point arrangements will remain. In the near term, GB is legally obliged to comply with EU Regulations and subsequent Codes and work to adapt GB Codes continues. | ALL | Awaiting clear direction from central government via BEIS and Ofgem. | tbc
Smart Meter Roll-out complete | As roll-out of Smart meters approaches completion, the availability of reliable and frequent data items should permit the industry to improve many processes, such as Settlement, Forecasting, Balancing and capacity management | ALL | Ofgem are leading work under the "Future Energy Insights" banner that should inform direction on these matters. | https://www.ofgem.gov.uk/publications-and-updates/ofgem-s-future-insights-series-overview-paper
Gas Settlement Evolution | Currently a placeholder for a piece of work that is only just starting - essentially to think about how Settlement could be further improved. | UNC iGT UNC | Initial discussions are taking place at the Change Overview Board | http://www.gasgovernance.co.uk/COB
All changes to enable mandatory HH Settlement should be in place by the first half of 2018. Currently there is only one change planned to enable mandatory HH Settlement. However, it is anticpated that a SGR will be adopted to facilitate mandatory HH Settlement.

## A1. Smart metering
Area 1. Smart Metering
Smart Metering aims to faciliate the roll out electricity and gas smart Meters across Great Britain.
Headlines
* No updates provided
Code | Change Ref | Title | A1 | A2 | A3 | A4 | A5 | Timeline Ref | S | Raised | S | Imp Decision | S | Imp Date | Assessment Duration | Implementation Duration | Progression State | RAG Status | Commentary | Drivers
Status | Smart metering status | Smart metering timeline and status | [5 empty] | Smart metering status | C | 2011-04-01 | E | 2020-12-31 |  |  | 3562 | -44196 |  | ON TRACK | The overall status of smart metering is 'on track'. This is because all 21 live change are on track. | Government policy
Today | Today | Today's date | [5 empty] | Today | C | 2017-05-09 | C | 2017-05-10 | - | N/A | 1 |  |  | ON TRACK | - | -
BSC | P272 | Mandatory Hlaf Hourly Settlement for Profle Classes 5-8 | Yes | Yes | No | No | No | BSC - P272 | C | 2011-05-20 | C | 2014-10-29 | C | 2017-04-01 | 1258 | 885 | Implemented | On Track | -
DCUSA | DCP 204 | Smart Metering Related Amendments to Schedule 8 | Yes | No | No | No | No | DCUSA - DCP 204 | C | 2014-02-27 | C | 2016-02-23 | C | 2016-09-01 | 726 | 191 | Implemented | On Track | -
SEC | SECMP0002 | Add New Command to Reset Debt Registers | Yes | No | No | No | Yes | SEC - SECMP0002 | C | 2016-02-19 | E | TBD | E | 2018-11-01 | 1 | 986 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change.
SEC | SECMP0004 | Inclusion of Device Serial Number data item in the Smart Metering Inventory | Yes | No | No | No | Yes | SEC - SECMP0004 | C | 2016-02-19 | E | TBD | E | 2018-06-28 | 1 | 860 | Modification Report consultation | On Track | SECMP0004 has been issued for Modification Report Consutlation until 5th April 2017. The Change Board will vote on SECMP0004 on 19th April 2017.
SEC | SECMP0005 | Include Tariff and Register Labels in SMETS2 Devices | Yes | No | No | No | Yes | SEC - SECMP0005 | C | 2016-03-01 | E | TBD | E | 2018-11-01 | 1 | 975 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change.
SEC | SECMP0006 | Specifying the number of digits for device display | Yes | No | No | No | Yes | SEC - SECMP0006 | C | 2016-03-01 | E | TBD | E | 2018-11-01 | 1 | 975 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change.
SEC | SECMP0007 | Firmware updates to mandated HAN devices | Yes | No | No | No | Yes | SEC - SECMP0007 | C | 2016-03-01 | E | TBD | E | 2018-11-01 | 1 | 975 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change.
SEC | SECMP0008 | Provision of a Service Request error response for quarantined Service Requests | Yes | No | No | No | Yes | SEC - SECMP0008 | C | 2016-03-01 | E | TBD | E | 2018-06-28 | 1 | 849 | Modification Report consultation | On Track | SECMP0008 has been issued for Modification Report Consutlation until 5th April 2017. The Change Board will vote on SECMP0008 on 19th April 2017.
SEC | SECMP0009 | Centralised Firmware Library | Yes | No | No | No | Yes | SEC - SECMP0009 | C | 2016-03-01 | E | TBD | E | 2018-11-01 | 1 | 975 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change.
SEC | SECMP0010 | Introduction of triage arrangements for Communication Hubs | Yes | No | No | No | Yes | SEC - SECMP0010 | C | 2016-03-02 | E | TBD | E | 2018-11-01 | 1 | 974 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change.
SEC | SECMP0011 | Inclusion of Meter Asset Provider Participant Code (MAP ID) Participant Codes in the Smart Metering Inventory | Yes | No | No | No | Yes | SEC - SECMP0011 | C | 2016-03-22 | E | TBD | E | 2018-06-28 | 1 | 828 | Modification Report consultation | On Track | SECMP0011 has been issued for Modification Report Consutlation until 5th April 2017. The Change Board will vote on SECMP0011 on 19th April 2017.
SPAA | CP 16/334 | Introduction of Smart Prepayment Change of Supplier Exceptions Process | Yes | No | No | No | No | SPAA - CP 16/334 | C | 2016-05-01 | C | 2016-10-20 | E | TBD | 172 |  | Implemented | On Track | Confirmation of authority approval 1 WD after Authority Consent received
SEC | SECMP0013 | Smart meter device diagnostics and triage | Yes | No | No | No | Yes | SEC - SECMP0013 | C | 2016-05-04 | E | TBD | E | 2018-11-01 | 1 | 911 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change.
SEC | SECMP0012 | Channel selection to support Shared HAN solutions | Yes | No | No | No | Yes | SEC - SECMP0012 | C | 2016-05-05 | E | TBD | E | 2018-11-01 | 1 | 910 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change.
SEC | SECMP0015 | GPF timestamp for reading instantaneous Gas values | Yes | No | No | No | Yes | SEC - SECMP0015 | C | 2016-05-31 | E | TBD | E | 2018-11-01 | 1 | 884 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change.
SEC | SECMP0016 | Consideration of "Maximum Credit" value in credit cover calculation | Yes | No | No | No | Yes | SEC - SECMP0016 | C | 2016-06-03 | C | 2017-01-28 | C | 2018-04-01 | 239 | 428 | Implemneted | On Track | SECMP0016 was implemented on 1sdt April 2017.
SEC | SECMP0018 | Standard Electricity Distributor Configuration Settings | Yes | No | No | No | Yes | SEC - SECMP0018 | C | 2016-06-23 | E | TBD | E | 2018-11-01 | 1 | 861 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change.
BSC | P347 | Reduction in R1 Read Threshold | Yes | Yes | No | No | No | BSC - P347 | C | 2016-07-01 | E | 2017-02-10 | C | 2017-04-01 | 224 | 50 | Implemented | On Track | On 19 January the Panel considered the Sendback Direction from the Authority and approved the revised Final Modification Report for P347. The Panel maintained its recomendation to the Authority that P347 should be rejected. The revised Final Modification Report was submitted to the Authority for decision on 19 January 2017. On 30 January 2017 the Authority determined that P347 should be Approved and implemented on 1 April 2017.
SEC | SECMP0019 | ALCS Description Labels | Yes | No | No | No | Yes | SEC - SECMP0019 | C | 2016-07-14 | E | TBD | E | 2018-11-01 | 1 |  | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change.
UNC | 0594R | Meter Reading Submission for Advanced & Smart Metering | Yes | No | No | No | No | UNC - 0594R | C | 2016-09-02 |  | n/a |  | n/a | 1 |  | Request | On Track | This is a UNC Request - to review the arrangements for meter reading submission. A modification is one possible output. | None- Review
SEC | SECMP0021 | Increase Other SEC Party representation for TABASC and SSC | Yes | No | No | No | Yes | SEC - SECMP0021 | C | 2016-10-04 | E | TBD | E | 2017-05-11 | 1 | 219 | Modification Report Consutlation | On Track | SECMP0021 has been issued for Modification Report Consutlation until 5th April 2017. The Change Board will vote on SECMP0021 on 19th April 2017.
SEC | SECMP0023 | Correct Units of Measure for Uncontrolled Gas Flow Rate | Yes | No | No | No | Yes | SEC - SECMP0023 | C | 2016-10-26 | E | TBD | E | 2018-11-01 | 1 |  | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change.
SEC | SECMP0024 | Enduring Approach to Communication Hub Firmware Management | Yes | No | No | No | Yes | SEC - SECMP0024 | C | 2016-10-27 | E | TBD | E | 2018-11-01 | 1 | 735 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change.
SEC | SECMP0025 | Electricity Network Party Access to Load Switching Information | Yes | No | No | No | Yes | SEC - SECMP0025 | C | 2016-11-18 | E | TBD | E | 2018-06-01 | 1 | 560 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change.
SEC | SECMP0028 | Prioritising Service Requests | Yes | No | No | No | Yes | SEC - SECMP0028 | C | 2016-12-07 | E | TBD | E | TBD | 1 |  | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change.
SEC | SECMP0026 | Changes to the Security Sub-Committee Nomination Process | Yes | No | No | No | Yes | SEC - SECMP0026 | C | 2016-12-12 | E | TBD | C | 2017-03-16 | 1 | 94 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change.
SEC | SECMP0027 | Amending Service Request Forecasting | Yes | No | No | No | Yes | SEC - SECMP0027 | C | 2016-12-16 | E | TBD | E | TBD | 1 |  | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change.
SEC | SECMP0029 | Business Continuity and Disaster Recovery Testing Amendments | Yes | No | No | No | Yes | SEC - SECMP0029 | C | 2016-12-19 | E | TBD | E | TBD | 1 |  | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change.
SEC | SECMP0030 | Demand Management of DCC Systems | Yes | No | No | No | Yes | SEC - SECMP0030 | C | 2017-01-04 | E | TBD | E | TBD | 1 |  | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change.
SEC | SECMP0031 | Adding UTRN Functionality to SMETS | Yes | No | No | No | Yes | SEC - SECMP0031 | C | 2017-02-20 | E | TBD | E | TBD | 1 |  | Initial Modification Report | On Track | This Modification was presented to the March 2017 Panel. The Panel referred the Modification Proposal to BEIS to seek a view on whether transitional powers set out in Section X2.3(d) should be applied. Subject to the response from BEIS, the Panel will take the appropriate action.
SEC | SECMP0032 | Prioritising Prepayment Customers in No WAN Situations | Yes | No | No | No | Yes | SEC - SECMP0032 | C | 2017-02-20 | E | TBD | E | TBD | 1 |  | Initial Modification Report | On Track | This Modification was presented to the March 2017 Panel. The Panel referred the Modification Proposal to BEIS to seek a view on whether transitional powers set out in Section X2.3(d) should be applied. Subject to the response from BEIS, the Panel will take the appropriate action.
SEC | SECMP0033 | Update to CH Handover Support Materials | Yes | No | No | No | Yes | SEC - SECMP0033 | C | 2017-02-22 | E | TBD | E | 2017-05-11 | 1 | 78 | Modification Report Consutlation | On Track | SECMP0033 has been issued for Modification Report Consutlation until 5th April 2017. The Change Board will vote on SECMP0033 on 19th April 2017.
Note on O19: All estimated implementation dates are the earliest possible implementation dates. These are subject to change.

## A2. Half Hourly Settlement
Area 2. Half Hourly Settlement
Half Hourly Settlement aims to settle all consumers using Half Hourly consumption data.
For more information, please visit the Ofgem website.
Headlines
* Ofgem publish their latest update on Half Hourly Settlement. The update confirmed that the SCR is likely to be launched in Q1 2017-18, with a parallel Request for Information. * BSC Modification P272 'Mandatory Half Hourly Settlement for Profile Classes 5-8' was implemented on 1 April 2017. P271 makes HH Settlement mandatory for all Metering Systems within PCs 5-8 (where capable metering has been installed), as the Proposer believes that the use of Non Half Hourly (NHH) data is not as accurate and masks individual customer behaviour.
Code | Change Ref | Title | A1 | A2 | A3 | A4 | A5 | Timeline Ref | S | Raised | S | Imp Decision | S | Imp Date | Assessment Duration | Implementation Duration | Progression State | RAG Status | Commentary | Drivers
Status | Elective HH Settlement status | Elective Half Hourly Settlement timeline and status | [5 empty] | Elective HH Settlement status | C | 2014-04-04 | C | 2017-06-29 |  |  | 1182 | -42915 |  | ON TRACK | The overall status of Elective Half Hourly Settlement is 'on track'. This is because15 of the 16 live changes are on track. | Ofgem
Status | Mandatory Half Hourly Settlement status | Mandatory Half Hourly Settlement timeline | [5 empty] | Mandatory HH Settlement status | C | 2016-11-11 | E | 2018-06-30 |  |  | 596 | -43281 |  | ON TRACK | The overall status of Mandatory HH Settlement is 'on track'. Based on Ofgem's consultation, it is anticpated that Ofgem will make a how to implement mandatory HHS should be taken by the first half of 2018 following their policy and design work. The proposed approach sets out a ‘potential‘ SCR. | Ofgem
Today | Today | Today's date | [5 empty] | Today | C | 2017-05-09 | C | 2017-05-10 | N | N/A | 1 |  |  | On Track | - | -
BSC | P272 | Mandatory Hlaf Hourly Settlement for Profle Classes 5-8 | Yes | Yes | No | No | No | BSC - P272 | C | 2011-05-20 | C | 2014-10-29 | C | 2017-04-01 | 1258 | 885 | Implemented | On Track | - | -
DCUSA | DCP 160 | Non-Half Hourly (NHH) Notional Capacity | No | Yes | No | No | No | DCUSA - DCP 160 | C | 2013-01-08 | C | 2016-10-18 | N | n/a | 1379 |  | Authority Rejected the change | On Track | Authority Rejected the change | -
DCUSA | DCP 169 | Seasonal Time of Day (SToD) HH Metered Tariffs in the CDCM | No | Yes | No | No | No | DCUSA - DCP 169 | C | 2013-03-13 | E | TBD | E | TBD | 1 |  | Assessment | At Risk | CP on Hold - Working Group is awaiting Ofgem decision on DCP 228 before deciding on how to proceed with DCP 169. DCP 225 is due to be implemented 1 Apr 2018 | -
BSC | P320 | Reporting on Profile Classes 5 – 8 Metering Systems after the implementation of P272 | No | Yes | No | No | No | BSC - P320 | C | 2015-03-13 | C | 2015-09-09 | C | 2017-04-01 | 180 | 570 | Implemented | On Track | - | -
DCUSA | DCP 262 | Schedule 19 Credit/Re-invoice for HH Specific Data | No | Yes | No | No | No | DCUSA - DCP 262 | C | 2016-01-13 | C | 2016-07-29 | C | 2016-09-01 | 198 | 34 | Implemented | On Track | - | -
DCUSA | DCP 268 | DUoS Charging Using HH settlement data | No | Yes | No | No | No | DCUSA - DCP 268 | C | 2016-03-14 | E | TBD | E | 2018-04-01 |  | 748 | Assessment | On Track | Under Development - Working Group developing the CP solution | -
BSC | P338 | Consequential changes to P272 legal text | No | Yes | No | No | No | BSC - P338 | C | 2016-04-14 | C | 2016-04-14 | C | 2017-04-01 | 0 | 352 | Implemented | On Track | - | -
BSC | P339 | Introduction of new Consumption Component Classes for Measurement Classes E-G | No | Yes | No | No | No | BSC - P339 | C | 2016-05-04 | C | 2016-12-08 | C | 2017-04-01 | 218 | 114 | Implemented | On Track | - | -
BSC | CP1466 | Removing SMETS compliant Meters from the scope of BSCP601 ‘Metering Protocol Approval and Compliance Testing’ | No | Yes | No | No | No | BSC - CP1466 | C | 2016-06-14 | C | 2016-12-08 | C | 2017-02-23 | 177 | 77 | Implemented | On track | - | Settlement Reform Advisory Group recommendations
BSC | P346 | Changes to Specific Charges for Elective HH Settlement | No | Yes | No | No | No | BSC - P346 | C | 2016-06-23 | C | 2016-11-10 | C | 2017-04-01 | 140 | 142 | Implemented | On Track | Approved. Awaiting implementation in April Standalone release | -
BSC | P347 | Reduction in R1 Read Threshold | Yes | Yes | No | No | No | BSC - P347 | C | 2016-07-01 | E | 2017-02-10 | C | 2017-04-01 | 224 | 50 | Implemented | On Track | On 19 January the Panel considered the Sendback Direction from the Authority and approved the revised Final Modification Report for P347. The Panel maintained its recomendation to the Authority that P347 should be rejected. The revised Final Modification Report was submitted to the Authority for decision on 19 January 2017. On 30 January 2017 the Authority determined that P347 should be Approved and implemented on 1 April 2017. | -
BSC | CP1469 | Changes to support the implementation of the SRAG’s recommendations | No | Yes | No | No | No | BSC - CP1469 | C | 2016-07-19 | C | 2016-10-04 | C | 2017-06-29 | 77 | 268 | Awaiting Implementation | On track | - | Settlement Reform Advisory Group recommendations
DCUSA | DCP 281 | Changes to Schedule 19 – Portfolio Billing | No | Yes | No | No | No | DCUSA - DCP 281 | C | 2016-09-14 | E | TBD | E | 2019-04-01 |  | 929 | Assessment | On Track | Under Development - Working Group developing the CP solution | -
BSC | CP1474 | Updating the CoMC processes to facilitate the elective HH Settlement of SMETS Meters | No | Yes | No | No | No | BSC - CP1474 | C | 2016-10-14 | C | 2017-01-04 | C | 2017-06-29 | 82 | 176 | Awaiting Implementation | On Track | - | Ofgem’s Elective half-hourly settlement: conclusions paper
BSC | CP1475 | Remove obligation to re-date final NHH Meter readings on CoMC | No | Yes | No | No | No | BSC - CP1475 | C | 2016-10-14 | C | 2017-01-03 | C | 2017-06-29 | 81 | 177 | Awaiting Implementation | On Track | - | -
BSC | BSC Potential Change 14 | Ofgem SCR on HH Settlement | No | Yes | No | No | No | BSC - BSC Potential Change 14 | E | 2017-06-01 | E | 2018-03-01 | E | 2018-06-28 | 273 | 119 | Upcoming | - | - | -

## A3. European Harmonisation
Area 3. European Harmonisation
European harmonisation aims to ensure that the GB energy market is compliant with European obligations.
For more information, please visit the Ofgem website.
Please be aware SQSS changes have also been provided, as the relevant to European Harmonisation. Please also note that there are differing assumptions on the implementation dates for Electricity Balancing Guidelines (EBGL) changes between Code bodies.
Headline
* No updates provided
Code | Change Ref | Title | A1 | A2 | A3 | A4 | A5 | Timeline Ref | S | Raised | S | Imp Decision | S | Imp Date | Assessment Duration | Implementation Duration | Progression State | RAG Status | Commentary | Drivers
Status | European harmonisation status | European harmonisation timeline and status | [5 empty] | European harmonisation status |  | 2015-08-01 | E | 2022-01-01 |  |  | 2345 | -44562 |  | ON TRACK | 11 out of 12 live changes are 'on track'. This gives European Harmonisation an overall 'on track' status. | EU Legislation
Today | Today | Today's date | [5 empty] | Today | C | 2017-05-09 | C | 2017-05-10 | - | N/A | 1 |  |  | ON TRACK | - | -
SQSS | GSR012 | Treatment of Interconnectors | No | No | Yes | No | Yes | SQSS - GSR012 | C | 2010-10-05 | E | TBD | E | TBD | 1 |  | Assessment | At Risk | Workgroup meetings need to re-convene following 1 year hiatus. | -
GC | GC0048 | Requirements for Generators - Implementation of European Network Code | No | No | Yes | No | Yes | GC - GC0048 | C | 2013-07-01 | C | TBD | C | 2018-05-17 | 1 | 1781 | Raised | On Track | This is a workgroup, and it is expected that this workgroup will manage the raising of all additional modifications required to deliver The deadline for EIF is fixed. National Implementation Compliance date is 17/05/2018 | European Regulation/Law
GC | GC0090 | HVDC - Implementation of European Network Code | No | No | Yes | No | Yes | GC - GC0090 | C | 2015-07-01 | C | TBD | C | 2018-09-29 | 1 | 1186 | Raised | On Track | This is a workgroup, and it is expected that this workgroup will manage the raising of all additional modifications required to deliver Deadline for EIF is fixed. National Implementation Compliance date is 29/09/2018 | European Regulation/Law
Milestone | CACM came into force | CACM came into force | [5 empty] | CACM came into force | C | 2015-08-01 |  | 2015-08-02 | - | N/A | 1 |  |  |  |  | ENC
BSC | P329 | Changes to REMIT inside information reporting | No | No | Yes | No | No | BSC - P329 | C | 2015-11-25 | C | 2016-04-19 | C | 2017-06-29 | 146 | 436 | Awaiting Implementation | On Track | - | -
GC | GC0091 | Application of the the Demand Connection Code - Implementation of European Network Code | No | No | Yes | No | Yes | GC - GC0091 | C | 2016-03-01 | C | TBD | C | 2018-09-07 | 1 | 920 | Raised | On Track | This is a workgroup, and it is expected that this workgroup will manage the raising of all additional modifications required to deliver. Deadline for EIF is fixed. National Implementation Compliance date is 07/09/2018 | European Regulation/Law
BSC | P342 | Change to Gate Closure for Energy Contract Volume Notifications | No | No | Yes | No | Yes | BSC - P342 | C | 2016-05-25 | E | 2016-12-08 | C | 2017-11-02 | 197 | 329 | Awaiting Implementation | On Track | - | -
GC | GC0095 | GB implementation workgroup for Transmission System Operation Guideline (TSOG) European Network Code | No | No | Yes | No | Yes | GC - GC0095 | C | 2016-05-27 | E | TBD | C | 2018-10-01 | 1 | 857 | Assessment | On Track | All areas of TSOG are curently held within one workgroup, this may change as modification are raised to deliver respective areas are completed There is a range of Entry into Force dates ranging to October 2018 | EU Regulation/Law
BSC | P344 | Project TERRE implementation into GB market arrangements | No | No | Yes | No | No | BSC - P344 | C | 2016-06-01 | C | 2017-09-21 | E | 2018-09-01 | 477 | 345 | Assessment | On track | Project TERRE is currently set to go-live in Q3 2018. | -
UNC | 0597S | Rules for the release of incremental capacity at Interconnection Points | No | No | Yes | No | Yes | UNC - 0597S | C | 2016-10-10 | E | 2017-03-31 | C | 2017-04-06 | 172 | 6 | Awaiting Implementation | On Track | - | EU CAM
UNC | 0598 | Amendments to Capacity Allocations Mechanisms to comply with EU Capacity Regulations | No | No | Yes | No | Yes | UNC - 0598 | C | 2016-10-10 | E | 2017-03-31 | C | 2017-04-06 | 172 | 6 | Awaiting Implementation | On Track | - | EU CAM
UNC | 0599 | Amendments to Capacity Allocations Mechanisms (Interruptible) to comply with EU Capacity Regulations | No | No | Yes | No | Yes | UNC - 0599 (withdrawn) | C | 2016-10-10 | C | n/a | C | n/a | 1 |  | Withdrawn | - | Withdrawn | EU CAM
GC | GC0097 | European Energy Balancing Guidelines - Replacement Reserves - TERRE | No | No | Yes | No | Yes | GC - GC0097 | E | 2016-11-16 | C | TBD | E | 2019-07-01 | 1 | 957 | Assessment | On Track | This modification maybe required to address changes associated with project TERRE Deadline for EIF is fixed. This mod is set to be implemented Q3 2019. | EU Regulation/Law
Dcode | DCRP1701 | Entry into Force of the EU Network Code “Transmission System Operational Guideline | No | No | Yes | No | Yes | Dcode - DCRP1701 | E | 2016-12-08 | E | TBC | E | TBC | 1 |  | Awaiting authority Determination | On Track | RTA submitted on 09/03/17 | EU Regulation/Law
GC | Grid Code Potential Change 1 | Implementation of CACM European Network Code | No | No | Yes | No | Yes | GC - Grid Code Potential Change 1 | E | 2017-01-01 | C | TBD | E | 2018-01-01 | 1 | 365 | Upcoming | On Track | This modification may be required to address the requirements of the Common Grid Model This mod is currently set to be raised in Q1 2017 Deadline for EIF is fixed. Compliance for CGM is Jan 2018 - and TBC based on methodologies | European Regulation/Law
GC | Grid Code Potential Change 2 | European Energy Balancing Guidelines - General Compliance | No | No | Yes | No | Yes | GC - Grid Code Potential Change 2 | E | 2017-01-01 | E | TBD | E | 2018-07-01 | 1 | 546 | Upcoming | On Track | This modification maybe required to address general compliance requirements of the EB GL The mod if currently set to be raised in Q1 2020. Deadline for EIF is fixed. The mod if set to be implemented in Q3 2021. | EU Regulation/Law
GC | Grid Code Potential Change 5 | European RfG Banding and RfG/HVDC requirements | No | No | Yes | No | Yes | GC - Grid Code Potential Change 5 | E | 2017-04-19 | E | TBD | E | 2018-04-01 | 1 | 347 | Upcoming | On Track | This mod is set to be raised in Q2 2017. This mod is set to be implementedin Q2 2018. | EU Regulation/Law
Milestone | NC ER comes into force | NC ER comes into force | [5 empty] | NC ER comes into force | E | 2017-05-01 | E | 2017-05-02 | - | N/A | 1 |  |  |  |  | ENC
GC | Grid Code Potential Change 6 | RfG and HVDC Voltage and Frequency Response requirements | No | No | Yes | No | Yes | GC - Grid Code Potential Change 6 | E | 2017-04-19 | E | TBD | E | 2018-01-01 | 1 | 257 | Upcoming | On Track | This mod is set to be raised in Q2 2017 Deadline for EIF is fixed. This mod is set to be implemented in Q1 2018. | EU Regulation/Law
BSC | BSC Potential Change 1 | Time of Interconnector Data Submission | No | No | Yes | No | No | BSC - BSC Potential Change 1 | E | 2017-06-01 | E | 2018-03-01 | E | 2018-06-01 | 273 | 92 | Upcoming | - | A Modification is expected to be raised in April 2017 under Grid Code, to address the CACM requirement. If the Grid Code Modification removes the impact on the BSC, this Modification will be redundant. | ENC
GC | Grid Code Potential Change 8 | DCC Technical & Demand Side Response | No | No | Yes | No | Yes | GC - Grid Code Potential Change 8 | E | 2017-06-21 | E | TBD | E | 2018-09-01 | 1 | 437 | Upcoming | On Track | This mod is set to be raised in Q2 2017 Deadline for EIF is fixed. This mod is set to be implemented in Q3 2018. | EU Regulation/Law
GC | Grid Code Potential Change 9 | Interconnector Data Provision | No | No | Yes | No | Yes | GC - Grid Code Potential Change 9 | E | 2017-06-21 | E | TBD | E | 2019-01-01 | 1 | 559 | Upcoming | On Track | This mod is set to be raised in Q2 2017 Deadline for EIF is provisionally Q1 2019 | EU Regulation/Law
Dcode | Dcode Potential Change 3 | To Implement within the Dcode the Fast Fault Current Injection requirements contained within the EU Network Code - Requirements for Generators | No | No | Yes | No | Yes | Dcode - Dcode Potential Change 3 | E | 2017-06-30 | E | TBD | E | TBD | 1 |  | Upcoming | TBC | Depends on National Grid GC 0048 modification | EU Regulation/Law
GC | Grid Code Potential Change 4 | European Emergency & Restoration Code - System Defence & Restoration Plan | No | No | Yes | No | Yes | GC - Grid Code Potential Change 4 | E | 2017-07-01 | E | TBD | E | 2018-07-01 | 1 | 365 | Upcoming | On Track | This mod is set to be raised in Q2 2017. This mod is set to be implemente din Q3 2018. | EU Regulation/Law
GC | Grid Code Potential Change 13 | Market Suspension | No | No | Yes | No | Yes | GC - Grid Code Potential Change 13 | E | 2017-07-01 | E | TBD | E | 2018-10-01 | 1 | 457 | Upcoming | On Track | This mod is set to be raised in Q3 2017 Deadline for EIF is provisionally Q3 2018 | EU Regulation/Law
Milestone | EB GL entry into force | EB GL entry into force | [5 empty] | EB GL entry into force | E | 2017-10-01 | E | 2017-10-02 | - | N/A | 1 |  |  |  |  | ENC
Milestone | Assignment of EB GL where needed | Assignment of EB GL where needed | [5 empty] | Assignment of EB GL where needed | E | 2017-10-01 | E | 2017-10-02 | - | N/A | 1 |  |  |  |  | ENC
Milestone | Application for Exemption from 15 min Settlement | Application for Exemption from 15 min Settlement | [5 empty] | Application for Exemption from 15 min Settlement | E | 2017-10-01 | E | 2017-10-02 | - | N/A | 1 |  |  |  |  | ENC
Milestone | Backstop date for Derogation from Article 55 (imbalance price) | Backstop date for Derogation from Article 55 (Imbalance Price) | [5 empty] | Backstop date for Derogation from Article 55 (Imbalance Price) | E | 2017-10-01 | E | 2017-10-02 | - | N/A | 1 |  |  |  |  | ENC
BSC | BSC Potential Change 2 | Imbalance Price (without derogation) | No | No | Yes | No | No | BSC - BSC Potential Change 2 (without derogation) | E | 2017-10-01 | E | 2018-04-01 | E | 2018-10-01 | 182 | 183 | Upcoming | - | It is assumed that NGET will apply for a derogation for this requirement. If a derogation is approved, this Modification will be included within the scope of Potential Modification 11 "Harmonised Imbalance Settlement". | ENC
BSC | BSC Potential Change 3 | Inclusion of Imbalance Adjustments (without derogation) | No | No | Yes | No | No | BSC - BSC Potential Change 3 (without derogation) | E | 2017-10-01 | E | 2018-04-01 | E | 2018-10-01 | 182 | 183 | Upcoming | - | It is assumed that NGET will apply for a derogation for this requirement. If a derogation be approved, this Modification will be raised on 01/10/19 | ENC
BSC | BSC Potential Change 4 | Align BSC with the Authority's oversight obligation | No | No | Yes | No | No | BSC - BSC Potential Change 4 | E | 2017-10-01 | E | 2018-04-01 | E | 2018-10-01 | 182 | 183 | Upcoming | - | Assignment by BEIS/Ofgem and decisions by Ofgem on how it wishes to approach this requirement | ENC
CUSC | CUSC Potential Change 1 | European Energy Balancing Guidelines - Replacement Reserves | No | No | Yes | No | Yes | CUSC - CUSC Potential Change 1 | E | 2017-10-01 | E | TBD | E | 2018-10-01 | 1 | 365 | Upcoming | On Track | This mod is set to be raised in Q4 2017. This mod is set to be implemented in Q4 2018. | EU Regulation/Law
STC | STC Potential Change 1 | European TSOG - Multi TSO Training Cooperation | No | No | Yes | No | Yes | STC - STC Potential Change 1 | E | 2017-10-01 | E | TBD | C | 2018-10-01 | 1 | 365 | Upcoming | On Track | - | EU Regulation/Law
STC | STC Potential Change 2 | European TSOG Implementation - Data Exchange | No | No | Yes | No | Yes | STC - STC Potential Change 2 | E | 2017-10-01 | E | TBD | C | 2018-10-01 | 1 | 365 | Upcoming | On Track | - | EU Regulation/Law
Dcode | Dcode Potential Change 2 | Changes to DOC 5 of the Distribution Code | No | No | Yes | No | Yes | Dcode - Dcode Potential Change 2 | E | 2017-12-08 | E | TBD | E | TBD | 1 |  | Upcoming | On Track | RTA submitted on 09/03/17 | EU Regulation/Law
GC | Grid Code Potential Change 11 | European TSOG Implementation -Regional Outage Coordination | No | No | Yes | No | Yes | GC - Grid Code Potential Change 11 | E | 2018-01-01 | E | TBD | E | 2018-10-01 | 1 | 273 | Upcoming | On Track | This mod is set to be raised in Q1 2018 Deadline for EIF is provisionally Q4 2018 | EU Regulation/Law
GC | Grid Code Potential Change 12 | European TSOG - Requirements | No | No | Yes | No | Yes | GC - Grid Code Potential Change 12 | E | 2018-01-01 | E | TBD | E | 2018-10-01 | 1 | 273 | Upcoming | On Track | This mod is set to be raised in Q1 2018 Deadline for EIF is provisionally Q4 2018 | EU Regulation/Law
STC | STC Potential Change 3 | European TSOG Implementation -Regional Outage Coordination | No | No | Yes | No | Yes | STC - STC Potential Change 3 | E | 2018-01-01 | E | TBD | C | 2018-12-01 | 1 | 334 | Upcoming | On Track | This mod is set to be raised in Q1 2018 | EU Regulation/Law
Milestone | NGET suspension/restoration proposals | NGET proposals for suspension and restoration | [5 empty] | NGET proposals for suspension and restoration | E | 2018-05-01 | E | 2018-05-02 | - | N/A | 1 |  |  |  |  | ENC
Milestone | ELEXON assigned / delegated | Backstop date for ELEXON assigned / delegated | [5 empty] | Backstop date for ELEXON assigned / delegated | E | 2018-10-01 | E | 2018-10-02 | - | N/A | 1 |  |  |  | GB Legislation for Assignment (would need to changed first, to allow us to be assigned. BEIS will need to write consultation) Derogation requires a contract with NGET, Ofem would need to issue a consultation before this is agreed. | ENC
Milestone | EB GL provisions apply | EB GL provisions apply (assumed) | [5 empty] | EB GL provisions apply (assumed) | E | 2018-10-01 | E | 2018-10-02 | - | N/A | 1 |  |  |  |  | ENC
BSC | BSC Potential Change 5 | Amendments to Imbalance Price | No | No | Yes | No | No | BSC - BSC Potential Change 5 | E | 2018-10-01 | E | 2019-04-01 | E | 2020-04-01 | 182 | 366 | Upcoming | - | If TSO Proposal for activiation purpose do not align with the BSC, this Modification will be raised to amend the imbalance price calculation | ENC
BSC | BSC Potential Change 6 | Align BSC with the TSO's Terms and Conditions | No | No | Yes | No | No | BSC - BSC Potential Change 6 | E | 2018-10-01 | E | 2019-04-01 | E | 2019-10-01 | 182 | 183 | Upcoming | - | If NGET write Ts & Cs in a way that differs from the Ts & Cs of the BSC, this Modification will be raised to align the BSC with the Ts & Cs of the TSO. | ENC
BSC | BSC Potential Change 7 | Project TERRE 2 | No | No | Yes | No | No | BSC - BSC Potential Change 7 | E | 2018-10-01 | E | 2019-07-01 | E | 2020-03-01 | 273 | 244 | Upcoming | - | This Modification will be raised to implement outstanding activities from Project TERRE | ENC
BSC | BSC Potential Change 8 | Unintended exchanges of energy | No | No | Yes | No | No | BSC - BSC Potential Change 8 | E | 2018-10-01 | E | 2019-04-01 | E | 2019-10-01 | 182 | 183 | Upcoming | - | Assignment Certainty on whether this Mod is reaquired, is based on the provision of infomration from NGET, on what will be proposed. | ENC
BSC | BSC Potential Change 9 | NGET proposal on specific products | No | No | Yes | No | No | BSC - BSC Potential Change 9 | E | 2018-10-01 | E | 2019-04-01 | E | 2019-10-01 | 182 | 183 | Upcoming | - | If NGET make a proposal on specific products, an assessment will be required to ensure that the understanding of specific products aligns with the BSC. If understanding of specific products in the TSO proposal, differs from the BSC, this Modification will be raised to align the BSC with the proposal. | ENC
BSC | BSC Potential Change 10 | Market Suspension and Restoration Arrangement | No | No | Yes | No | No | BSC - BSC Potential Change 10 | E | 2018-11-01 | E | 2019-08-01 | E | 2020-05-01 | 273 | 274 | Upcoming | - | If NGET makes proposals for rules concerning the suspension and restoration of market activities; and the rules for balancing energy and imbalance settlement during market suspension, that differ from the BSC, this Modification will be raised to align the BSC with the proposals. | ENC
Milestone | UK leaves EU | UK leaves EU | [5 empty] | UK leaves EU (Confirmed) | E | 2019-03-29 | E | 2019-03-30 | - | N/A | 1 |  |  |  |  | ENC
BSC | BSC Potential Change 3 | Inclusion of Imbalance Adjustments (with derogation) | No | No | Yes | No | No | BSC - BSC Potential Change 3 (with derogation) | E | 2019-04-01 | E | 2020-01-01 | E | 2020-10-01 | 275 | 274 | Upcoming | - | It is assumed that NGET will apply for a derogation for this requirement. If a derogation be approved, this Modification will be raised on 01/10/19 | ENC
BSC | BSC Potential Change 11 | Harmonised Imbalance Settlement (Includes Mod 2 with derogation) | No | No | Yes | No | No | BSC - BSC Potential Change 11 (Inc. Mod 2 with derogation) | E | 2019-04-01 | E | 2020-01-01 | E | 2020-10-01 | 275 | 274 | Upcoming | - | This Modification will be raised to align the BSC with NGETs proposals to harmonise the main features of imbalance settlement If Potential Modification 2 'Imbalance Price' receives a derogation, it will be included within the scope of this Modification. | ENC
BSC | BSC Potential Change 12 | Project mFRR | No | No | Yes | No | No | BSC - BSC Potential Change 12 | E | 2019-04-01 | E | 2021-01-01 | E | 2021-10-01 | 641 | 273 | Upcoming | - | This Modification will be raised, as an extension of the principles introduced under P344 ' Project TERRE' | ENC
Milestone | Backstop date for RR standard products | Backstop date for RR standard products | [5 empty] | Backstop date for RR standard products | E | 2019-10-01 | E | 2019-10-02 | - | N/A | 1 |  |  |  |  | ENC
BSC | BSC Potential Change 13 | Project TERRE 3 | No | No | Yes | No | No | BSC - BSC Potential Change 13 | E | 2019-10-01 | E | 2019-07-01 | E | 2020-02-27 | -92 | 241 | Upcoming | - | This Modification will be raised to implementation outstanding activities from P344 'Project TERRE' | -
GC | Grid Code Potential Change 3 | European Energy Balancing Guidelines - Manual Frequency Restoration Reserves (mFRR) | No | No | Yes | No | Yes | GC - Grid Code Potential Change 3 | E | 2020-01-01 | E | TBD | E | 2021-07-01 | 1 | 547 | Upcoming | On Track | This modification maybe required to address mFRR requirements of the EB GL This mod is set to be raised in Q1 2020. Deadline for EIF is fixed. This mod is set to be implemented in Q3 2021. | EU Regulation/Law
GC | Grid Code Potential Change 10 | Frequency Restoration Reserves | No | No | Yes | No | Yes | GC - Grid Code Potential Change 10 | E | 2020-01-01 | E | TBD | E | 2021-10-01 | 1 | 639 | Upcoming | On Track | This mod is set to be raised in Q1 2020 Deadline for EIF is provisionally Q3 2021 | EU Regulation/Law
CUSC | CUSC Potential Change 2 | European Energy Balancing Guidelines - Manual Frequency Restoration Reserves (mFRR) | No | No | Yes | No | Yes | CUSC - CUSC Potential Change 2 | E | 2020-07-01 | E | TBD | E | 2021-07-01 | 1 | 365 | Upcoming | On Track | This mod is set ot be raised Q3 2020. This mod is set to be implemented in Q3 2021 | EU Regulation/Law
Milestone | The earliest decision on bidding zone change | Earliest decision on bidding zone change | [5 empty] | Earliest decision on bidding zone change | E | 2020-07-01 | E | 2020-07-02 | - | N/A | 1 |  |  |  |  | ENC
Milestone | Backstop date for hamonised Imbalance Settlement | Backstop date for harmonised Imbalance Settlement | [5 empty] | Backstop date for harmonised Imbalance Settlement | E | 2020-10-01 | E | 2020-10-02 | - | N/A | 1 |  |  |  |  | ENC
Milestone | Implementation date for any bidding zone change | Implementation date for any bidding zone change | [5 empty] | Implementation date for any bidding zone change | E | 2021-07-01 | E | 2021-07-02 | - | N/A | 1 |  |  |  |  | ENC
Milestone | Backstop date for FRR standard products | Backstop date for FRR standard products | [5 empty] | Backstop date for FRR standard products | E | 2021-10-01 | E | 2021-10-02 | - | N/A | 1 |  |  |  |  | ENC
Dcode | Dcode Potential Change 1 | Implementation of the requirements of the European Network Code - Demand Connection | No | No | Yes | No | Yes | Dcode - Dcode Potential Change 1 | E | TBD | E | TBD | E | TBD | 1 |  | Upcoming | On Track | Will be raised at the the time of the GC0048 housekeeping mods | EU Regulation/Law
Dcode | Dcode Potential Change 4 | To Implement within the Dcode the Fault Ride Through requirements contained within the EU Network Code - Requirements for Generators | No | No | Yes | No | Yes | Dcode - Dcode Potential Change 4 | E | TBD | E | TBD | E | TBD | 1 |  | Upcoming | TBD | Depends on National Grid GC 0048 modification | EU Regulation/Law
Dcode | Dcode Potential Change 5 | To Implement within the Dcode the Frequency Response requirements contained within the EU Network Code - Requirements for Generators | No | No | Yes | No | Yes | Dcode - Dcode Potential Change 5 | E | TBD | E | TBD | E | TBD | 1 |  | Upcoming | TBD | Depends on National Grid GC 0048 modification | EU Regulation/Law
Dcode | Dcode Potential Change 6 | To Implement within the Dcode the Reactive Power and Voltage Control requirements contained within the EU Network Code - Requirements for Generators | No | No | Yes | No | Yes | Dcode - Dcode Potential Change 6 | E | TBD | E | TBD | E | TBD | 1 |  | Upcoming | TBD | Depends on National Grid GC 0048 modification | EU Regulation/Law
Dcode | Dcode Potential Change 7 | Implementation of the new Engineering Recommendation G98 | No | No | Yes | No | Yes | Dcode - Dcode Potential Change 7 | E | TBD | E | TBD | E | TBD | 1 |  | Upcoming | TBD | Target for public consultation Sept 2017 | EU Regulation/Law
Dcode | Dcode Potential Change 8 | Implementation of the new Engineering Recommendation G99 | No | No | Yes | No | Yes | Dcode - Dcode Potential Change 8 | E | TBD | E | TBD | E | TBD | 1 |  | Upcoming | TBD | TBC | EU Regulation/Law
Dcode | Dcode Potential Change 9 | Implementation of the Transmission System Operators Guidelines | No | No | Yes | No | Yes | Dcode - Dcode Potential Change 9 | E | TBD | E | TBD | E | TBD | 1 |  | Upcoming | TBD | TBC | EU Regulation/Law

## A4. Faster Switching
Area 4. Faster Switching
Faster and more reliable switching aims to improve customers' experience of switching, leading to greater engagement in the retail energy market by designing and implementing a new switching process that is reliable, fast and cost-effective.
For more information, please visit the Ofgem website.
Headlines
* No updates provided
Code | Change Ref | Title | A1 | A2 | A3 | A4 | A5 | Timeline Ref | S | Raised | S | Imp Decision | S | Imp Date | Assessment Duration | Implementation Duration | Progression State | RAG Status | Commentary | Drivers
Status | Faster and more reliable switching status | Faster and more reliable switching timeline and status | [5 empty] | Faster and more reliable switching status | C | 2014-06-16 | E | 2019-01-01 |  |  | 1660 | -43466 |  | ON TRACK | There are currently no live changes being progressed. Howeve, 6 of the 7 milestones are 'on track', this gives faster and more reliable switching an overall 'on track' status. Ofgem view is for new arrangements to go live in 2019. | Ofgem
Today | Today | Today's date | [5 empty] | Today | C | 2017-05-09 | C | 2017-05-10 | N | N/A | 1 |  |  | ON TRACK | - | -
Milestone | Next-day switching consultation | Ofgem consultation 'Moving to reliable next-day switching' | [5 empty] | Next-day switching consultation | C | 2014-06-16 | C | 2014-08-11 | - | N/A | 56 |  |  | ON TRACK | Ofgem consultation on reliable next-day switching. Ofgem proposes to lead a programme of work to deliver these policy proposals for 2019. | -
Milestone | Next-day switching consultation conclusions | Ofgem consultation decision on moving to reliable next-day switching | [5 empty] | Next-day switching consultation conclusions | C | 2015-02-10 | C | 2015-02-11 | - | N/A | 1 |  |  | ON TRACK | The conclusions paper to Ofgem's consultation on reliable next-day switching, published on 10/02/2015. | -
Milestone | SCR switching | Switching Significant Code Review launch statement and request for expressions of interest to participate in Programme workgroups | [5 empty] | SCR switching | C | 2015-11-17 | E | 2019-01-01 | - | N/A | 1141 |  |  | ON TRACK | - | -
Milestone | SCR Blueprint | SCR Blueprint Phase | [5 empty] | SCR Blueprint | E | 2016-01-01 | E | 2017-04-01 | - | N/A | 456 |  |  | ON TRACK | - | -
Milestone | SCR DLS | SCR Detailed-Level Specification Phase | [5 empty] | SCR DLS | E | 2016-01-01 | E | 401769 | - | N/A | 359399 |  |  | ON TRACK |  | -
Milestone | SCR Enactment | SCR Enactment Phase | [5 empty] | SCR Enactment | E | 2016-01-01 | E | 401769 | - | N/A | 359399 |  |  | ON TRACK | - | -
Milestone | Deadline for changes for faster and more reliable switching | Deadline for changes to enable faster and more reliable switching | [5 empty] | Deadline for changes to enable faster and more reliable switching | E | 2019-01-01 | E | 2019-01-02 | - | N/A | 1 |  |  | ON TRACK | - | -

## Code Changes
Code Changes
Code Change highlights any live and upcoming changes to assist in the release management. It also provide headline updates for code specific changes that may also be of importance to the industry.
Headlines
* The new UK Link system being delivered under Project Nexus is on track to go-live on 01 June 2017. There are a number of associated and transitional modifications in place to facilitate the changeover from existing arrangements. Simultaneously settlement-related activities currently performed offline by iGTs will be included within the scope of UK Link and therefore iGTs will become subject to related provisions in the UNC. Please contact the Joint Office for more information. * Ofgem published its final version of its work programme, following its consultation. Includes its Simplification Plan 2017-18.
Code | Change Ref | Title | A1 | A2 | A3 | A4 | A5 | Timeline Ref | S | Raised | S | Imp Decision | S | Imp Date | Assessment Duration | Implementation Duration | Progression State | RAG Status | Commentary | Drivers
BSC | BSC Potential Change 1 | Time of Interconnector Data Submission | No | No | Yes | No | No | BSC - BSC Potential Change 1 | E | 2017-06-01 | E | 2018-03-01 | E | 2018-06-01 | 273 | 365 | Upcoming | - | A Modification is expected to be raised in April 2017 under Grid Code, to address the CACM requirement. If the Grid Code Modification removes the impact on the BSC, this Modification will be redundant. | ENC
BSC | BSC Potential Change 2 | Imbalance Price (without derogation) | No | No | Yes | No | No | BSC - BSC Potential Change 2 | E | 2017-10-01 | E | 2018-04-01 | E | 2018-10-01 | 182 | 365 | Upcoming | - | It is assumed that NGET will apply for a derogation for this requirement. If a derogation is approved, this Modification will be included within the scope of Potential Modification 11 "Harmonised Imbalance Settlement". | ENC
BSC | BSC Potential Change 3 | Inclusion of Imbalance Adjustments (without derogation) | No | No | Yes | No | No | BSC - BSC Potential Change 3 | E | 2017-10-01 | E | 2018-04-01 | E | 2018-10-01 | 182 | 365 | Upcoming | - | It is assumed that NGET will apply for a derogation for this requirement. If a derogation be approved, this Modification will be raised on 01/10/19 | ENC
BSC | BSC Potential Change 4 | Align BSC with the Authority's oversight obligation | No | No | Yes | No | No | BSC - BSC Potential Change 4 | E | 2017-10-01 | E | 2018-04-01 | E | 2018-10-01 | 182 | 365 | Upcoming | - | Assignment by BEIS/Ofgem and decisions by Ofgem on how it wishes to approach this requirement | ENC
BSC | BSC Potential Change 5 | Amendments to Imbalance Price | No | No | Yes | No | No | BSC - BSC Potential Change 5 | E | 2018-10-01 | E | 2019-04-01 | E | 2020-04-01 | 182 | 548 | Upcoming | - | If TSO Proposal for activiation purpose do not align with the BSC, this Modification will be raised to amend the imbalance price calculation | ENC
BSC | BSC Potential Change 6 | Align BSC with the TSO's Terms and Conditions | No | No | Yes | No | No | BSC - BSC Potential Change 6 | E | 2018-10-01 | E | 2019-04-01 | E | 2019-10-01 | 182 | 365 | Upcoming | - | If NGET write Ts & Cs in a way that differs from the Ts & Cs of the BSC, this Modification will be raised to align the BSC with the Ts & Cs of the TSO. | ENC
BSC | BSC Potential Change 7 | Project TERRE 2 | No | No | Yes | No | No | BSC - BSC Potential Change 7 | E | 2018-10-01 | E | 2019-07-01 | E | 2020-03-01 | 273 | 517 | Upcoming | - | This Modification will be raised to implement outstanding activities from Project TERRE | ENC
BSC | BSC Potential Change 8 | Unintended exchanges of energy | No | No | Yes | No | No | BSC - BSC Potential Change 8 | E | 2018-10-01 | E | 2019-04-01 | E | 2019-10-01 | 182 | 365 | Upcoming | - | Assignment Certainty on whether this Mod is reaquired, is based on the provision of infomration from NGET, on what will be proposed. | ENC
BSC | BSC Potential Change 9 | NGET proposal on specific products | No | No | Yes | No | No | BSC - BSC Potential Change 9 | E | 2018-10-01 | E | 2019-04-01 | E | 2019-10-01 | 182 | 365 | Upcoming | - | If NGET make a proposal on specific products, an assessment will be required to ensure that the understanding of specific products aligns with the BSC. If understanding of specific products in the TSO proposal, differs from the BSC, this Modification will be raised to align the BSC with the proposal. | ENC
BSC | BSC Potential Change 10 | Market Suspension and Restoration Arrangement | No | No | Yes | No | No | BSC - BSC Potential Change 10 | E | 2018-11-01 | E | 2019-08-01 | E | 2020-05-01 | 273 | 547 | Upcoming | - | If NGET makes proposals for rules concerning the suspension and restoration of market activities; and the rules for balancing energy and imbalance settlement during market suspension, that differ from the BSC, this Modification will be raised to align the BSC with the proposals. | ENC
BSC | BSC Potential Change 3 | Inclusion of Imbalance Adjustments (with derogation) | No | No | Yes | No | No | BSC - BSC Potential Change 3 | E | 2019-04-01 | E | 2020-01-01 | E | 2020-10-01 | 275 | 549 | Upcoming | - | It is assumed that NGET will apply for a derogation for this requirement. If a derogation be approved, this Modification will be raised on 01/10/19 | ENC
BSC | BSC Potential Change 11 | Harmonised Imbalance Settlement (Includes Mod 2 with derogation) | No | No | Yes | No | No | BSC - BSC Potential Change 11 | E | 2019-04-01 | E | 2020-01-01 | E | 2020-10-01 | 275 | 549 | Upcoming | - | This Modification will be raised to align the BSC with NGETs proposals to harmonise the main features of imbalance settlement If Potential Modification 2 'Imbalance Price' receives a derogation, it will be included within the scope of this Modification. | ENC
BSC | BSC Potential Change 12 | Project mFRR | No | No | Yes | No | No | BSC - BSC Potential Change 12 | E | 2019-04-01 | E | 2021-01-01 | E | 2021-10-01 | 641 | 914 | Upcoming | - | This Modification will be raised, as an extension of the principles introduced under P344 ' Project TERRE' | ENC
BSC | BSC Potential Change 13 | Project TERRE 3 | No | No | Yes | No | No | BSC - BSC Potential Change 13 | E | 2019-01-01 | E | 2019-11-01 | E | 2020-02-27 | 304 | 422 | Upcoming | - | This Modification will be raised to implementation outstanding activities from P344 'Project TERRE' | -
BSC | BSC Potential Change 14 | Ofgem SCR on HH Settlement | No | Yes | No | No | No | BSC - BSC Potential Change 14 | E | 2017-06-01 | E | 2018-03-01 | E | 2018-06-28 | 273 | 392 | Upcoming | - | - | -
BSC | CP1465 | Sending revised Meter Technical Details following a change of Meter Operator Agent | No | No | No | No | Yes | BSC - CP1465 | C | 2016-06-13 | C | 2016-09-06 | C | 2017-02-23 | 85 | 255 | Implemented | On track | - | -
BSC | CP1466 | Removing SMETS compliant Meters from the scope of BSCP601 ‘Metering Protocol Approval and Compliance Testing’ | No | Yes | No | No | No | BSC - CP1466 | C | 2016-06-14 | C | 2016-12-08 | C | 2017-02-23 | 177 | 254 | Implemented | On track | - | Settlement Reform Advisory Group recommendations
BSC | CP1469 | Changes to support the implementation of the SRAG’s recommendations | No | Yes | No | No | No | BSC - CP1469 | C | 2016-07-19 | C | 2016-10-04 | C | 2017-06-29 | 77 | 345 | Awaiting Implementation | On track | - | Settlement Reform Advisory Group recommendations
BSC | CP1470 | Housekeeping Change to CoPs 1, 2, 3 and 5 following P266 | No | No | No | No | No | BSC - CP1470 | C | 2016-08-12 | C | 2016-10-04 | C | 2017-02-23 | 53 | 195 | Implemented | On track | - | -
BSC | CP1471 | Housekeeping - discrepancies in the requirements of the CRA URS | No | No | No | No | Yes | BSC - CP1471 | C | 2016-10-04 | C | 2016-10-04 | C | 2017-02-23 | 0 | 142 | Implemented | On track | - | -
BSC | CP1472 | Removal of SVA proving tests for Meters with a pulse multiplier of one | No | No | No | No | Yes | BSC - CP1472 | C | 2016-09-14 | C | 2017-01-24 | C | 2017-02-23 | 132 | 162 | Implemented | On track | - | BSC Audit Issue Review Group
BSC | CP1473 | Alteration to the LTV Entry Criteria | No | No | No | No | Yes | BSC - CP1473 | C | 2016-10-05 | E | 2017-01-03 | C | 2017-02-23 | 90 | 141 | Implemented | On Track | - | -
BSC | CP1474 | Updating the CoMC processes to facilitate the elective HH Settlement of SMETS Meters | No | Yes | No | No | No | BSC - CP1474 | C | 2016-10-14 | C | 2017-01-04 | C | 2017-06-29 | 82 | 258 | Awaiting Implementation | On Track | - | Ofgem’s Elective half-hourly settlement: conclusions paper
BSC | CP1475 | Remove obligation to re-date final NHH Meter readings on CoMC | No | Yes | No | No | No | BSC - CP1475 | C | 2016-10-14 | C | 2017-01-03 | C | 2017-06-29 | 81 | 258 | Awaiting Implementation | On Track | - | -
BSC | CP1476 | Facilitation of Incremental LLFs | No | No | No | No | Yes | BSC - CP1476 | C | 2016-10-27 | E | 2017-01-31 | E | 2017-06-29 | 96 | 245 | Awaiting Implementation | On Track | - | -
BSC | CP1477 | Updates to BSCP537 Appendix 1 as a result of P283 | No | No | No | No | Yes | BSC - CP1477 | C | 2016-11-07 | E | 2017-04-04 | E | 2017-06-29 | 148 | 234 | Assessment | On Track | - | -
BSC | CP1478 | Automate the loading of the DF Matrix | No | No | No | No | No | BSC - CP1478 | C | 2016-11-22 | E | 2017-02-28 | E | 2017-11-02 | 98 | 345 | Awaiting Implemenation | On Track | - | -
BSC | CP1479 | Updates to the Defined Metering Points in Codes of Practice 1, 2, 3, 5 and 10 | No | No | No | No | Yes | BSC - CP1479 | C | 2016-11-23 | E | 2017-02-20 | E | 2017-11-02 | 89 | 344 | Assessment | On Track | - | -
BSC | CP1480 | Creation of a new authorisation category for corrections to BOA related data | No | No | No | No | No | BSC - CP1480 | C | 2016-11-28 | E | 2017-02-28 | E | 2017-06-29 | 92 | 213 | Assessment | On Track | - | -
BSC | CP1481 | Housekeeping Change to BSCP536 following approval of P339 | No | No | No | No | Yes | BSC - CP1481 | C | 2016-12-14 | E | 2017-01-26 | E | 2017-04-01 | 43 | 108 | Implemented | On Track | - | -
BSC | CP1482 | Upgrade of NHHDA and EAC/AA systems from Oracle 11g to version 12c | No | No | No | No | Yes | BSC - CP1482 | C | 2017-01-05 | E | 2017-05-02 | E | 2017-11-02 | 117 | 301 | Assessment | On Track | - | -
BSC | CP1483 | Changes to BSCP550 – Shared Metering Arrangements | No | No | No | No | Yes | BSC - CP1483 | C | 2017-01-18 | E | 2017-05-30 | E | 2017-11-02 | 132 | 288 | Assessment | On Track | In the SVG meeting on 4 April, the SVG chose to make an amendment to the redlined legal text. Due to the matierial nature of the change, CP1483 was issued for a second consultation on 10 April, with a response deadline of 4 May. This CP will be presented to SVG for decision on 22 May. | -
BSC | CP1484 | Introduce additional validation for DA data flows submitted to the SVAA | No | No | No | No | Yes | BSC - CP1484 | C | 2017-02-08 | E | 2017-05-02 | E | 2017-11-02 | 83 | 267 | Assessment | On Track | - | -
BSC | CP1485 | Validation of power transformer and cable/line loss adjustments | No | No | No | No | Yes | BSC - CP1485 | C | 2017-03-13 | E | 2017-05-22 | E | 2017-11-02 | 70 | 234 | Assessment | On Track | - | -
BSC | CP1486 | VAT Domestic Reverse Charge for Wholesale Supplies of Gas and Electricity | No | No | No | No | Yes | BSC - CP1486 | C | 2017-03-22 | E | 2017-05-22 | E | 2017-06-29 | 61 | 99 | Assessment | On Track | - | -
BSC | P272 | Mandatory Hlaf Hourly Settlement for Profle Classes 5-8 | Yes | Yes | No | No | No | BSC - P272 | C | 2011-05-20 | C | 2014-10-29 | C | 2017-04-01 | 1258 | 2143 | Implemented | On Track | - | -
BSC | P297 | Receipt and Publication of New and Revised Dynamic Data items | No | No | No | No | Yes | BSC - P297 | C | 2013-07-24 | C | 2014-04-28 | C | TBD | 278 |  | Awaiting Implementation | On Track | Due to further EBS delays, the Panel requested a revised Implementation Date for P297. The revised implementation date is TBD | -
BSC | CP1484 | Introduction of Additional SVAA Validation at SVA Run time | No | No | No | No | Yes | BSC - CP1484 | C | 2017-02-08 | E | TBD | E | 2017-11-03 |  | 268 | Assessment | On Track | - | -
BSC | P308 | Alternative security product for securing credit under the BSC | No | No | No | No | Yes | BSC - P308 | C | 2014-06-04 | E | 2017-02-01 | E | TBD | 973 |  | Withdrawn | At risk | The Proposer’s Representative withdrew Modification P308 on 2 February 2017. | -
BSC | P320 | Reporting on Profile Classes 5 – 8 Metering Systems after the implementation of P272 | No | Yes | No | No | No | BSC - P320 | C | 2015-03-13 | C | 2015-09-09 | C | 2017-04-01 | 180 | 750 | Implemented | On Track | - | -
BSC | P321 | Publication of Trading Unit Delivery Mode | No | No | No | No | Yes | BSC - P321 | C | 2015-04-01 | C | 2015-10-08 | C | 2017-06-29 | 190 | 820 | Awaiting Implementation | On Track | P321 was originally approved under Self-Governance on 8 October 2015 for implementation on 30 June 2016. On 5 January 2016, the Panel wrote to the Authority to request the approved Implementation Date be deferred to 3 November 2016. The Authority approved this request on 26 January 2016. On 9 June 2016, the Panel wrote to the Authority to request the approved Implementation Date be deferred to 29 June 2017. The Authority approved this request on 8 August 2016. P321 will therefore be implemented on 29 June 2017 as part of the June 2017 BSC Systems Release. | -
BSC | P325 | Improving the accountability of BSCCo to stakeholders and better aligning BSCCo governance with best practice | No | No | No | No | Yes | BSC - P325 | C | 2015-07-30 | E | TBD | E | TBD |  |  | Assessment | On Track | - | -
BSC | P326 | Introduction of a non-Working Day adjustment to the Credit Cover Percentage calculation | No | No | No | No | Yes | BSC - P326 | C | 2015-08-25 | C | 2016-04-14 | C | 2017-02-23 | 233 | 548 | Implemented | On Track | - | -
BSC | P329 | Changes to REMIT inside information reporting | No | No | Yes | No | No | BSC - P329 | C | 2015-11-25 | C | 2016-04-19 | C | 2017-06-29 | 146 | 582 | Awaiting Implementation | On Track | - | -
BSC | P332 | Revisions to the Supplier Hub Principle | No | No | No | No | Yes | BSC - P332 | C | 2016-01-28 | E | TBD | E | TBD |  |  | Assessment | On Track | - | -
BSC | P335 | Inclusion of Non-BM STOR costs and volumes in the indicative cashout price | No | No | No | No | Yes | BSC - P335 | C | 2016-02-19 | C | 2016-09-19 | C | 2017-11-02 | 213 | 622 | Awaiting Implementation | On Track | - | -
BSC | P336 | Fuel types on the BMRS | No | No | No | No | Yes | BSC - P336 | C | 2016-02-29 | C | 2016-04-14 | C | 2017-11-02 | 45 | 612 | Awaiting Implementation | On Track | - | -
BSC | P338 | Consequential changes to P272 legal text | No | Yes | No | No | No | BSC - P338 | C | 2016-04-14 | C | 2016-04-14 | C | 2017-04-01 | 0 | 352 | Implemented | On Track | - | -
BSC | P339 | Introduction of new Consumption Component Classes for Measurement Classes E-G | No | Yes | No | No | No | BSC - P339 | C | 2016-05-04 | C | 2016-12-08 | C | 2017-04-01 | 218 | 332 | Implemented | On Track | - | -
BSC | P341 | MEL and other data earlier than Gate Closure | No | No | No | No | Yes | BSC - P341 | C | 2016-05-20 | E | 2017-04-01 | E | TBD | 316 |  | Assessment | At risk | Awaiting confirmation from Ofgem and a decision on progression from the Workgroup. | -
BSC | P342 | Change to Gate Closure for Energy Contract Volume Notifications | No | No | Yes | No | Yes | BSC - P342 | C | 2016-05-25 | E | 2016-12-08 | C | 2017-11-02 | 197 | 526 | Awaiting Implementation | On Track | - | -
BSC | P343 | Increase to the number of Supplier IDs that can be held by a Supplier | No | No | No | No | Yes | BSC - P343 | C | 2016-05-26 | C | 2016-11-10 | C | 2017-02-23 | 168 | 273 | Implemented | On Track | - | -
BSC | P344 | Project TERRE implementation into GB market arrangements | No | No | Yes | No | No | BSC - P344 | C | 2016-06-01 | C | 2017-09-21 | E | 2018-09-01 | 477 | 822 | Assessment | On track | Project TERRE is currently set to go-live in Q3 2018. | -
BSC | P346 | Changes to Specific Charges for Elective HH Settlement | No | Yes | No | No | No | BSC - P346 | C | 2016-06-23 | C | 2016-11-10 | C | 2017-04-01 | 140 | 282 | Implemented | On Track | Approved. Awaiting implementation in April Standalone release | -
BSC | P347 | Reduction in R1 Read Threshold | Yes | Yes | No | No | No | BSC - P347 | C | 2016-07-01 | E | 2017-02-10 | C | 2017-04-01 | 224 | 274 | Implemented | On Track | On 19 January the Panel considered the Sendback Direction from the Authority and approved the revised Final Modification Report for P347. The Panel maintained its recomendation to the Authority that P347 should be rejected. The revised Final Modification Report was submitted to the Authority for decision on 19 January 2017. On 30 January 2017 the Authority determined that P347 should be Approved and implemented on 1 April 2017. | -
BSC | P348 | Provision of gross BM Unit data for TNUoS charging | No | No | No | No | Yes | BSC - P348 | C | 2016-07-01 | E | 2017-04-13 | E | 2019-11-07 | 286 | 1224 | Assessment | On Track | This Modification will be progressed in line with P349. | Transmission Network Use of System (TNUoS) Charging changes
BSC | P349 | Facilitating Embedded Generation Triad Avoidance Standstill | No | No | No | No | Yes | BSC - P349 | C | 2016-07-04 | E | 2017-04-13 | E | 2017-06-29 | 283 | 360 | Assessment | On Track | New Embedded Generators will be defined for the purpose of this Modification by Connection Use of System Code (CUSC) Modification Proposal (CMP) 264 ‘Embedded Generation Triad Avoidance Standstill’. The implementation of CMP264 requires both SVA and CVA meter data flows for new embedded generation. It is believed that the Transmission Company already receives the necessary CVA metered data to allow for the benefits of CMP264 to be realised. If this assumption is proved invalid, this Modification will require including CVA as well as SVA registered generators. | -
BSC | P350 | Introduction of a seasonal Zonal Transmission Losses scheme | No | No | No | No | Yes | BSC - P350 | C | 2016-07-05 | E | 2017-03-31 | E | 2018-04-01 | 269 | 635 | Assessment | On Track | The CMA has placed obligations on National Grid to raise a Modification, for implementation by 1 April 2018. If the Modification is not implemented in time, then National Grid will be required to implement the same technical solution on the same date but outside of the BSC. The BSC Panel will make its final reccomendation to Ofgem on 9 Febraury 2017. Ofgem is expected to make its final decision by the end of March 2017. | CMA
BSC | P351 | Align the BSC with changes to the SCR requirements | No | No | No | No | Yes | BSC - P351 | C | 2016-07-29 | C | 2017-01-19 | E | 2017-04-01 | 174 | 246 | Implemented | On Track | Initially rejected by Panel. Report consultation now closed and Final report decision on 19/1/17 | -
BSC | P353 | Fast Track Self-Governance Mod following P324 | No | No | No | No | Yes | BSC - P353 | C | 2016-11-10 | C | 2016-12-08 | C | 2017-01-06 | 28 | 57 | Implemented | On track | - | -
BSC | P354 | Use of ABSVD for non-BM Balancing Services at the metered (MPAN) level | No | No | No | No | Yes | BSC - P354 | C | 11-Jan-17 | E | TBD | E | TBD |  |  | Assessment | - | - | -
CUSC | CMP250 | Stabilising BSUoS with at least a twelve month notice period | No | No | No | No | Yes | CUSC - CMP250 | C | 2015-08-19 | E | 2017-07-10 | E | 2017-07-17 | 691 | 698 | Assessment | At Risk | - | CMP250
CUSC | CMP251 | Removing the error margin in the cap on total TNUoS recovered by generation and introducing a new charging element to TNUoS to ensure compliance with European Commission Regulation 838/2010 | No | No | No | No | Yes | CUSC - CMP251 | C | 2015-08-28 | C | 2016-10-14 | E | TBD | 413 |  | Authority Decision | - | - | -
CUSC | CMP259 | Clarification of decrease in TEC as a Modification | No | No | No | No | Yes | CUSC - CMP259 | C | 2016-05-22 | C | 2016-10-14 | E | TBD | 145 |  | Authority Decision | - | - | -
CUSC | CMP261 | Ensuring the TNUoS paid by Generators in GB in Charging Year 2015/16 is in compliance with the €2.5/MWh annual average limit set in EU Regulation 838/2010 Part B (3) | No | No | No | No | Yes | CUSC - CMP261 | C | 2016-03-11 | C | 2016-11-30 | E | TBD | 264 |  | Authority Decision | - | - | -
CUSC | CMP264 | Embedded Generation Triad Avoidance Standstill | No | No | No | No | Yes | CUSC - CMP264 | C | 2016-05-27 | C | 2016-11-28 | E | TBD | 185 |  | Authority Decision | - | - | -
CUSC | CMP265 | Gross charging of TNUoS for HH demand where embedded generation is in Capacity Market | No | No | No | No | Yes | CUSC - CMP265 | C | 2016-05-27 | C | 2016-11-28 | E | TBD | 185 |  | Authority Decision | - | - | -
CUSC | CMP266 | Removal of Demand TNUoS charging as a barrier to future elective Half Hourly settlement | No | No | No | No | Yes | CUSC - CMP266 | C | 2016-07-05 | C | 2016-11-30 | E | 2016-12-22 | 148 | 170 | Implemented | - | - | -
CUSC | CMP268 | Recognition of sharing by Conventional Carbon plant of Not-Shared Year-Round circuits | No | No | No | No | Yes | CUSC - CMP268 | C | 2016-08-02 | E | TBD | E | TBD |  |  | Workgroup | - | - | -
CUSC | CMP269 | Potential consequential changes to the CUSC as a result of CMP264 | No | No | No | No | Yes | CUSC - CMP269 | C | 2016-08-26 | C | 2016-11-28 | E | TBD | 94 |  | Authority Decision | - | - | Consequential of CMP264
CUSC | CMP270 | Potential consequential changes to the CUSC as a result of CMP265 | No | No | No | No | Yes | CUSC - CMP270 | C | 2016-08-19 | C | 2016-11-28 | E | TBD | 101 |  | Authority Decision | - | - | Consequential of CMP265
CUSC | CMP271 | Improving the cost reflectivity of demand transmission charges | No | No | No | No | Yes | CUSC - CMP271 | C | 2016-09-20 | E | 2018-03-16 | E | 2021-04-01 | 542 | 1654 | Assessment | On Track | - | CMP271
CUSC | CMP272 | Aligning Condition C5 of the CUSC to changes introduced by the Code Governance Review Phase 3 | No | No | No | No | Yes | CUSC - CMP272 | C | 2016-09-29 | E | 2017-03-07 | C | 2017-03-14 | 159 | 166 | Assessment | On Track | - | CMP272
CUSC | CMP274 | Winter TNUoS Time of Use Tariff (TToUT) for Demand TNUoS | No | No | No | No | Yes | CUSC - CMP274 | C | 2016-09-29 | E | 2018-03-16 | E | 2021-04-01 | 533 | 1645 | Assessment | On Track | - | CMP274
CUSC | CMP275 | Transmission Generator Benefits in the provision of ancillary and balancing services – levelling the playing field. | No | No | No | No | Yes | CUSC - CMP275 | C | 2017-01-18 | E | TBD | E | TBD | 1 |  | Assessment | On Track | - | -
CUSC | CMP276 | Socialising TO costs associated with "green policies" | No | No | No | No | Yes | CUSC - CMP276 | C | 2017-02-10 | E | TBD | E | TBD | 1 |  | Raised | On Track | - | -
CUSC | CMP277 | Special License Condition 4J | No | No | No | No | Yes | CUSC - CMP277 | C | 2017-03-31 | E | TBD | E | TBD | 1 |  | Raised | On Track | - | -
CUSC | CMP278 | BSIS 2017 Housekeeping | No | No | No | No | Yes | CUSC - CMP278 | C | 2017-03-31 | E | TBD | E | TBD | 1 |  | Raised | On Track | - | -
CUSC | CUSC Potential Change 1 | European Energy Balancing Guidelines - Replacement Reserves | No | No | Yes | No | Yes | CUSC - CUSC Potential Change 1 | E | 2017-10-01 | E | TBD | E | 2018-10-01 | 1 | 365 | Upcoming | On Track | This mod is set to be raised in Q4 2017. This mod is set to be implemented in Q4 2018. | EU Regulation/Law
CUSC | CUSC Potential Change 2 | European Energy Balancing Guidelines - Manual Frequency Restoration Reserves (mFRR) | No | No | Yes | No | Yes | CUSC - CUSC Potential Change 2 | E | 2020-07-01 | E | TBD | E | 2021-07-01 | 1 | 365 | Upcoming | On Track | This mod is set ot be raised Q3 2020. This mod is set to be implemented in Q3 2021 | EU Regulation/Law
Dcode | DCRP1702 | Implementation of the Ofgem CGR3 recommendation on Significant Code Review | No | No | No | No | Yes | Dcode - DCRP1702 | C | 2016-12-08 | C | 2017-03-31 | C | 2017-04-01 | 113 | 114 | Implemented | On Track | RTA submitted on 09/03/17 | CGR3
Dcode | DCRP1701 | Entry into Force of the EU Network Code “Transmission System Operational Guideline | No | No | Yes | No | Yes | Dcode - DCRP1701 | E | 2016-12-08 | E | TBC | E | TBC | 1 |  | Awaiting authority Determination | On Track | RTA submitted on 09/03/17 | EU Regulation/Law
Dcode | Dcode Potential Change 1 | Implementation of the requirements of the European Network Code - Demand Connection | No | No | Yes | No | Yes | Dcode - Dcode Potential Change 1 | E | TBD | E | TBD | E | TBD | 1 |  | Upcoming | On Track | Will be raised at the the time of the GC0048 housekeeping mods | EU Regulation/Law
Dcode | Dcode Potential Change 2 | Changes to DOC 5 of the Distribution Code | No | No | Yes | No | Yes | Dcode - Dcode Potential Change 2 | E | 2017-12-08 | E | TBD | E | TBD | 1 |  | Upcoming | On Track | RTA submitted on 09/03/17 | EU Regulation/Law
Dcode | Dcode Potential Change 3 | To Implement within the Dcode the Fast Fault Current Injection requirements contained within the EU Network Code - Requirements for Generators | No | No | Yes | No | Yes | Dcode - Dcode Potential Change 3 | E | 2017-06-30 | E | TBD | E | TBD | 1 |  | Upcoming | TBC | Depends on National Grid GC 0048 modification | EU Regulation/Law
Dcode | Dcode Potential Change 4 | To Implement within the Dcode the Fault Ride Through requirements contained within the EU Network Code - Requirements for Generators | No | No | Yes | No | Yes | Dcode - Dcode Potential Change 4 | E | TBD | E | TBD | E | TBD | 1 |  | Upcoming | TBD | Depends on National Grid GC 0048 modification | EU Regulation/Law
Dcode | Dcode Potential Change 5 | To Implement within the Dcode the Frequency Response requirements contained within the EU Network Code - Requirements for Generators | No | No | Yes | No | Yes | Dcode - Dcode Potential Change 5 | E | TBD | E | TBD | E | TBD | 1 |  | Upcoming | TBD | Depends on National Grid GC 0048 modification | EU Regulation/Law
Dcode | Dcode Potential Change 6 | To Implement within the Dcode the Reactive Power and Voltage Control requirements contained within the EU Network Code - Requirements for Generators | No | No | Yes | No | Yes | Dcode - Dcode Potential Change 6 | E | TBD | E | TBD | E | TBD | 1 |  | Upcoming | TBD | Depends on National Grid GC 0048 modification | EU Regulation/Law
Dcode | Dcode Potential Change 7 | Implementation of the new Engineering Recommendation G98 | No | No | Yes | No | Yes | Dcode - Dcode Potential Change 7 | E | TBD | E | TBD | E | TBD | 1 |  | Upcoming | TBD | Target for public consultation Sept 2017 | EU Regulation/Law
Dcode | Dcode Potential Change 8 | Implementation of the new Engineering Recommendation G99 | No | No | Yes | No | Yes | Dcode - Dcode Potential Change 8 | E | TBD | E | TBD | E | TBD | 1 |  | Upcoming | TBD | TBC | EU Regulation/Law
Dcode | Dcode Potential Change 9 | Implementation of the Transmission System Operators Guidelines | No | No | Yes | No | Yes | Dcode - Dcode Potential Change 9 | E | TBD | E | TBD | E | TBD | 1 |  | Upcoming | TBD | TBC | EU Regulation/Law
DCUSA | DCP 138 | Implementation of alternative network use factor (NUF) calculation method in EDCM | No | No | No | No | No | DCUSA - DCP 138 | C | 2012-06-18 | C | 2015-10-09 | C | 2017-04-01 | 1208 | 1748 | Implemented | On Track | - | -
DCUSA | DCP 160 | Non-Half Hourly (NHH) Notional Capacity | No | Yes | No | No | No | DCUSA - DCP 160 | C | 2013-01-08 | C | 2016-10-18 | n/a | n/a | 1379 |  | Authority Rejected the change | On Track | Authority Rejected the change | -
DCUSA | DCP 161 | Excess Capacity Charges | No | No | No | No | No | DCUSA - DCP 161 | C | 2013-02-06 | C | 2015-10-21 | C | 2018-04-01 | 987 | 1880 | Awaiting Implementation | On Track | - | -
DCUSA | DCP 169 | Seasonal Time of Day (SToD) HH Metered Tariffs in the CDCM | No | Yes | No | No | No | DCUSA - DCP 169 | C | 2013-03-13 | E | TBD | E | TBD | 1 |  | Assessment | At Risk | CP on Hold - Working Group is awaiting Ofgem decision on DCP 228 before deciding on how to proceed with DCP 169. DCP 225 is due to be implemented 1 Apr 2018 | -
DCUSA | DCP 181 | Previous Connection Terms Enduring | No | No | No | No | No | DCUSA - DCP 181 | C | 2013-06-17 | C | 2016-06-15 | C | 2016-10-01 | 1094 | 1202 | Implemented | On Track | - | -
DCUSA | DCP 204 | Smart Metering Related Amendments to Schedule 8 | Yes | No | No | No | No | DCUSA - DCP 204 | C | 2014-02-27 | C | 2016-02-23 | C | 2016-09-01 | 726 | 917 | Implemented | On Track | - | -
DCUSA | DCP 209 | Resolving Unregistered Customers | No | No | No | No | No | DCUSA - DCP 209 | C | 2014-05-08 | C | 2016-08-30 | C | 2016-10-01 | 845 | 877 | Implemented | On Track | - | -
DCUSA | DCP 222 | Non Billing Of Excess Reactive Power Charges | No | No | No | No | No | DCUSA - DCP 222 | C | 2014-12-02 | C | 2016-08-15 | C | 2018-04-01 | 622 | 1216 | Awaiting Implementation | On Track | - | -
DCUSA | DCP 226 | Housekeeping 66/72/73/77/80 | No | No | No | No | Yes | DCUSA - DCP 226 | C | 2015-01-05 | E | TBD | E | TBD |  |  | Assessment | At Risk | CP on Hold - housekeeping change to review refrences throuout the DCUSA Document. Work on this is to be carried out after the 1 October 2016 DCUSA Release. | -
DCUSA | DCP 227 | Removing the inconsistency in the application of Peaking Probabilities in the CDCM | No | No | No | No | No | DCUSA - DCP 227 | C | 2015-01-13 | C | 2015-10-21 | C | 2017-04-01 | 281 | 809 | Implemented | On Track | - | -
DCUSA | DCP 228 | Revenue Matching in the CDCM | No | No | No | No | No | DCUSA - DCP 228 | C | 2015-01-13 | C | 2016-09-08 | C | 2018-04-01 | 604 | 1174 | Awaiting Implementation | On Track | - | -
DCUSA | DCP 234 | Merging the PCDM and extended PCDM | No | No | No | No | No | DCUSA - DCP 234 | C | 2015-02-27 | C | 2016-08-03 | C | 2018-04-01 | 523 | 1129 | Awaiting Implementation | On Track | - | -
DCUSA | DCP 243 | Treatment of Customer Contributions in the CDCM | No | No | No | No | No | DCUSA - DCP 243 | C | 2015-06-05 | E | TBD | E | TBD | 1 |  | Assessment | On Track | Under Development - Working Group developing the CP solution | -
DCUSA | DCP 244 | MOP Leaving Site for Cat A Situations | No | No | No | No | No | DCUSA - DCP 244 | C | 2015-06-19 | E | TBD | E | TBD | 1 |  | Assessment | At Risk | CP on Hold - Working Group is waiting for Operational Delivery Group (ODG) to develop MOP guidance on leaving site where there is a category A situation. | -
DCUSA | DCP 251 | Clarification And Extension Of The Application Of LDNO Tariffs Under The CDCM | No | No | No | No | No | DCUSA - DCP 251 | C | 2015-10-15 | E | TBD | E | TBD | 1 |  | Assessment | On Track | Under Development - Working Group developing the CP solution DCP251/2 WG meeting indicated that the change declaration may be issued in June 2017, with an Ofgem decision anticipated in August 2017 | -
DCUSA | DCP 252 | Clarification And Extension Of The Application Of Portfolio Tariffs Under The EDCM | No | No | No | No | No | DCUSA - DCP 252 | C | 2015-10-15 | E | TBD | E | TBD | 1 |  | Assessment | On Track | Under Development - Working Group developing the CP solution DCP251/2 WG meeting indicated that the change declaration may be issued in June 2017, with an Ofgem decision anticipated in August 2017 | -
DCUSA | DCP 253 | Retightening and remaking of whole current metering system terminal connections. | No | No | No | No | No | DCUSA - DCP 253 | C | 2015-11-03 | C | 2016-09-21 | C | 2016-09-01 | 323 | 303 | Implemented | On Track | - | -
DCUSA | DCP 255 | Changes to Electricity (Connection Charges) Regulations 2002 | No | No | No | No | No | DCUSA - DCP 255 | C | 2015-11-06 | E | TBD | E | TBD | 1 |  | Assessment | On Track | The Working Group are awaiting the receipt of the final ECCR 2016 legal text from BEIS (formaly DECC) before progressing this change. | -
DCUSA | DCP 256 | Change to DCUSA to mitigate risks of non-payment of non-payment of DCUSA invoices | No | No | No | No | No | DCUSA - DCP 256 | C | 2015-11-10 | C | 2016-09-21 | C | 2016-10-01 | 316 | 326 | Implemented | On Track | - | -
DCUSA | DCP 262 | Schedule 19 Credit/Re-invoice for HH Specific Data | No | Yes | No | No | No | DCUSA - DCP 262 | C | 2016-01-13 | C | 2016-07-29 | C | 2016-09-01 | 198 | 232 | Implemented | On Track | - | -
DCUSA | DCP 263 | NTC DEH Gap | No | No | No | No | No | DCUSA - DCP 263 | C | 2016-01-22 | E | 17/01/201 | E | 2017-02-23 |  | 398 | Implemented | On Track | Change Report issued for Voting | -
DCUSA | DCP 264 | Introduction of Energy Theft Tip Off Line Service | No | No | No | No | No | DCUSA - DCP 264 | C | 2016-02-15 | C | 2016-08-15 | C | 2016-08-22 | 182 | 189 | Implemented | On Track | - | -
DCUSA | DCP 266 | The calculation and application of IDNO discounts | No | No | No | No | No | DCUSA - DCP 266 | C | 2016-03-09 | E | n/a | E | n/a | 1 |  | Assessment | On Track | Under Development - Working Group developing the CP solution | -
DCUSA | DCP 267 | Introduction of a new definition for 'Confirmed Theft' | No | No | No | No | No | DCUSA - DCP 267 | C | 2016-03-09 | C | 2016-09-14 | C | 2016-11-03 | 189 | 239 | Implemented | On Track | - | -
DCUSA | DCP 268 | DUoS Charging Using HH settlement data | No | Yes | No | No | No | DCUSA - DCP 268 | C | 2016-03-14 | E | TBD | E | 2018-04-01 |  | 748 | Assessment | On Track | Under Development - Working Group developing the CP solution | -
DCUSA | DCP 269 | Revenue Protection Service Withdrawal Period | No | No | No | No | No | DCUSA - DCP 269 | C | 2016-04-25 | C | 2016-07-12 | C | 2016-09-01 | 78 | 129 | Implemented | On Track | - | -
DCUSA | DCP 270 | Removal of HV Medium tariff from CDCM | No | No | No | No | No | DCUSA - DCP 270 | C | 2016-04-28 | C | 2017-11-16 | n/a | n/a | 567 |  | Rejected | On Track | Authority Rejected the change | -
DCUSA | DCP 271 | TRAS - Process and Costs of Providing Additional Hunter Facilities | No | No | No | No | No | DCUSA - DCP 271 | C | 2016-05-11 | C | 2016-09-15 | C | 2016-11-03 | 127 | 176 | Implemented | On Track | - | -
DCUSA | DCP 272 | TRAS – Amendment of Schedule 25 Appendix 2 | No | No | No | No | No | DCUSA - DCP 272 | C | 2016-05-11 | C | 2016-09-15 | C | 2016-11-03 | 127 | 176 | Implemented | On Track | - | -
DCUSA | DCP 273 | Align CDCM table 1001 (target revenue) to latest Schedule 15 template | No | No | No | No | No | DCUSA - DCP 273 | C | 2016-05-18 | C | 2016-10-14 | C | 2018-04-01 | 149 | 683 | Awaiting Implementation | On Track | - | -
DCUSA | DCP 274 | The application of export capacity charges in the EDCM | No | No | No | No | No | DCUSA - DCP 274 | C | 2016-06-10 | E | TBD | E | 2018-04-01 | 1 | 660 | Assessment | On Track | Under Development - Working Group developing the CP solution | -
DCUSA | DCP 275 | Code Governance Review 3 & SLC 22 | No | No | No | No | No | DCUSA - DCP 275 | C | 2016-06-10 | C | 2016-11-15 | C | 2017-02-23 | 158 | 258 | Implemented | On Track | - | -
DCUSA | DCP 276 | Amendments to CDCM LV Substation Tariff ‘Note 5’ | No | No | No | No | No | DCUSA - DCP 276 | C | 2016-07-04 | C | 2016-09-14 | C | 2016-11-03 | 72 | 122 | Implemented | On Track | - | -
DCUSA | DCP 277 | Schedule 25 – Amendment to Appendix 2 - Conditionality | No | No | No | No | No | DCUSA - DCP 277 | C | 2016-07-13 | C | 2016-11-17 | C | 2017-02-23 | 127 | 225 | Implemented | On Track | - | -
DCUSA | DCP 278 | Allocation of Users to the ETTOS Secure Email Service | No | No | No | No | No | DCUSA - DCP 278 | C | 2016-07-13 | C | 2016-12-15 | C | 2017-02-23 | 155 | 225 | Implemented | On Track | - | -
DCUSA | DCP 279 | Linking Credit Cover to the Annual Iteration Process | No | No | No | No | No | DCUSA - DCP 279 | C | 2016-07-29 | C | 2016-12-23 | C | 2017-02-23 | 147 | 209 | Implemented | On Track | - | -
DCUSA | DCP 280 | Clarification of TRAS Accession Process | No | No | No | No | No | DCUSA - DCP 280 | C | 2016-08-18 | C | 2016-12-15 | C | 2017-02-23 | 119 | 189 | Implemented | On Track | The voting period was extended to align with the equivilent SPAA CP (CP16/346) | -
DCUSA | DCP 281 | Changes to Schedule 19 – Portfolio Billing | No | Yes | No | No | No | DCUSA - DCP 281 | C | 2016-09-14 | E | TBD | E | 2019-04-01 |  | 929 | Assessment | On Track | Under Development - Working Group developing the CP solution | -
DCUSA | DCP 282 | Embedded Distribution Network Operator (EDNO) UMSO | No | No | No | No | No | DCUSA - DCP 282 | C | 2016-09-14 | E | 2017-03-14 | E | TBD | 181 |  | Assessment | On Track | Under Development - Working Group developing the CP solution | -
DCUSA | DCP 283 | The calculation of generation credits in the CDCM | No | No | No | No | No | DCUSA - DCP 283 | C | 2016-10-12 | E | TBD | E | 2019-04-01 | 1 | 901 | Assessment | On Track | Under Development - Working Group developing the CP solution | -
DCUSA | DCP 284 | The application of scaling to generation credits in the CDCM | No | No | No | No | No | DCUSA - DCP 284 | C | 2016-10-12 | E | TBD | E | 2019-04-01 | 1 | 901 | Assessment | On Track | Under Development - Working Group developing the CP solution | -
DCUSA | DCP 285 | Schedule 23, Appendix 1 SLC References | No | No | No | No | No | DCUSA - DCP 285 | C | 2016-10-12 | E | 2017-01-24 | E | 2017-02-23 | 104 | 134 | Implemented | On Track | Under Development - legal text being updated | -
DCUSA | DCP 286 | Formalising the Theft Steering Group | No | No | No | No | No | DCUSA - DCP 286 | C | 2016-11-09 | E | TBD | E | TBD | 1 |  | Assessment | On Track | Under Development - Definition Stage | -
DCUSA | DCP 287 | Generation Credits in the EDCM | No | No | No | No | No | DCUSA - DCP 287 | C | 2016-11-11 | E | TBD | E | 2019-04-01 | 1 | 871 | Assessment | On Track | - | -
DCUSA | DCP 288 | Introduction of the Electricity Theft Detection Incentive Scheme | No | No | No | No | No | DCUSA - DCP 288 | C | 2016-12-12 | E | TBD | E | TBD | 1 |  | Assessment | On Track | - | -
DCUSA | DCP 289 | Creation of Distribution Charging Methodology Development Group | No | No | No | No | No | DCUSA - DCP 289 | C | 2016-12-16 | E | TBD | E | TBD | 1 |  | Assessment | On Track | - | -
DCUSA | DCP 290 | Housekeeping Change to Update PCDM Model References | No | No | No | No | No | DCUSA - DCP 290 | C | 2017-01-17 | E | TBD | C | 2018-04-01 | 1 | 439 | Awaiting Implementation | On Track | - | -
DCUSA | DCP 291 | Application of Generation Credits to EDCM Customers | No | No | No | No | No | DCUSA - DCP 291 | E | 2017-02-17 | E | TBD | E | 2019-04-01 | 1 | 773 | Definition | On Track | - | -
DCUSA | DCP 292 | Align DCUSA Schedule 15 table 3 to the CDCM tariff structure following the approval DCP 222 ‘Non billing of Excess Reactive Power Charges’ | No | No | No | No | No | DCUSA - DCP 292 | E | 2017-02-10 | E | TBD | E | 2017-06-29 | 1 | 139 | Change Report | On Track | - | -
DCUSA | DCP 293 | Charging Methodology Cut-off Date | No | No | No | No | No | DCUSA - DCP 293 | E | 2001-02-14 | E | TBD | E | 2017-10-01 | 1 | 6073 | Definition | On Track | - | -
DCUSA | DCP 294 | Capacity Management following acceptance of Connection Offer | No | No | No | No | No | DCUSA - DCP 294 | C | 2017-03-01 | E | 2017-10-17 | E | 2017-11-02 | 230 | 246 | Definition | On Track |  | N/A
DCUSA | DCP 295 | CVA Registrants acceding to the DCUSA | No | No | No | No | No | DCUSA - DCP 295 | C | 2017-03-07 | E | TBC | E | TBC | 1 |  | Raised | On Track |  | N/A
GC | GC0048 | Requirements for Generators - Implementation of European Network Code | No | No | Yes | No | Yes | GC - GC0048 | C | 2013-07-01 | C | TBD | C | 2018-05-17 | 1 | 1781 | Raised | On Track | This is a workgroup, and it is expected that this workgroup will manage the raising of all additional modifications required to deliver The deadline for EIF is fixed. National Implementation Compliance date is 17/05/2018 | European Regulation/Law
GC | GC0077 | Suppression of Sub-Synchronous Resonance from Series Capacitive Compensation | No | No | No | No | Yes | GC - GC0077 | C | 2013-08-14 | E | 2017-03-01 | E | 2017-04-01 | 1295 | 1326 | Assessment | On Track | - | -
GC | GC0079 | GC0035 / GC0079 Frequency Changes during Large Disturbances and their effect on the total system - Phase 1 & 2 | No | No | No | No | Yes | GC - GC0079 | C | 2008-05-21 | E | TBD | E | TBD | 1 |  | Assessment | At Risk | Ongoing for 8 years with with deliberations over funding arrangements to be decided. | -
GC | GC0086 | Open Governance | No | No | No | No | Yes | GC - GC0086 | C | 2014-07-02 | E | 2017-02-01 | E | 2017-03-01 | 945 | 973 | Assessment | On Track | - | -
GC | GC0087 | Requirements for Generators Frequency Provisions | No | No | No | No | Yes | GC - GC0087 | C | 2014-11-04 | E | 2017-07-01 | E | 2017-08-01 | 970 | 1001 | Assessment | On Track | - | GC0022
GC | GC0090 | HVDC - Implementation of European Network Code | No | No | Yes | No | Yes | GC - GC0090 | C | 2015-07-01 | C | TBD | C | 2018-09-29 | 1 | 1186 | Raised | On Track | This is a workgroup, and it is expected that this workgroup will manage the raising of all additional modifications required to deliver Deadline for EIF is fixed. National Implementation Compliance date is 29/09/2018 | European Regulation/Law
GC | GC0091 | Application of the the Demand Connection Code - Implementation of European Network Code | No | No | Yes | No | Yes | GC - GC0091 | C | 2016-03-01 | C | TBD | C | 2018-09-07 | 1 | 920 | Raised | On Track | This is a workgroup, and it is expected that this workgroup will manage the raising of all additional modifications required to deliver. Deadline for EIF is fixed. National Implementation Compliance date is 07/09/2018 | European Regulation/Law
GC | GC0095 | GB implementation workgroup for Transmission System Operation Guideline (TSOG) European Network Code | No | No | Yes | No | Yes | GC - GC0095 | C | 2016-05-27 | E | TBD | C | 2018-10-01 | 1 | 857 | Assessment | On Track | All areas of TSOG are curently held within one workgroup, this may change as modification are raised to deliver respective areas are completed There is a range of Entry into Force dates ranging to October 2018 | EU Regulation/Law
GC | GC0096 | Energy Storage | No | No | No | No | Yes | GC - GC0096 | C | 2016-05-18 | E | 2017-05-01 | E | 2017-06-01 | 348 | 379 | Assessment | On Track | - | -
GC | GC0097 | European Energy Balancing Guidelines - Replacement Reserves - TERRE | No | No | Yes | No | Yes | GC - GC0097 | E | 2016-11-16 | C | TBD | E | 2019-07-01 | 1 | 957 | Assessment | On Track | This modification maybe required to address changes associated with project TERRE Deadline for EIF is fixed. This mod is set to be implemented Q3 2019. | EU Regulation/Law
GC | Grid Code Potential Change 1 | Implementation of CACM European Network Code | No | No | Yes | No | Yes | GC - Grid Code Potential Change 1 | E | 2017-01-01 | C | TBD | E | 2018-01-01 | 1 | 365 | Upcoming | On Track | This modification may be required to address the requirements of the Common Grid Model This mod is currently set to be raised in Q1 2017 Deadline for EIF is fixed. Compliance for CGM is Jan 2018 - and TBC based on methodologies | European Regulation/Law
GC | Grid Code Potential Change 2 | European Energy Balancing Guidelines - General Compliance | No | No | Yes | No | Yes | GC - Grid Code Potential Change 2 | E | 2017-01-01 | E | TBD | E | 2018-07-01 | 1 | 546 | Upcoming | On Track | This modification maybe required to address general compliance requirements of the EB GL The mod if currently set to be raised in Q1 2020. Deadline for EIF is fixed. The mod if set to be implemented in Q3 2021. | EU Regulation/Law
GC | Grid Code Potential Change 3 | European Energy Balancing Guidelines - Manual Frequency Restoration Reserves (mFRR) | No | No | Yes | No | Yes | GC - Grid Code Potential Change 3 | E | 2020-01-01 | E | TBD | E | 2021-07-01 | 1 | 547 | Upcoming | On Track | This modification maybe required to address mFRR requirements of the EB GL This mod is set to be raised in Q1 2020. Deadline for EIF is fixed. This mod is set to be implemented in Q3 2021. | EU Regulation/Law
GC | Grid Code Potential Change 4 | European Emergency & Restoration Code - System Defence & Restoration Plan | No | No | Yes | No | Yes | GC - Grid Code Potential Change 4 | E | 2017-07-01 | E | TBD | E | 2018-07-01 | 1 | 365 | Upcoming | On Track | This mod is set to be raised in Q2 2017. This mod is set to be implemente din Q3 2018. | EU Regulation/Law
GC | Grid Code Potential Change 5 | European RfG Banding and RfG/HVDC requirements | No | No | Yes | No | Yes | GC - Grid Code Potential Change 5 | E | 2017-04-19 | E | TBD | E | 2018-04-01 | 1 | 347 | Upcoming | On Track | This mod is set to be raised in Q2 2017. This mod is set to be implementedin Q2 2018. | EU Regulation/Law
GC | Grid Code Potential Change 6 | RfG and HVDC Voltage and Frequency Response requirements | No | No | Yes | No | Yes | GC - Grid Code Potential Change 6 | E | 2017-04-19 | E | TBD | E | 2018-01-01 | 1 | 257 | Upcoming | On Track | This mod is set to be raised in Q2 2017 Deadline for EIF is fixed. This mod is set to be implemented in Q1 2018. | EU Regulation/Law
GC | Grid Code Potential Change 7 | RfG and HVDC Compliance and System Management | No | No | Yes | No | Yes | GC - Grid Code Potential Change 7 | E | 2017-06-21 | E | TBD | E | 2018-01-01 | 1 | 194 | Upcoming | On Track | This mod is set to be raised in Q2 2017 Deadline for EIF is fixed. This mod is set to be implemented in Q1 2018. | EU Regulation/Law
GC | Grid Code Potential Change 8 | DCC Technical & Demand Side Response | No | No | Yes | No | Yes | GC - Grid Code Potential Change 8 | E | 2017-06-21 | E | TBD | E | 2018-09-01 | 1 | 437 | Upcoming | On Track | This mod is set to be raised in Q2 2017 Deadline for EIF is fixed. This mod is set to be implemented in Q3 2018. | EU Regulation/Law
GC | Grid Code Potential Change 9 | Interconnector Data Provision | No | No | Yes | No | Yes | GC - Grid Code Potential Change 9 | E | 2017-06-21 | E | TBD | E | 2019-01-01 | 1 | 559 | Upcoming | On Track | This mod is set to be raised in Q2 2017 Deadline for EIF is provisionally Q1 2019 | EU Regulation/Law
GC | Grid Code Potential Change 10 | Frequency Restoration Reserves | No | No | Yes | No | Yes | GC - Grid Code Potential Change 10 | E | 2020-01-01 | E | TBD | E | 2021-10-01 | 1 | 639 | Upcoming | On Track | This mod is set to be raised in Q1 2020 Deadline for EIF is provisionally Q3 2021 | EU Regulation/Law
GC | Grid Code Potential Change 11 | European TSOG Implementation -Regional Outage Coordination | No | No | Yes | No | Yes | GC - Grid Code Potential Change 11 | E | 2018-01-01 | E | TBD | E | 2018-10-01 | 1 | 273 | Upcoming | On Track | This mod is set to be raised in Q1 2018 Deadline for EIF is provisionally Q4 2018 | EU Regulation/Law
GC | Grid Code Potential Change 12 | European TSOG - Requirements | No | No | Yes | No | Yes | GC - Grid Code Potential Change 12 | E | 2018-01-01 | E | TBD | E | 2018-10-01 | 1 | 273 | Upcoming | On Track | This mod is set to be raised in Q1 2018 Deadline for EIF is provisionally Q4 2018 | EU Regulation/Law
GC | Grid Code Potential Change 13 | Market Suspension | No | No | Yes | No | Yes | GC - Grid Code Potential Change 13 | E | 2017-07-01 | E | TBD | E | 2018-10-01 | 1 | 457 | Upcoming | On Track | This mod is set to be raised in Q3 2017 Deadline for EIF is provisionally Q3 2018 | EU Regulation/Law
SEC | SECMP0002 | Add New Command to Reset Debt Registers | Yes | No | No | No | Yes | SEC - SECMP0002 | C | 2016-02-19 | E | TBD | E | 2018-11-01 | 1 | 986 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0004 | Inclusion of Device Serial Number data item in the Smart Metering Inventory | Yes | No | No | No | Yes | SEC - SECMP0004 | C | 2016-02-19 | E | TBD | E | 2018-06-28 | 1 | 860 | Modification Report consultation | On Track | SECMP0004 has been issued for Modification Report Consutlation until 5th April 2017. The Change Board will vote on SECMP0004 on 19th April 2017. | -
SEC | SECMP0005 | Include Tariff and Register Labels in SMETS2 Devices | Yes | No | No | No | Yes | SEC - SECMP0005 | C | 2016-03-01 | E | TBD | E | 2018-11-01 | 1 | 975 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0006 | Specifying the number of digits for device display | Yes | No | No | No | Yes | SEC - SECMP0006 | C | 2016-03-01 | E | TBD | E | 2018-11-01 |  | 975 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0007 | Firmware updates to mandated HAN devices | Yes | No | No | No | Yes | SEC - SECMP0007 | C | 2016-03-01 | E | TBD | E | 2018-11-01 | 1 | 975 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0008 | Provision of a Service Request error response for quarantined Service Requests | Yes | No | No | No | Yes | SEC - SECMP0008 | C | 2016-03-01 | E | TBD | E | 2018-06-28 | 1 | 849 | Modification Report consultation | On Track | SECMP0008 has been issued for Modification Report Consutlation until 5th April 2017. The Change Board will vote on SECMP0008 on 19th April 2017. | -
SEC | SECMP0009 | Centralised Firmware Library | Yes | No | No | No | Yes | SEC - SECMP0009 | C | 2016-03-01 | E | TBD | E | 2018-11-01 | 1 | 975 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0010 | Introduction of triage arrangements for Communication Hubs | Yes | No | No | No | Yes | SEC - SECMP0010 | C | 2016-03-02 | E | TBD | E | 2018-11-01 | 1 | 974 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0011 | Inclusion of Meter Asset Provider Participant Code (MAP ID) Participant Codes in the Smart Metering Inventory | Yes | No | No | No | Yes | SEC - SECMP0011 | C | 2016-03-22 | E | TBD | E | 2018-06-28 | 1 | 828 | Modification Report consultation | On Track | SECMP0011 has been issued for Modification Report Consutlation until 5th April 2017. The Change Board will vote on SECMP0011 on 19th April 2017. | -
SEC | SECMP0012 | Channel selection to support Shared HAN solutions | Yes | No | No | No | Yes | SEC - SECMP0012 | C | 2016-05-05 | E | TBD | E | 2018-11-01 | 1 | 910 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0013 | Smart meter device diagnostics and triage | Yes | No | No | No | Yes | SEC - SECMP0013 | C | 2016-05-04 | E | TBD | E | 2018-11-01 | 1 | 911 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0015 | GPF timestamp for reading instantaneous Gas values | Yes | No | No | No | Yes | SEC - SECMP0015 | C | 2016-05-31 | E | TBD | E | 2018-11-01 | 1 | 884 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0016 | Consideration of "Maximum Credit" value in credit cover calculation | Yes | No | No | No | Yes | SEC - SECMP0016 | C | 2016-06-03 | C | 2017-01-28 | C | 2018-04-01 | 239 | 667 | Implemneted | On Track | SECMP0016 was implemented on 1sdt April 2017. | -
SEC | SECMP0018 | Standard Electricity Distributor Configuration Settings | Yes | No | No | No | Yes | SEC - SECMP0018 | C | 2016-06-23 | E | TBD | E | 2018-11-01 | 1 | 861 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0019 | ALCS Description Labels | Yes | No | No | No | Yes | SEC - SECMP0019 | C | 2016-07-14 | E | TBD | E | 2018-11-01 | 1 | 840 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0021 | Increase Other SEC Party representation for TABASC and SSC | Yes | No | No | No | Yes | SEC - SECMP0021 | C | 2016-10-04 | E | TBD | E | 2017-05-11 | 1 | 219 | Modification Report Consutlation | On Track | SECMP0021 has been issued for Modification Report Consutlation until 5th April 2017. The Change Board will vote on SECMP0021 on 19th April 2017. | -
SEC | SECMP0023 | Correct Units of Measure for Uncontrolled Gas Flow Rate | Yes | No | No | No | Yes | SEC - SECMP0023 | C | 2016-10-26 | E | TBD | E | 2018-11-01 | 1 | 736 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0024 | Enduring Approach to Communication Hub Firmware Management | Yes | No | No | No | Yes | SEC - SECMP0024 | C | 2016-10-27 | E | TBD | E | 2018-11-01 | 1 | 735 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0025 | Electricity Network Party Access to Load Switching Information | Yes | No | No | No | Yes | SEC - SECMP0025 | C | 2016-11-18 | E | TBD | E | 2018-06-01 | 1 | 560 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0026 | Changes to the Security Sub-Committee Nomination Process | Yes | No | No | No | Yes | SEC - SECMP0026 | C | 2016-12-12 | E | TBD | C | 2017-03-16 | 1 | 94 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0027 | Amending Service Request Forecasting | Yes | No | No | No | Yes | SEC - SECMP0027 | C | 2016-12-16 | E | TBD | E | TBD | 1 |  | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0028 | Prioritising Service Requests | Yes | No | No | No | Yes | SEC - SECMP0028 | C | 2016-12-07 | E | TBD | E | TBD | 1 |  | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0029 | Business Continuity and Disaster Recovery Testing Amendments | Yes | No | No | No | Yes | SEC - SECMP0029 | C | 2016-12-19 | E | TBD | E | TBD | 1 |  | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0030 | Demand Management of DCC Systems | Yes | No | No | No | Yes | SEC - SECMP0030 | C | 2017-01-04 | E | TBD | E | TBD | 1 |  | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0031 | Adding UTRN Functionality to SMETS | Yes | No | No | No | Yes | SEC - SECMP0031 | C | 2017-02-20 | E | TBD | E | TBD | 1 |  | Initial Modification Report | On Track | This Modification was presented to the March 2017 Panel. The Panel referred the Modification Proposal to BEIS to seek a view on whether transitional powers set out in Section X2.3(d) should be applied. Subject to the response from BEIS, the Panel will take the appropriate action. | -
SEC | SECMP0032 | Prioritising Prepayment Customers in No WAN Situations | Yes | No | No | No | Yes | SEC - SECMP0032 | C | 2017-02-20 | E | TBD | E | TBD | 1 |  | Initial Modification Report | On Track | This Modification was presented to the March 2017 Panel. The Panel referred the Modification Proposal to BEIS to seek a view on whether transitional powers set out in Section X2.3(d) should be applied. Subject to the response from BEIS, the Panel will take the appropriate action. | -
SEC | SECMP0033 | Update to CH Handover Support Materials | Yes | No | No | No | Yes | SEC - SECMP0033 | C | 2017-02-22 | E | TBD | E | 2017-05-11 | 1 | 78 | Modification Report Consutlation | On Track | SECMP0033 has been issued for Modification Report Consutlation until 5th April 2017. The Change Board will vote on SECMP0033 on 19th April 2017. | -
SPAA | CP 14/268 | Introduction of The Gas Theft Incentive Scheme | No | No | No | No | No | SPAA - CP 14/268 | C | 2014-03-01 | C | n/a | E | TBD | 1 |  | Implemented | On Track | Confirmation of go-live date required Mod will be implemented 5 WDs after Authority Decision, with the Scheme Year to start on the first day of the calendar month two months after Authority Decision. | Gas Theft
SPAA | CP 15/305 | Additional MDD Rejection Codes for UKLP | No | No | No | No | No | SPAA - CP 15/305 | C | 2015-05-01 | C | 2016-07-21 | E | TBD | 447 |  | Awaiting implementation | On Track | Confirmation of go-live date required Project Nexus Implementation Date | Nexus
SPAA | CP 15/306 | Inclusion of new definition – Project Nexus Implementation Date | No | No | No | No | No | SPAA - CP 15/306 | C | 2016-06-01 | C | 2016-07-21 | E | TBD | 50 |  | Awaiting implementation | On Track | Confirmation of go-live date required Project Nexus Implementation Date | Nexus
SPAA | CP 15/307 | Amendment to the Implementation date of CP14/284 | No | No | No | No | No | SPAA - CP 15/307 | C | 2015-06-01 | C | 2016-07-21 | E | TBD | 416 |  | Awaiting implementation | On Track | Confirmation of go-live date required Project Nexus Implementation Date | Nexus
SPAA | CP 15/308 | Removal of Schedule 7 (Cooperative Objections) as a result of Nexus | No | No | No | No | No | SPAA - CP 15/308 | C | 2016-03-01 | C | 2016-04-01 | E | TBD | 31 |  | Awaiting implementation | On Track | Confirmation of go-live date required Project Nexus Implementation Date | Nexus
SPAA | CP 15/317 | Amendment to Schedule 23 to reflect Changes at Project Nexus Implementation | No | No | No | No | No | SPAA - CP 15/317 | C | 2015-11-01 | C | 2015-12-01 | E | TBD | 30 |  | Awaiting implementation | On Track | Confirmation of go-live date required Project Nexus Implementation Date | Nexus
SPAA | CP 16/327 | Revision and Implementation of the Gas Theft Detection Incentive Scheme | No | No | No | No | No | SPAA - CP 16/327 | C | 2016-06-01 | C | 2016-07-21 | C | 2017-06-05 | 50 | 369 | Awaiting implementation | On Track | - | Gas Theft
SPAA | CP 16/329 | Introduction of Schedule 38 and a new defined term in Schedule 29 | No | No | No | No | No | SPAA - CP 16/329 | C | 2016-05-01 | C | 2017-02-01 | C | 2017-02-24 | 276 | 299 | Implemented | On Track | - | n/a
SPAA | CP 16/334 | Introduction of Smart Prepayment Change of Supplier Exceptions Process | Yes | No | No | No | No | SPAA - CP 16/334 | C | 2016-05-01 | C | 2016-10-20 | E | TBD | 172 |  | Implemented | On Track | Confirmation of authority approval 1 WD after Authority Consent received | n/a
SPAA | CP 16/336 | Amendments to the SPAA change process v1.1 | No | No | No | No | No | SPAA - CP 16/336 | C | 2016-06-01 | C | 2016-10-20 | C | 2017-02-24 | 141 | 268 | Implemented | On Track | - | n/a
SPAA | CP 16/338 | Process and Costs of Providing Additional Hunter Facilities | No | No | No | No | No | SPAA - CP 16/338 | C | 2016-05-01 | C | 2016-09-15 | C | 2017-02-24 | 137 | 299 | Implemented | On Track | - | TRAS
SPAA | CP 16/339 | TRAS Amendment of Schedule 34 Appendix 2 | No | No | No | No | Yes | SPAA - CP 16/339 | C | 2016-05-01 | C | 2016-09-15 | E | TBD | 137 |  | Issued | On Track | Confirmation of authority approval 5WDs after decision to align with DCUSA | TRAS
SPAA | CP 16/343 | Housekeeping amendment to redundant Schedules | No | No | No | No | Yes | SPAA - CP 16/343 | C | 2016-06-01 | C | 2016-07-21 | C | TBD | 50 |  | Awaiting implementation | On Track | Confirmation of go-live date required Project Nexus Implementation Date | Nexus
SPAA | CP 16/344 | Requirement on Gas Transporters to Provide Data to the ETTOS Service Provider | No | No | No | No | No | SPAA - CP 16/344 | C | 2016-06-01 | C | 2016-07-21 | E | TBD | 50 |  | Awaiting implementation | On Track | Confirmation of authority approval 5 Working Days following Authority approval (aligned with the DCUSA change) | TRAS
SPAA | CP 16/346 | Inclusion of User Allocation Rules for ETTOS Secure Email System (Draft) | No | No | No | No | No | SPAA - CP 16/346 | C | 2016-07-01 | C | 2016-12-15 | E | 2017-02-24 | 167 | 238 | Implemented | On Track | - | TRAS
SPAA | CP 16/346 | Inclusion of User Allocation Rules for ETTOS Secure Email System | No | No | No | No | No | SPAA - CP 16/346 | C | 2016-11-01 | C | 2016-12-15 | C | 2017-02-24 | 44 | 115 | Implemented | On Track | - | TRAS
SPAA | CP 16/347 | Amendments to Pre-Payment tariff pages (Draft) | No | No | No | No | No | SPAA - CP 16/347 | C | 2016-07-01 | C | n/a | E | TBD | 1 |  | Awaiting implementation | On Track | Confirmation of authority approval 5WD after Authority Consent received | -
SPAA | CP 16/349 | Introduction of OAMI into SPAA EC Vires | No | No | No | No | No | SPAA - CP 16/349 | C | 2017-01-01 | C | TBD | E | TBD | 1 |  | Issued in Change Pack | On Track | Modication due to be implemented 5 Working Days after Authority Decision | -
SPAA | CP 16/350 | Clarification of TRAS Accession Process | No | No | No | No | No | SPAA - CP 16/350 | C | 2016-11-01 | C | 2016-12-15 | C | 2017-02-24 | 44 | 115 | Implemented | On Track |  | TRAS
SPAA | CP 16/352 | Changes to SLC 30 of SPAA | No | No | No | No | No | SPAA - CP 16/352 | C | 2016-08-01 | C | 2016-10-20 | C | 2017-02-24 | 80 | 207 | Implemented | On Track | - | -
SPAA | CP 16/354 | Mandate that all Suppliers shall use the DTN for the exchange of RET Flows | No | No | No | No | No | SPAA - CP 16/354 | C | 2016-09-01 | C | 2016-10-20 | C | 2017-06-05 | 49 | 277 | Awaiting implementation | On Track | - | -
SPAA | CP 16/355 | Mandate that all Suppliers shall use the DTN for the exchange of SAR Flows | No | No | No | No | No | SPAA - CP 16/355 | C | 2016-09-01 | C | 2016-10-20 | C | 2017-06-05 | 49 | 277 | Awaiting implementation | On Track | - | -
SPAA | CP 16/360 | Schedule 33, Appendix 1 SLC References | No | No | No | No | Yes | SPAA - CP 16/360 | C | 2016-11-01 | C | 2016-12-15 | C | 2017-02-24 | 44 | 115 | Deferred | On Track | - | -
SPAA | CP 16/363 | Adding Meter Serial Number (MSN) to the Supplier Agreed Read (SAR) flow. | No | No | No | No | No | SPAA - CP 16/363 | C | 2016-11-01 | C | 2016-12-15 | C | 2017-06-05 | 44 | 216 | Awaiting implementation | On Track | - | -
SPAA | CP 16/364 | Amendment to Actual Reading Definition | No | No | No | No | Yes | SPAA - CP 16/364 | C | 2016-11-01 | C | 2016-12-15 | C | 2017-02-24 | 44 | 115 | Implemented | On Track | - | -
SPAA | CP 17/371 | To reference ‘MAP 24’ within Schedule 38 | No | No | No | No | No | SPAA - CP 17/371 | C | 2017-01-01 | C | 2017-02-01 | C | 2017-06-30 | 31 | 180 | Issued in Change Pack | On Track | - | -
SPAA | CP 17/372 | Implementation of the Approved Meter Installer Governance | No | No | No | No | No | SPAA - CP 17/372 | C | 2017-01-01 | C | 2017-02-01 | C | 2017-04-01 | 31 | 90 | Issued in Change Pack | On Track | - | -
SPAA | CP 17/373 | Reordering Schedule 32 | No | No | No | No | No | SPAA - CP 17/373 | C | 2017-01-01 | C | 2017-02-01 | C | 2017-06-30 | 31 | 180 | Issued in Change Pack | On Track | - | -
SPAA | CP 17/374 | Introducing a funding mechanism into Schedule 32 | No | No | No | No | No | SPAA - CP 17/374 | C | 2017-01-01 | C | 2017-02-01 | C | 2017-09-01 | 31 | 243 | Issued in Change Pack | On Track | - | -
SPAA | CP 17/375 | Removal of reference to commercial disputes from Schedule 32 | No | No | No | No | No | SPAA - CP 17/375 | C | 2017-01-01 | C | 2017-02-01 | C | 2017-06-30 | 31 | 180 | Issued in Change Pack | On Track | - | -
SPAA | CP 17/376 | Xoserve funding and Governance Impacts | No | No | No | No | No | SPAA - CP 17/376 | C | 2017-01-01 | C | 2017-02-01 | C | 2017-04-01 | 31 | 90 | Withdrawn | On Track | - | -
SPAA | CP 17/377 | Amendments to Prepayment Tariff Pages | No | No | No | No | No | SPAA - CP 17/377 | C | 2017-01-01 | C | 2017-02-01 | C | 2017-04-01 | 31 | 90 | Issued in Change Pack | On Track | - | -
SPAA | CP 17/378 | Amendments to Prepayment Tariff Pages | No | No | No | No | No | SPAA - CP 17/378 | C | 2017-01-01 | C | 2017-02-01 | E | TBD | 31 |  | Issued in Change Pack | On Track | Modication due to be implemented 5 Working Days after Authority Decision | -
SPAA | CP 17/379 | Introduction of an Unidentified Funds Process in Schedule 25 | No | No | No | No | No | SPAA - CP 17/379 | C | 2017-02-16 | C | 2017-03-14 | E | 2017-06-30 | 26 | 134 | Issued in Change Pack | On Track | - | -
SPAA | CP 17/380 | Amendments to Schedule 32 in relation to the Provision of Services Regulations | No | No | No | No | No | SPAA - CP 17/380 | C | 2017-02-17 | C | 2017-03-14 | E | 2017-07-01 | 25 | 134 | Issued in Change Pack | On Track | - | -
SPAA | CP 17/381 | Introducing Failed Status in the Asset Status Code (A0037) for In Home Display. | No | No | No | No | No | SPAA - CP 17/381 | C | 2017-02-18 | C | 2017-03-14 | E | 2017-11-03 | 24 | 258 | Issued in Change Pack | On Track | - | -
SPAA | CP 17/382 | Amendments to Prepayment Tariff Pages – Updated following legal review | No | No | No | No | No | SPAA - CP 17/382 | C | 2017-03-03 | C | 2017-03-15 | E | TBD | 12 |  | Issued in Change Pack | On Track | Urgent The proposed implementation date is 5 working days after Authority approval | CMA
SQSS | GSR012 | Treatment of Interconnectors | No | No | Yes | No | Yes | SQSS - GSR012 | C | 2010-10-05 | E | TBD | E | TBD | 1 |  | Assessment | At Risk | Workgroup meetings need to re-convene following 1 year hiatus. | -
SQSS | GSR014 | Offshore Transformer Requirements | No | No | No | No | No | SQSS - GSR014 | C | 2012-11-19 | E | TBD | E | TBD | 1 |  | Assessment | At Risk | Finalising report | -
SQSS | GSR016 | Embedded Generation Scaling | No | No | No | No | Yes | SQSS - GSR016 | C | 2013-07-22 | E | TBD | E | TBD | 1 |  | Assessment | On Track | - | -
SQSS | GSR017 | Treatment of Switch Faults in Operational Timescales | No | No | No | No | No | SQSS - GSR017 | C | 2014-02-05 | E | TBD | E | TBD | 1 |  | Raised | On Track | - | -
SQSS | GSR018 | Treatment of Sub-Synchronous Oscillations in the NETS SQSS | No | No | No | No | Yes | SQSS - GSR018 | C | 2014-12-04 | E | TBD | E | TBD | 1 |  | Raised | On Track | - | GC0077
SQSS | GSR022 | Review of Security and Economy Planned Transfer Conditions | No | No | No | No | Yes | SQSS - GSR022 | C | 2016-06-01 | E | TBD | E | TBD | 1 |  | Raised | On Track | - | -
SQSS | SQSS Potential Change 1 | European TSOG -Minimum Required Inertia | No | No | No | No | No | SQSS - SQSS Potential Change 1 | E | 2017-10-01 | E | TBD | E | 2018-10-01 | 1 | 365 | Upcoming | On Track | - | -
SQSS | SQSS Potential Change 2 | European TSOG Implementation -Regional Outage Coordination | No | No | No | No | No | SQSS - SQSS Potential Change 2 | E | 2018-01-01 | E | TBD | E | 2018-10-01 | 1 | 273 | Upcoming | On Track | - | -
SQSS | SQSS Potential Change 3 | European TSOG - Requirements | No | No | No | No | No | SQSS - SQSS Potential Change 3 | E | 2018-01-01 | E | TBD | E | 2018-10-01 | 1 | 273 | Upcoming | On Track | - | -
STC | CM059 | Changes to Section C and H following OFGEM Response to Adjudication Request | No | No | No | No | No | STC - CM059 | C | 2016-09-21 | E | TBD | E | TBD | 1 |  | Assessment | On Track | - | -
STC | STC Potential Change 1 | European TSOG - Multi TSO Training Cooperation | No | No | Yes | No | Yes | STC - STC Potential Change 1 | E | 2017-10-01 | E | TBD | C | 2018-10-01 | 1 | 365 | Upcoming | On Track | - | EU Regulation/Law
STC | STC Potential Change 2 | European TSOG Implementation - Data Exchange | No | No | Yes | No | Yes | STC - STC Potential Change 2 | E | 2017-10-01 | E | TBD | C | 2018-10-01 | 1 | 365 | Upcoming | On Track | - | EU Regulation/Law
STC | STC Potential Change 3 | European TSOG Implementation -Regional Outage Coordination | No | No | Yes | No | Yes | STC - STC Potential Change 3 | E | 2018-01-01 | E | TBD | C | 2018-12-01 | 1 | 334 | Upcoming | On Track | This mod is set to be raised in Q1 2018 | EU Regulation/Law
STC | STC Potential Change 4 | SO/TO Funding Mechanism | No | No | No | n | Yes | STC - STC Potential Change 4 | E | n/a | N/A | TBD | E | N/A | 1 |  | Upcoming | On Track | Still under review to confirm if any changes needed | Update to STC to reflect changes identified by NAP workgroup
STC | STC Potential Change 5 | Changes to incorporate changes from ECIT | No | No | No | N | Yes | STC - STC Potential Change 5 | E | n/a | N/A | TBD | E | TBD | 1 |  | Upcoming | On Track | Waiting information from Ofgem on scope of change and change mechanism to be used | Regulatory change
STC | STC Potential Change 6 | Changes to Section K as a result of Grid Code Modification GC075 | No | No | No | N | Yes | STC - STC Potential Change 6 | E | n/a | N/A | TBD | E | TBD | 1 |  | Upcoming | On Track | Review being performed | Industry review
STC | PM0094 | Housekeeping to STCP18-2 | No | No | No | n | No | STC - PM0094 | C | 2017-03-29 | 2017-04-26 | 2017-04-26 | C | 2017-04-26 | 28 | 28 | Awaiting implementation | On Track | Waiting updated form to sign off | Improve process to reflect current working practices
STC | PM0095 | Housekeeping to STCP18-3 | No | No | No | n | No | STC - PM0095 | C | 2017-03-29 | 2017-04-26 | 2017-04-26 | C | 2017-04-26 | 28 | 28 | Awaiting implementation | On Track | Waiting updated form to sign off | Improve process to reflect current working practices
STC | STCP Potential Change 1 | Housekeeping to STCP18-1 | No | No | No | n | No | STC - STCP Potential Change 1 | E | n/a | N/A | TBD | E | N/A | 1 |  | Upcoming | On Track | Still under review to confirm if any changes needed | Improve process to reflect current working practices
STC | STCP Potential Change 2 | Housekeeping to STCP18-4 | No | No | No | n | No | STC - STCP Potential Change 2 | E | n/a | N/A | TBD | E | N/A | 1 |  | Upcoming | On Track | Still under review to confirm if any changes needed | Improve process to reflect current working practices
STC | STCP Potential Change 3 | Housekeeping to STCP08-2 | No | No | No | n | No | STC - STCP Potential Change 3 | E | n/a | N/A | TBD | E | N/A | 1 |  | Upcoming | On Track | Still under review to confirm if any changes needed | Improve process to reflect current working practices
STC | STCP Potential Change 4 | SO/TO Funding Mechanism | No | No | No | n | No | STC - STCP Potential Change 4 | E | n/a | N/A | TBD | E | N/A | 1 |  | Upcoming | On Track | Still under review to confirm if any changes needed | Update to STC to reflect changes identified by NAP workgroup
STC | STCP Potential Change 5 | Review of STCP09-1 | No | No | No | n | No | STC - STCP Potential Change 5 | E | n/a | N/A | TBD | E | TBD | 1 |  | Upcoming | On Track | Further Workgroup needed to refine any changes | Industry review
STC | STCP Potential Change 6 | Review of STCP19-3 | No | No | No | n | No | STC - STCP Potential Change 6 | E | n/a | N/A | TBD | E | TBD | 1 |  | Upcoming | On Track | Further Workgroup needed to refine any changes | Industry review
STC | STCP Potential Change 7 | Review of STCP22-1 | No | No | No | n | No | STC - STCP Potential Change 7 | E | n/a | N/A | TBD | E | TBD | 1 |  | Upcoming | On Track | Further Workgroup needed to refine any changes | Industry review
UNC | 0565A | Central Data Service Provider: General framework and obligations | No | No | No | No | Yes | UNC - 0565A | C | 2016-10-10 | E | 2017-01-31 | E | 2017-04-01 | 113 | 173 | Awaiting Implementation | On Track | Goes live on 01 April 2017 | Licence - FGO
UNC | 0570 | Obligation on Shippers to provide at least one valid meter reading per meter point into settlement once per annum | No | No | No | No | Yes | UNC - 0570 | C | 2015-12-03 | E | 2017-08-30 | E | 2017-09-01 | 636 | 638 | Assessment | On Track | Workgroup assessment timetable has been extended | CMA Order
UNC | 0571 | Application of Ratchets Charges to Class 1 Supply Points Only | No | No | No | No | Yes | UNC - 0571 | C | 2015-12-24 | E | 2017-05-30 | E | 2017-08-01 | 523 | 586 | Assessment | On Track | Returned to the Workgroup for consideration of an issue identified in the consultation | -
UNC | 0571A | Application of Ratchet Charges to Class 1 Supply Points and Class 2 with an AQ above 73,200kWhs | No | No | No | No | Yes | UNC - 0571A | C | 2016-05-05 | E | 2017-05-30 | E | 2017-08-01 | 390 | 453 | Assessment | On Track | Returned to the Workgroup for consideration of an issue identified in the consultation | -
UNC | 0587 | Seasonal Energy Balancing Credit Cover | No | No | No | No | Yes | UNC - 0587 | C | 2016-06-06 | C | 2016-11-24 | C | 2017-05-01 | 171 | 329 | Implemented | - | Minor changes required - and elective as required | -
UNC | 0593 | Provision of access to data for Price Comparison Websites and Third Party Intermediaries | No | No | No | No | Yes | UNC - 0593 | C | 2016-08-08 | E | 2017-08-30 | E | 2017-09-01 | 387 | 389 | Assessment | On Track | Returned to the Workgroup for consideration of issues raised in Ofgem's 'sendback' letter | CMA Order
UNC | 0594R | Meter Reading Submission for Advanced & Smart Metering | Yes | No | No | No | No | UNC - 0594R | C | 2016-09-02 |  | n/a |  | n/a |  |  | Request | On Track | This is a UNC Request - to review the arrangements for meter reading submission. A modification is one possible output. | None- Review
UNC | 0595S | Amendment to the Arrangements between National Grid NTS and GNI at the Moffat IP to Provide for Interruption of Virtual Reverse Flow | No | No | No | No | Yes | UNC - 0595S | C | 2016-09-02 | C | 2016-11-17 | C | 2016-12-09 | 76 | 98 | Implemented | - | No action to implement since the service was already available in Ireland | -
UNC | 0596 | Implementing CGR3 decisions on Significant Code Reviews and self-governance | No | No | No | No | Yes | UNC - 0596 | C | 2016-10-07 | E | 2017-01-31 | C | 2017-02-17 | 116 | 133 | Implemented | - |  | CGR3
UNC | 0597S | Rules for the release of incremental capacity at Interconnection Points | No | No | Yes | No | Yes | UNC - 0597S | C | 2016-10-10 | E | 2017-03-31 | C | 2017-04-06 | 172 | 178 | Awaiting Implementation | On Track | - | EU CAM
UNC | 0598 | Amendments to Capacity Allocations Mechanisms to comply with EU Capacity Regulations | No | No | Yes | No | Yes | UNC - 0598 | C | 2016-10-10 | E | 2017-03-31 | C | 2017-04-06 | 172 | 178 | Awaiting Implementation | On Track | - | EU CAM
UNC | 0599 | Amendments to Capacity Allocations Mechanisms (Interruptible) to comply with EU Capacity Regulations | No | No | Yes | No | Yes | UNC - 0599 | C | 2016-10-10 | C | n/a | C | n/a | 1 |  | Withdrawn | - | Withdrawn | EU CAM
UNC | 0600S | Amend obligation for the acceptance of EPDQD revisions made after D+5 | No | No | No | No | Yes | UNC - 0600S | C | 2016-10-10 | E | 2017-03-16 | C | 2017-04-07 | 157 | 179 | Awaiting Implementation | On Track | - | -
UNC | 0601FT | Revision of National Grid Gas plc’s Individual Network Code to reflect the correct company name | No | No | No | No | No | UNC - 0601FT | C | 2016-11-01 | C | 2016-11-17 | C | 2016-12-09 | 16 | 38 | Implemented | - | - | -
UNC | 0602A | Implementation of Non Effective Days and Variant Non-Business Days for Project Nexus Implementation, maintaining two Supply Point Business Days (Project Nexus transitional modification) | No | No | No | No | Yes | UNC - 0602A | C | 2016-12-23 | E | 2017-03-31 | C | 2017-02-20 | 98 | 59 | Implemented | - |  | Nexus
UNC | 0603S | Removal of liability for members of Performance Assurance Committee | No | No | No | No | Yes | UNC - 0603S | C | 2016-11-08 | C | 2016-12-15 | C | 2017-01-11 | 37 | 64 | Implemented | - | Minor change - no action required | -
UNC | 0604S | Central Data Services Provider – Arrangements following implementation of Project Nexus | No | No | No | No | Yes | UNC - 0604S | C | 2016-11-30 | C | 2017-04-20 | C | 2017-06-01 | 141 | 183 | Consultation | On Track | - | Licence - FGO
UNC | 0605S | Amendments to TPD Section K - Additional Methods to Procure and Dispose of Operating Margins Gas | No | No | No | No | Yes | UNC - 0605S | C | 2016-12-02 | E | 2017-07-31 | E | 2017-09-01 | 241 | 273 | Assessment | On Track | Expected to be returned to Workgroup at April Panel for further assessment | -
UNC | 0606S | National Grid Gas plc and National Grid Gas Distribution Limited transitional invoicing arrangement post Project Nexus implementation | No | No | No | No | Yes | UNC - 0606S | C | 2016-12-05 | C | 2017-04-20 | C | 2017-06-01 | 136 | 178 | Consultation | On Track | - | -
UNC | 0607S | Amendment to Gas Quality NTS Entry Specification at the St Fergus NSMP System Entry Point | No | No | No | No | No | UNC - 0607S | C | 2016-12-07 | E | 2017-08-30 | E | 2017-09-01 | 266 | 268 | Assessment | On Track | - | -
UNC | 0608S | Implementation of ‘single service provision’ arrangements for iGT connected system exit points (Project Nexus transitional modification) | No | No | No | No | No | UNC - 0608S | C | 2017-01-09 | C | 2017-04-20 | E | 2017-05-15 | 101 | 126 | Consultation | On Track | - | -
UNC | 0609 | Transitional arrangements for gas settlement and replacement of Meter Readings (Project Nexus transitional modification) | No | No | No | No | No | UNC - 0609 | C | 2017-01-09 | E | 2017-05-20 | E | 2017-06-01 | 131 | 143 | Consultation | On Track | - | -
UNC | 0610S | Project Nexus - Miscellaneous Requirements | No | No | No | No | No | UNC - 0610S | C | 2017-01-11 | C | 2017-04-20 | E | 2017-05-15 | 99 | 124 | Consultation | On Track | - | -
UNC | 0611 | Amendments to the firm capacity payable price at Interconnection Points | No | No | No | No | No | UNC - 0611 | C | 2017-02-03 | C | 2017-05-18 | E | TBD | 104 |  | Assessment | On Track | - | -
UNC | 0613S | Revised UK Link Manual CDSP Data Services Document | No | No | No | No | Yes | UNC - 0613S | C | 2017-03-07 | E | 2017-06-15 | E | TBD | 100 |  | Assessment | On Track | - | FGO
UNC | 0614 | Introducing IHD (In-Home Display) Installed Status of Failed | No | No | No | No | No | UNC - 0614 | C | 2017-03-08 | E | TBD | E | TBD | 1 |  | On Hold | - | Deferred at March Panel as this may not be a UNC matter. Awaiting proposer update | -

## Change Register
Change Register
The Change Regiser is a list of live, closed and upcoming changes provided by Code Administrators to determine potential cross-code coordination opportunities to assist in forward work planning.
Updates that have been provided since the previous publication, are shown in red.
Please be aware the National Grid also provided SQSS changes, as the relevant to European Harmonisation.
FURTHER GUIDANCE |  |  |  |  | Does the change involve Smart Metering? (Yes, No) | Does the change involve HH Settlement? (Yes, No) | Does the change involve EU Harmonisation? (Yes, No) | Does the change involve switching ? (Yes, No) | Does the change involve a specific code change? Yes, No) | What is the status of the raised date? (E for Estimated or C for Confirmed) |  | What is the status of the decision date? (E for Estimated or C for Confirmed) |  | What is the Status of the implementation date? (E for Estimated or C for Confirmed) |  | At what state of progression is the change? (Upcoming, Raised, Assessment, Awaiting Implementation, Implemented) |  | Any other information or updates |  |  | What type of change? (Mod , CP) |  |  |  | Does this change need to be displayed in the FWP? (Yes,No)
Code | Change Ref | Title | Summary | Proposer | A1 | A2 | A3 | A4 | A5 | Status (raised date) | Raised | Status (imp decision date) | Imp Decision | Status (imp date) | Imp Date | Progression State | RAG Status | Commentary | Drivers | Other Codes impacted | Category of Modification | Workgroup website | Code Administrator | Live/closed | Display
BSC | BSC Potential Change 1 | Time of Interconnector Data Submission |  | National Grid | No | No | Yes | No | No | E | 2017-06-01 | E | 2018-03-01 | E | 2018-06-01 | Upcoming | - | A Modification is expected to be raised in April 2017 under Grid Code, to address the CACM requirement. If the Grid Code Modification removes the impact on the BSC, this Modification will be redundant. | ENC |  | Mod |  | ELEXON | Upcoming | Yes
BSC | BSC Potential Change 2 | Imbalance Price (without derogation) |  | National Grid | No | No | Yes | No | No | E | 2017-10-01 | E | 2018-04-01 | E | 2018-10-01 | Upcoming | - | It is assumed that NGET will apply for a derogation for this requirement. If a derogation is approved, this Modification will be included within the scope of Potential Modification 11 "Harmonised Imbalance Settlement". | ENC |  | Mod |  | ELEXON | Upcoming | Yes
BSC | BSC Potential Change 3 | Inclusion of Imbalance Adjustments (without derogation) |  | National Grid | No | No | Yes | No | No | E | 2017-10-01 | E | 2018-04-01 | E | 2018-10-01 | Upcoming | - | It is assumed that NGET will apply for a derogation for this requirement. If a derogation be approved, this Modification will be raised on 01/10/19 | ENC |  | Mod |  | ELEXON | Upcoming | Yes
BSC | BSC Potential Change 4 | Align BSC with the Authority's oversight obligation |  | National Grid | No | No | Yes | No | No | E | 2017-10-01 | E | 2018-04-01 | E | 2018-10-01 | Upcoming | - | Assignment by BEIS/Ofgem and decisions by Ofgem on how it wishes to approach this requirement | ENC |  | Mod |  | ELEXON | Upcoming | Yes
BSC | BSC Potential Change 5 | Amendments to Imbalance Price |  | National Grid | No | No | Yes | No | No | E | 2018-10-01 | E | 2019-04-01 | E | 2020-04-01 | Upcoming | - | If TSO Proposal for activiation purpose do not align with the BSC, this Modification will be raised to amend the imbalance price calculation | ENC |  | Mod |  | ELEXON | Upcoming | Yes
BSC | BSC Potential Change 6 | Align BSC with the TSO's Terms and Conditions |  | National Grid | No | No | Yes | No | No | E | 2018-10-01 | E | 2019-04-01 | E | 2019-10-01 | Upcoming | - | If NGET write Ts & Cs in a way that differs from the Ts & Cs of the BSC, this Modification will be raised to align the BSC with the Ts & Cs of the TSO. | ENC |  | Mod |  | ELEXON | Upcoming | Yes
BSC | BSC Potential Change 7 | Project TERRE 2 |  | National Grid | No | No | Yes | No | No | E | 2018-10-01 | E | 2019-07-01 | E | 2020-03-01 | Upcoming | - | This Modification will be raised to implement outstanding activities from Project TERRE | ENC |  | Mod |  | ELEXON | Upcoming | Yes
BSC | BSC Potential Change 8 | Unintended exchanges of energy |  | National Grid | No | No | Yes | No | No | E | 2018-10-01 | E | 2019-04-01 | E | 2019-10-01 | Upcoming | - | Assignment Certainty on whether this Mod is reaquired, is based on the provision of infomration from NGET, on what will be proposed. | ENC |  | Mod |  | ELEXON | Upcoming | Yes
BSC | BSC Potential Change 9 | NGET proposal on specific products |  | National Grid | No | No | Yes | No | No | E | 2018-10-01 | E | 2019-04-01 | E | 2019-10-01 | Upcoming | - | If NGET make a proposal on specific products, an assessment will be required to ensure that the understanding of specific products aligns with the BSC. If understanding of specific products in the TSO proposal, differs from the BSC, this Modification will be raised to align the BSC with the proposal. | ENC |  | Mod |  | ELEXON | Upcoming | Yes
BSC | BSC Potential Change 10 | Market Suspension and Restoration Arrangement |  | National Grid | No | No | Yes | No | No | E | 2018-11-01 | E | 2019-08-01 | E | 2020-05-01 | Upcoming | - | If NGET makes proposals for rules concerning the suspension and restoration of market activities; and the rules for balancing energy and imbalance settlement during market suspension, that differ from the BSC, this Modification will be raised to align the BSC with the proposals. | ENC |  | Mod |  | ELEXON | Upcoming | Yes
BSC | BSC Potential Change 3 | Inclusion of Imbalance Adjustments (with derogation) |  | National Grid | No | No | Yes | No | No | E | 2019-04-01 | E | 2020-01-01 | E | 2020-10-01 | Upcoming | - | It is assumed that NGET will apply for a derogation for this requirement. If a derogation be approved, this Modification will be raised on 01/10/19 | ENC |  | Mod |  | ELEXON | Upcoming | Yes
BSC | BSC Potential Change 11 | Harmonised Imbalance Settlement (Includes Mod 2 with derogation) |  | National Grid | No | No | Yes | No | No | E | 2019-04-01 | E | 2020-01-01 | E | 2020-10-01 | Upcoming | - | This Modification will be raised to align the BSC with NGETs proposals to harmonise the main features of imbalance settlement If Potential Modification 2 'Imbalance Price' receives a derogation, it will be included within the scope of this Modification. | ENC |  | Mod |  | ELEXON | Upcoming | Yes
BSC | BSC Potential Change 12 | Project mFRR |  | National Grid | No | No | Yes | No | No | E | 2019-04-01 | E | 2021-01-01 | E | 2021-10-01 | Upcoming | - | This Modification will be raised, as an extension of the principles introduced under P344 ' Project TERRE' | ENC |  | Mod |  | ELEXON | Upcoming | Yes
BSC | BSC Potential Change 13 | Project TERRE 3 |  | National Grid | No | No | Yes | No | No | E | 2019-01-01 | E | 2019-11-01 | E | 2020-02-27 | Upcoming | - | This Modification will be raised to implementation outstanding activities from P344 'Project TERRE' | - |  | Mod |  | ELEXON | Upcoming | Yes
BSC | BSC Potential Change 14 | Ofgem SCR on HH Settlement |  |  | No | Yes | No | No | No | E | 2017-06-01 | E | 2018-03-01 | E | 2018-06-28 | Upcoming | - | - | - |  | Mod |  | ELEXON | Upcoming | Yes
BSC | CP1465 | Sending revised Meter Technical Details following a change of Meter Operator Agent | CP1465 proposes to add a new footnote only to those sections of BSCP514 that specifically relate to a change of Non Half Hourly Meter Operator Agent (NHHMOA), these being sections 6.2.1 and 6.2.4. The new footnote will be additional to footnote 30 (which will remain unchanged) and will ensure that the enhanced requirement for sending MTD applies only to the scenarios identified by the Electricity Data Quality Working Group (DQWG). | ELEXON | No | No | No | No | Yes | C | 2016-06-13 | C | 2016-09-06 | C | 2017-02-23 | Implemented | On track | - | - | No | CP | https://www.elexon.co.uk/change-proposal/cp1465-2/ | ELEXON | Live | Yes
BSC | CP1466 | Removing SMETS compliant Meters from the scope of BSCP601 ‘Metering Protocol Approval and Compliance Testing’ | CP1466 proposes to remove the requirement of protocol approval and compliance testing for Smart Metering Equipment Technical Specifications (SMETS) compliant Meters. This will be achieved by removing SMETS compliant Meters from the scope of BSCP601. | ELEXON | No | Yes | No | No | No | C | 2016-06-14 | C | 2016-12-08 | C | 2017-02-23 | Implemented | On track | - | Settlement Reform Advisory Group recommendations | No | CP | https://www.elexon.co.uk/change-proposal/cp1466/ | ELEXON | Closed | Yes
BSC | CP1469 | Changes to support the implementation of the SRAG’s recommendations | CP1469 seeks to introduce new processes for getting smart Meter data from the Supplier to the HHDC. The validation and estimation requirements are also defined under this CP for smart Meters. | ELEXON | No | Yes | No | No | No | C | 2016-07-19 | C | 2016-10-04 | C | 2017-06-29 | Awaiting Implementation | On track | - | Settlement Reform Advisory Group recommendations | No | CP | https://www.elexon.co.uk/change-proposal/cp1469/ | ELEXON | Closed | Yes
BSC | CP1470 | Housekeeping Change to CoPs 1, 2, 3 and 5 following P266 | CP1470 proposes to make a Housekeeping Change to correct the manifest error in CoPs 1, 2, 3 and 5. This will amend the sections which incorrectly reference section 4.3.1 ‘Overall Accuracy’ section as 4.2.1 | ELEXON | No | No | No | No | No | C | 2016-08-12 | C | 2016-10-04 | C | 2017-02-23 | Implemented | On track | - | - | No | CP | https://www.elexon.co.uk/change-proposal/cp1470/ | ELEXON | Closed | No
BSC | CP1471 | Housekeeping - discrepancies in the requirements of the CRA URS | CP1471 seeks to make a Housekeeping Change to amend discrepancies between the Central Registration Agent (CRA) User Requirements Specification (URS) and the content of the New Electricity Trading Arrangements (NETA) Interface Definition and Design (IDD). | ELEXON | No | No | No | No | Yes | C | 2016-10-04 | C | 2016-10-04 | C | 2017-02-23 | Implemented | On track | - | - | No | CP | https://www.elexon.co.uk/change-proposal/cp1471/ | ELEXON | Closed | No
BSC | CP1472 | Removal of SVA proving tests for Meters with a pulse multiplier of one | CP1472 proposes to amend BSCPs 502, 514 and 601 to remove the requirement for proving test for Meters that only have a pulse multiplier of one. It also proposes a new process for the validation of complex sites. | NPower | No | No | No | No | Yes | C | 2016-09-14 | C | 2017-01-24 | C | 2017-02-23 | Implemented | On track | - | BSC Audit Issue Review Group | No | CP | https://www.elexon.co.uk/change-proposal/cp1472/ | ELEXON | Closed | Yes
BSC | CP1473 | Alteration to the LTV Entry Criteria | CP1473 seeks to alter the qualification criteria to be more reflective of the ‘Remain’ criteria. A Site will be able to be enter into the LTV process even if D0004s with SVCC’s of 18, 19, 20 and 28 are received in between the two qualifying D0004s with a SVCC 02. Proactive attempts to indentify the owner to obtain meter reads via mail or phone will still be required. | British Gas | No | No | No | No | Yes | C | 2016-10-05 | E | 2017-01-03 | C | 2017-02-23 | Implemented | On Track | - | - | No | CP | https://www.elexon.co.uk/change-proposal/cp1473-2/ | ELEXON | Closed | Yes
BSC | CP1474 | Updating the CoMC processes to facilitate the elective HH Settlement of SMETS Meters | CP1474 proposes to create new Change of Measurement Class processes for smart Meters. | ELEXON | No | Yes | No | No | No | C | 2016-10-14 | C | 2017-01-04 | C | 2017-06-29 | Awaiting Implementation | On Track | - | Ofgem’s Elective half-hourly settlement: conclusions paper | No | CP | https://www.elexon.co.uk/change-proposal/cp1474/ | ELEXON | Live | Yes
BSC | CP1475 | Remove obligation to re-date final NHH Meter readings on CoMC | CP1475 proposes to stop the re-dating of final Non Half Hourly (NHH) reading(s) on a Change of Measurement Class (CoMC) from NHH to Half Hourly (HH). This will be achieved by removing the process step where the NHH Meter Operator Agent (MOA) re-dates the meter register reading(s) in BSCP514. | E.ON | No | Yes | No | No | No | C | 2016-10-14 | C | 2017-01-03 | C | 2017-06-29 | Awaiting Implementation | On Track | - | - | No | CP | https://www.elexon.co.uk/change-proposal/cp1475/ | ELEXON | Live | Yes
BSC | CP1476 | Facilitation of Incremental LLFs | CP1476 proposes to amend BSCP128 Appendix 7 to allow LDSOs to submit incremental changes their Line Loss Factor data set. | ELEXON | No | No | No | No | Yes | C | 2016-10-27 | E | 2017-01-31 | E | 2017-06-29 | Awaiting Implementation | On Track | - | - | No | CP | https://www.elexon.co.uk/change-proposal/cp1476/ | ELEXON | Live | Yes
BSC | CP1477 | Updates to BSCP537 Appendix 1 as a result of P283 | CP1477 proposes to update BSCP537 Appendix 1 to account for the new Commissioning obligations introduced by P283. Specifically, this CP will update the guidance to answering questions around the Commissioning process. | ELEXON | No | No | No | No | Yes | C | 2016-11-07 | E | 2017-04-04 | E | 2017-06-29 | Assessment | On Track | - | - | No | CP | https://www.elexon.co.uk/change-proposal/cp1477/ | ELEXON | Live | Yes
BSC | CP1478 | Automate the loading of the DF Matrix | CP1478 seeks to automate the loading of Trading Disputes information into the DF matrix in the Supplier Volume Allocation Agent system. It is proposed that this will reduce the risk of error associated with the current manual data entry process. | ELEXON | No | No | No | No | No | C | 2016-11-22 | E | 2017-02-28 | E | 2017-11-02 | Awaiting Implemenation | On Track | - | - | No | CP | https://www.elexon.co.uk/change-proposal/cp1478/ | ELEXON | Live | Yes
BSC | CP1479 | Updates to the Defined Metering Points in Codes of Practice 1, 2, 3, 5 and 10 | CP1479 proposes to amend CoPs 1, 2, 3, 5 and 10 in order to resolve the three issues highlighted and implement the recommendations in the Issue 54 Report. | ELEXON | No | No | No | No | Yes | C | 2016-11-23 | E | 2017-02-20 | E | 2017-11-02 | Assessment | On Track | - | - | No | CP | https://www.elexon.co.uk/change-proposal/cp1479/ | ELEXON | Live | Yes
BSC | CP1480 | Creation of a new authorisation category for corrections to BOA related data | CP1480 proposes the creation of a new authorisation category specifically for this activity. Details of individuals in this new category would be made available to the TC for the purpose of seeking consent for corrections to BOA related data to be made. | National Grid | No | No | No | No | No | C | 2016-11-28 | E | 2017-02-28 | E | 2017-06-29 | Assessment | On Track | - | - | No | CP | https://www.elexon.co.uk/change-proposal/cp1480/ | ELEXON | Live | Yes
BSC | CP1481 | Housekeeping Change to BSCP536 following approval of P339 | CP1481 proposes to make a housekeeping change following approval of P339. | ELEXON | No | No | No | No | Yes | C | 2016-12-14 | E | 2017-01-26 | E | 2017-04-01 | Implemented | On Track | - | - | No | CP | https://www.elexon.co.uk/change-proposal/cp1481/ | ELEXON | Live | Yes
BSC | CP1482 | Upgrade of NHHDA and EAC/AA systems from Oracle 11g to version 12c | The current versions of NHHDA and EAC/AA applications that ELEXON provides to Party Agents run on Oracle 11g, for which Oracle Corporation will withdraw application support in 2018. The Oracle 11g platform was installed as part of CP1383 in June 2013. It will be necessary to complete an Upgrade to Oracle 12c as soon as possible in order to ensure continuity of service. | ELEXON | No | No | No | No | Yes | C | 2017-01-05 | E | 2017-05-02 | E | 2017-11-02 | Assessment | On Track | - | - | No | CP | https://www.elexon.co.uk/change-proposal/cp1482/ | ELEXON | Live | Yes
BSC | CP1483 | Changes to BSCP550 – Shared Metering Arrangements | This CP will make it a requirement for Suppliers to inform their agents, at the time of agent appointments, of the allocation schedule and any technical information necessary for the agent to deploy that solution. | ELEXON | No | No | No | No | Yes | C | 2017-01-18 | E | 2017-05-30 | E | 2017-11-02 | Assessment | On Track | In the SVG meeting on 4 April, the SVG chose to make an amendment to the redlined legal text. Due to the matierial nature of the change, CP1483 was issued for a second consultation on 10 April, with a response deadline of 4 May. This CP will be presented to SVG for decision on 22 May. | - | No | CP | https://www.elexon.co.uk/change-proposal/cp1483/ | ELEXON | Live | Yes
BSC | CP1484 | Introduce additional validation for DA data flows submitted to the SVAA | This CP proposes to introduce validation measures to reduce errors. Firstly, individual Data Aggregator (DA) data will be validated and checked for the plausibility of the consumption values. Secondly, it will ensure there is a complete set of DA data ready for the SVA run. Lastly, it will include checks on the results of runs. | ELEXON | No | No | No | No | Yes | C | 2017-02-08 | E | 2017-05-02 | E | 2017-11-02 | Assessment | On Track | - | - | No | CP | https://www.elexon.co.uk/change-proposal/cp1484/ | ELEXON | Live | Yes
BSC | CP1485 | Validation of power transformer and cable/line loss adjustments | This CP proposes changes to the BSCP32, Code of Practices (CoPs) 1, 2, 3, and 5 to address the validation of power transformer and cable or line electrical loss adjustments as part of the Metering Dispensation application process. | ELEXON | No | No | No | No | Yes | C | 2017-03-13 | E | 2017-05-22 | E | 2017-11-02 | Assessment | On Track | - | - | No | CP | https://www.elexon.co.uk/change-proposal/cp1485/ | ELEXON | Live | Yes
BSC | CP1486 | VAT Domestic Reverse Charge for Wholesale Supplies of Gas and Electricity | CP1486 proposes to remove the following sections from BSCP301: Section 5.1.1 ‘BSCP301/01a Combined Advice Note’, Section 5.1.3 ‘BSCP301/03a Combined Confirmation Notice’, Section 5.1.5 ‘BSCP301/05a Advice note Backing Sheet’ and Section 5.1.6 ‘BSCP301/05b Default Advice Note Backing Sheet’. | ELEXON | No | No | No | No | Yes | C | 2017-03-22 | E | 2017-05-22 | E | 2017-06-29 | Assessment | On Track | - | - | No | CP | https://www.elexon.co.uk/change-proposal/cp1486/ | ELEXON | Live | Yes
BSC | P272 | Mandatory Hlaf Hourly Settlement for Profle Classes 5-8 | P272 proposes to make HH Settlement mandatory for all Metering Systems within PCs 5-8 (where capable metering has been installed), as the Proposer believes that the use of Non Half Hourly (NHH) data is not as accurate and masks individual customer behaviour. | Smartest Energy | Yes | Yes | No | No | No | C | 2011-05-20 | C | 2014-10-29 | C | 2017-04-01 | Implemented | On Track | - | - | No | Mod | https://www.elexon.co.uk/mod-proposal/p272-mandatory-half-hourly-settlement-for-profile-classes-5-8/ | ELEXON | Live | Yes
BSC | P297 | Receipt and Publication of New and Revised Dynamic Data items | P297 proposes to amend the BSC to reflect the changes in the Dynamic Data Set under the Grid Code. Sections Q and V of the BSC will need to be updated whilst the BMRS will need to be modified to receive and publish the new and revised Dynamic Data from the Transmission Company. | National Grid | No | No | No | No | Yes | C | 2013-07-24 | C | 2014-04-28 | C | TBD | Awaiting Implementation | On Track | Due to further EBS delays, the Panel requested a revised Implementation Date for P297. The revised implementation date is TBD | - | No | Mod | https://www.elexon.co.uk/mod-proposal/p297/ | ELEXON | Live | Yes
BSC | CP1484 | Introduction of Additional SVAA Validation at SVA Run time | This CP proposes to introduce validation measures to reduce errors. Firstly, individual DA data will be validated and checked for the plausibility of the consumption values. Secondly, it will ensure there is a complete set of DA data ready for the VAR. Lastly, it will include checks on the results of VARs. | ELEXON | No | No | No | No | Yes | C | 2017-02-08 | E | TBD | E | 2017-11-03 | Assessment | On Track | - | - | No | CP | https://www.elexon.co.uk/change-proposal/cp1483/ | ELEXON | Live | Yes
BSC | P308 | Alternative security product for securing credit under the BSC | P308 proposes to introduce a centrally provided alternative security product as an alternative method for securing credit under the BSC, which Parties could use in place of the existing requirements to provide Credit Cover individually. | Eggborough Power | No | No | No | No | Yes | C | 2014-06-04 | E | 2017-02-01 | E | TBD | Withdrawn | At risk | The Proposer’s Representative withdrew Modification P308 on 2 February 2017. | - | No | Mod | https://www.elexon.co.uk/mod-proposal/p308/ | ELEXON | Live | Yes
BSC | P320 | Reporting on Profile Classes 5 – 8 Metering Systems after the implementation of P272 | P320 proposes to remove the relevant paragraphs that require PARMS changes introduced by P272 | British Gas | No | Yes | No | No | No | C | 2015-03-13 | C | 2015-09-09 | C | 2017-04-01 | Implemented | On Track | - | - | No | Mod | https://www.elexon.co.uk/mod-proposal/p320/ | ELEXON | Live | Yes
BSC | P321 | Publication of Trading Unit Delivery Mode | P321 proposes to publish information on the direction of delivery (delivering or offtaking) of Trading Units, particularly for each Grid Supply Point (GSP) Group, in each Settlement Period. | Smartest Energy | No | No | No | No | Yes | C | 2015-04-01 | C | 2015-10-08 | C | 2017-06-29 | Awaiting Implementation | On Track | P321 was originally approved under Self-Governance on 8 October 2015 for implementation on 30 June 2016. On 5 January 2016, the Panel wrote to the Authority to request the approved Implementation Date be deferred to 3 November 2016. The Authority approved this request on 26 January 2016. On 9 June 2016, the Panel wrote to the Authority to request the approved Implementation Date be deferred to 29 June 2017. The Authority approved this request on 8 August 2016. P321 will therefore be implemented on 29 June 2017 as part of the June 2017 BSC Systems Release. | - | No | Mod | https://www.elexon.co.uk/mod-proposal/p321/ | ELEXON | Live | Yes
BSC | P325 | Improving the accountability of BSCCo to stakeholders and better aligning BSCCo governance with best practice | The P325 proposes to amend proposes to amend the current provisions in BSC Section C to permit ELEXON to undertake roles and activities outside the BSC, subject to the approval of BSC Parties. | SSE Energy Supply Ltd | No | No | No | No | Yes | C | 2015-07-30 | E | TBD | E | TBD | Assessment | On Track | - | - | No | Mod | https://www.elexon.co.uk/mod-proposal/p325/ | ELEXON | Live | Yes
BSC | P326 | Introduction of a non-Working Day adjustment to the Credit Cover Percentage calculation | P326 proposes to introduce a method to account for reductions in Supplier demand on non-Working Days within the Credit Cover calculations. | Haven Power | No | No | No | No | Yes | C | 2015-08-25 | C | 2016-04-14 | C | 2017-02-23 | Implemented | On Track | - | - | No | Mod | https://www.elexon.co.uk/mod-proposal/p326/ | ELEXON | Live | Yes
BSC | P329 | Changes to REMIT inside information reporting | P329 proposes to align the BSC and Balancing Mechanism Reporting Service (BMRS) with the Regulation on Wholesale Energy Markets Integrity and Transparency (REMIT) common schemas for inside information web feeds, required by the Agency for the Cooperation of Energy Regulators (ACER). | National Grid | No | No | Yes | No | No | C | 2015-11-25 | C | 2016-04-19 | C | 2017-06-29 | Awaiting Implementation | On Track | - | - | No | Mod | https://www.elexon.co.uk/mod-proposal/p329/ | ELEXON | Live | Yes
BSC | P332 | Revisions to the Supplier Hub Principle | P332 seeks to address issues associated with customers choosing Party Agents, instead of Party Agents being appointed by Suppliers. The Modificaiton propsoes to make Party Agents signatories to the BSC and make all of their activities directly accountable to the Performance Assurance Board (PAB) and ELEXON. | Smartest Energy | No | No | No | No | Yes | C | 2016-01-28 | E | TBD | E | TBD | Assessment | On Track | - | - | No | Mod | https://www.elexon.co.uk/mod-proposal/p332/ | ELEXON | Live | Yes
BSC | P335 | Inclusion of Non-BM STOR costs and volumes in the indicative cashout price | P335 seeks to facilitate the submission of non-BM STOR costs and volumes such that they can be included in the indicative cashout price | ENGIE | No | No | No | No | Yes | C | 2016-02-19 | C | 2016-09-19 | C | 2017-11-02 | Awaiting Implementation | On Track | - | - | No | Mod | https://www.elexon.co.uk/mod-proposal/p335/ | ELEXON | Live | Yes
BSC | P336 | Fuel types on the BMRS | P336 proposes to add ‘biomass’ as a specific fuel type category reported on the Balancing Mechanism Reporting Service (BMRS). It also seeks to allow the Panel to approve further fuel types without needing to raise a Modification. | Drax Power Limited | No | No | No | No | Yes | C | 2016-02-29 | C | 2016-04-14 | C | 2017-11-02 | Awaiting Implementation | On Track | - | - | No | Mod | https://www.elexon.co.uk/mod-proposal/p336/ | ELEXON | Live | Yes
BSC | P338 | Consequential changes to P272 legal text | P338 proposes to make consequential changes to the approved legal text for P272 ‘Mandatory Half Hourly Settlement for Profile Classes 5-8’, to resolve conflicts that exist between it and certain approved Modifications. | BSC Panel | No | Yes | No | No | No | C | 2016-04-14 | C | 2016-04-14 | C | 2017-04-01 | Implemented | On Track | - | - | No | Mod | https://www.elexon.co.uk/mod-proposal/consequential-changes-to-p272-legal-text/ | ELEXON | Live | Yes
BSC | P339 | Introduction of new Consumption Component Classes for Measurement Classes E-G | P339 seeks to introduce new Consumption Component Classes (CCCs) for Measurement Classes “E”, “F” and “G” to enable aggregated consumption volumes for both Active Import (AI) and Active Export (AE) to be identified separately. | Ovo | No | Yes | No | No | No | C | 2016-05-04 | C | 2016-12-08 | C | 2017-04-01 | Implemented | On Track | - | - | No | Mod | https://www.elexon.co.uk/mod-proposal/p339/ | ELEXON | Live | Yes
BSC | P341 | MEL and other data earlier than Gate Closure | P341 seeks to mandate the Transmission Company to send MEL and MIL data to the BMRA for a period up to two days ahead to the BMRA for publication. | EDF | No | No | No | No | Yes | C | 2016-05-20 | E | 2017-04-01 | E | TBD | Assessment | At risk | Awaiting confirmation from Ofgem and a decision on progression from the Workgroup. | - | No | Mod | https://www.elexon.co.uk/mod-proposal/p341/ | ELEXON | Live | Yes
BSC | P342 | Change to Gate Closure for Energy Contract Volume Notifications | P342 proposes to introduce a new deadline for the purpose of submitting Energy Contract Volume Notifications (ECVNs) and Metered Volume Reallocation Notifications (MVRNs) for each Settlement Period. | EDF | No | No | Yes | No | Yes | C | 2016-05-25 | E | 2016-12-08 | C | 2017-11-02 | Awaiting Implementation | On Track | - | - | No | Mod | https://www.elexon.co.uk/mod-proposal/p342/ | ELEXON | Live | Yes
BSC | P343 | Increase to the number of Supplier IDs that can be held by a Supplier | P343 proposes to allow a Supplier to apply for a fourth or more Supplier IDs through an application form submitted to the Panel. | RWE npower | No | No | No | No | Yes | C | 2016-05-26 | C | 2016-11-10 | C | 2017-02-23 | Implemented | On Track | - | - | No | Mod | https://www.elexon.co.uk/mod-proposal/p343/ | ELEXON | Live | Yes
BSC | P344 | Project TERRE implementation into GB market arrangements | P344 seeks to align the Balancing and Settlement Code (BSC) with the European Balancing Project TERRE (Trans European Replacement Reserves Exchange) requirements. This is in order to allow the implementation of the project at national level and be compliant with the first tranche of obligations in the European Network Codes (ENCs). | National Grid | No | No | Yes | No | No | C | 2016-06-01 | C | 2017-09-21 | E | 2018-09-01 | Assessment | On track | Project TERRE is currently set to go-live in Q3 2018. | - | No | Mod | https://www.elexon.co.uk/mod-proposal/p344/ | ELEXON | Live | Yes
BSC | P346 | Changes to Specific Charges for Elective HH Settlement | P346 proposes to reduce BSC costs to Suppliers for entering domestic and small non-domestic customers into elective Half Hourly (HH) Settlement and could encourage Suppliers to promote such Settlement on a larger scale | British Gas | No | Yes | No | No | No | C | 2016-06-23 | C | 2016-11-10 | C | 2017-04-01 | Implemented | On Track | Approved. Awaiting implementation in April Standalone release | - | No | Mod | https://www.elexon.co.uk/mod-proposal/p346/ | ELEXON | Live | Yes
BSC | P347 | Reduction in R1 Read Threshold | 347 seeks to reduce the R1 Read requirement to 90% for Measurement Classes “F” and “G”. | Npower | Yes | Yes | No | No | No | C | 2016-07-01 | E | 2017-02-10 | C | 2017-04-01 | Implemented | On Track | On 19 January the Panel considered the Sendback Direction from the Authority and approved the revised Final Modification Report for P347. The Panel maintained its recomendation to the Authority that P347 should be rejected. The revised Final Modification Report was submitted to the Authority for decision on 19 January 2017. On 30 January 2017 the Authority determined that P347 should be Approved and implemented on 1 April 2017. | - | No | Mod | https://www.elexon.co.uk/mod-proposal/p347/ | ELEXON | Live | Yes
BSC | P348 | Provision of gross BM Unit data for TNUoS charging | P348 seeks to enable the Supplier Volume Allocation Agent (SVAA) to provide gross export and gross import data to the Transmission Company (TC) to support proposed revisions to the Transmission Network Use of System (TNUoS) Charging methods under Connection Use of System Code (CUSC) Modification Proposal (CMP) 265 ‘Gross charging of TNUoS for HH demand where embedded generation is in Capacity Market’. | EDF | No | No | No | No | Yes | C | 2016-07-01 | E | 2017-04-13 | E | 2019-11-07 | Assessment | On Track | This Modification will be progressed in line with P349. | Transmission Network Use of System (TNUoS) Charging changes | No | Mod | https://www.elexon.co.uk/mod-proposal/p348/ | ELEXON | Live | Yes
BSC | P349 | Facilitating Embedded Generation Triad Avoidance Standstill | P349 introduce a requirement under the BSC for Suppliers that are the registrants of New Embedded Generators to tell their Half Hourly Data Aggregators (HHDAs) which Metering System IDs (MSIDs) relate to New Embedded Generation. They will also be requited to tell their HHDAs to provide Period Metered Data from these MSIDs to the Transmission Company (TC) in the most efficient and cost-effective manner. | ScottishPower | No | No | No | No | Yes | C | 2016-07-04 | E | 2017-04-13 | E | 2017-06-29 | Assessment | On Track | New Embedded Generators will be defined for the purpose of this Modification by Connection Use of System Code (CUSC) Modification Proposal (CMP) 264 ‘Embedded Generation Triad Avoidance Standstill’. The implementation of CMP264 requires both SVA and CVA meter data flows for new embedded generation. It is believed that the Transmission Company already receives the necessary CVA metered data to allow for the benefits of CMP264 to be realised. If this assumption is proved invalid, this Modification will require including CVA as well as SVA registered generators. | - | No | Mod | https://www.elexon.co.uk/mod-proposal/p349/ | ELEXON | Live | Yes
BSC | P350 | Introduction of a seasonal Zonal Transmission Losses scheme | P350 proposes to introduce a Transmission Loss Factor for each TLF Zone (which will align with the existing Grid Supply Point (GSP) Groups) for each BSC Season in order to allocate transmission losses on a geographical basis. | National Grid | No | No | No | No | Yes | C | 2016-07-05 | E | 2017-03-31 | E | 2018-04-01 | Assessment | On Track | The CMA has placed obligations on National Grid to raise a Modification, for implementation by 1 April 2018. If the Modification is not implemented in time, then National Grid will be required to implement the same technical solution on the same date but outside of the BSC. The BSC Panel will make its final reccomendation to Ofgem on 9 Febraury 2017. Ofgem is expected to make its final decision by the end of March 2017. | CMA | No | Mod | https://www.elexon.co.uk/mod-proposal/p350/ | ELEXON | Live | Yes
BSC | P351 | Align the BSC with changes to the SCR requirements | P351 seeks to introduce three routes for taking forward the conclusions of an SCR. It is hoped that this will accelerate the change process and enable more efficient delivery of priority Modifications. | National Grid | No | No | No | No | Yes | C | 2016-07-29 | C | 2017-01-19 | E | 2017-04-01 | Implemented | On Track | Initially rejected by Panel. Report consultation now closed and Final report decision on 19/1/17 | - | No | Mod | https://www.elexon.co.uk/mod-proposal/p351/ | ELEXON | Live | Yes
BSC | P353 | Fast Track Self-Governance Mod following P324 | P353 proposes to make consequential changes to the approved legal text for P324 ‘Review of BSCCo’s governance: introducing improved accountability to BSC Parties’ to remove text no longer required in Section B 3.1.2 (h). | Panel | No | No | No | No | Yes | C | 2016-11-10 | C | 2016-12-08 | C | 2017-01-06 | Implemented | On track | - | - | No | Mod | https://www.elexon.co.uk/mod-proposal/p353/ | ELEXON | Live | Yes
BSC | P354 | Use of ABSVD for non-BM Balancing Services at the metered (MPAN) level | P354 proposes to allow the System Operator to provide Applicable Balancing Services Volume Data (ABSVD) volume at the MPAN level and the Settlement Administration Agent (SAA) to allocate this to the appropriate Supplier BM Unit. | ENGIE | No | No | No | No | Yes | C | 11-Jan-17 | E | TBD | E | TBD | Assessment | - | - | - | MRA | Mod | https://www.elexon.co.uk/mod-proposal/p354/ | ELEXON | Live | Yes
CUSC | CMP250 | Stabilising BSUoS with at least a twelve month notice period | The defect this modification seeks to address is that industry parties have no real certainty of their BSUoS costs when forward contracting their power. This is directly caused by the current BSUoS charging methodology that produces a highly volatile and unpredictable cost. This modification allows parties to know ahead of time what their BSUoS charge will be, and to reallocate this risk from those parties that are poorly placed to manage the risk, in particular smaller market participants, to a party that is better suited to deal with it . | Drax Power | No | No | No | No | Yes | C | 2015-08-19 | E | 2017-07-10 | E | 2017-07-17 | Assessment | At Risk | - | CMP250 | No | Mod | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/CUSC/Modifications/CMP250/ | National Grid | Live | Yes
CUSC | CMP251 | Removing the error margin in the cap on total TNUoS recovered by generation and introducing a new charging element to TNUoS to ensure compliance with European Commission Regulation 838/2010 | CMP251 aims to ensure that there is no risk of non-compliance with European Regulation 838/2010 by removing the error margin introduced by CMP224 and by introducing a new charging element to the calculation of TNUoS. CMP251 has been raised as Urgent by the Proposer. | British Gas | No | No | No | No | Yes | C | 2015-08-28 | C | 2016-10-14 | E | TBD | Authority Decision | - | - | - | None | Mod | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/CUSC/Modifications/CMP251/ | National Grid | Live | Yes
CUSC | CMP259 | Clarification of decrease in TEC as a Modification | CMP259 aims to amend the CUSC to enable a User to request both a TEC reduction and a subsequent TEC increase in the form of a single modification application to National Grid | RWE | No | No | No | No | Yes | C | 2016-05-22 | C | 2016-10-14 | E | TBD | Authority Decision | - | - | - | None | Mod | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/CUSC/Modifications/CMP259/ | National Grid | Closed | Yes
CUSC | CMP261 | Ensuring the TNUoS paid by Generators in GB in Charging Year 2015/16 is in compliance with the €2.5/MWh annual average limit set in EU Regulation 838/2010 Part B (3) | Having due regard for Regulation (EC) No 714/2009, the Commission Regulation (EU) No 838/2010 entitled “Guidelines for a Common Regulatory Approach to Transmission Charging” was introduced to provide a common regulatory approach to transmission charging across all the Member States. This Regulation, in Part B (paragraph 3), restricts the annual average transmission charges paid by electricity generators in Great Britain to the range of €0/MWh to €2.50/MWh. | SSE | No | No | No | No | Yes | C | 2016-03-11 | C | 2016-11-30 | E | TBD | Authority Decision | - | - | - | None | Urgent | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/CUSC/Modifications/CMP261/ | National Grid | Live | Yes
CUSC | CMP264 | Embedded Generation Triad Avoidance Standstill | CMP264 seeks to make changes to the Transport and Tariff Model and billing arrangements to remove the netting of output from New Embedded Generators until Ofgem has completed its consideration of the current electricity transmission Charging Arrangements (and any review which ensues) and any resulting changes have been fully implemented. | Scottish Power | No | No | No | No | Yes | C | 2016-05-27 | C | 2016-11-28 | E | TBD | Authority Decision | - | - | - | BSC & CMP265 | Mod | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/CUSC/Modifications/CMP264/ | National Grid | Live | Yes
CUSC | CMP265 | Gross charging of TNUoS for HH demand where embedded generation is in Capacity Market | CMP265 specifically seeks to address the issue that half hourly metered (HH) demand for TNUoS purposes is currently charged net of embedded generation. CMP265 has been proposed as urgent, we are awaiting a decision from Ofgem on this. | EDF Energy | No | No | No | No | Yes | C | 2016-05-27 | C | 2016-11-28 | E | TBD | Authority Decision | - | - | - | BSC & CMP264 | Urgent | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/CUSC/Modifications/CMP265/ | National Grid | Live | Yes
CUSC | CMP266 | Removal of Demand TNUoS charging as a barrier to future elective Half Hourly settlement | CMP266 seeks to prevent double charging of TNUoS for a meter electing to be HH settled, all demand within Measurement Class F & G will be charged under the TNUoS NHH methodology from April 2017 up until HH settlement is mandatory for all consumers. | National Grid | No | No | No | No | Yes | C | 2016-07-05 | C | 2016-11-30 | E | 2016-12-22 | Implemented | - | - | - | No | Mod | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/CUSC/Modifications/CMP266/ | National Grid | Closed | Yes
CUSC | CMP268 | Recognition of sharing by Conventional Carbon plant of Not-Shared Year-Round circuits | Recognition of sharing by Conventional Carbon plant of Not-Shared Year-Round circuits | SSE | No | No | No | No | Yes | C | 2016-08-02 | E | TBD | E | TBD | Workgroup | - | - | - | No | Urgent | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/CUSC/Modifications/CMP268/ | National Grid | Live | Yes
CUSC | CMP269 | Potential consequential changes to the CUSC as a result of CMP264 | This modification aims for the CMP264 Workgroup to address a number of consequential changes required to non-charging sections of the CUSC to reflect the CMP264 Proposal or any alternative proposals agreed by the CMP264 Workgroup. | SP | No | No | No | No | Yes | C | 2016-08-26 | C | 2016-11-28 | E | TBD | Authority Decision | - | - | Consequential of CMP264 |  | Mod | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/CUSC/Modifications/CMP269/ | National Grid | Live | Yes
CUSC | CMP270 | Potential consequential changes to the CUSC as a result of CMP265 | This modification aims for the CMP265 Workgroup to address a number of consequential changes required to non-charging sections of the CUSC to reflect the CMP265 Proposal or any alternative proposals agreed by the CMP265 Workgroup. | EDF Energy | No | No | No | No | Yes | C | 2016-08-19 | C | 2016-11-28 | E | TBD | Authority Decision | - | - | Consequential of CMP265 |  | Mod | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/CUSC/Modifications/CMP270/ | National Grid | Live | Yes
CUSC | CMP271 | Improving the cost reflectivity of demand transmission charges | This CUSC modification proposal aims to improve the cost reflectivity of demand transmission charges. It is proposed that the transmission charging methodology should include a Peak Security demand tariff levied at Triad, a Year Round demand tariff and revenue recovery levied on year round supplier demand. | RWE | No | No | No | No | Yes | C | 2016-09-20 | E | 2018-03-16 | E | 2021-04-01 | Assessment | On Track | - | CMP271 | SQSS | Mod | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/CUSC/Modifications/CMP271/ | National Grid | Live | Yes
CUSC | CMP272 | Aligning Condition C5 of the CUSC to changes introduced by the Code Governance Review Phase 3 | CMP272 seeks to implement the license changes to the CUSC arising from Ofgem’s Code Governance Review (Phase 3). | National Grid | No | No | No | No | Yes | C | 2016-09-29 | E | 2017-03-07 | C | 2017-03-14 | Assessment | On Track | - | CMP272 | No | Mod | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/CUSC/Modifications/CMP272/ | National Grid | Closed | Yes
CUSC | CMP274 | Winter TNUoS Time of Use Tariff (TToUT) for Demand TNUoS | This CUSC modification proposal aims to improve the cost reflectivity of demand transmission charges. It is proposed that the transmission charging methodology should include a Winter Weekday Time of use demand tariff which reflects the existing Demand Residual element of the existing methodology so that revenue recovery is levied over a longer period of assessment. | UK Power Reserve | No | No | No | No | Yes | C | 2016-09-29 | E | 2018-03-16 | E | 2021-04-01 | Assessment | On Track | - | CMP274 | SQSS | Mod | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/CUSC/Modifications/CMP274/ | National Grid | Live | Yes
CUSC | CMP275 | Transmission Generator Benefits in the provision of ancillary and balancing services – levelling the playing field. | CMP275 seeks that a principle of financial mutual exclusivity is introduced to prevent BM units from accessing multiple sources of duplicate and overlapping revenue from ancillary services on the same asset | UK Power Reserve | No | No | No | No | Yes | C | 2017-01-18 | E | TBD | E | TBD | Assessment | On Track | - | - | No | Mod | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/CUSC/Modifications/CMP275/ | National Grid | Live | Yes
CUSC | CMP276 | Socialising TO costs associated with "green policies" | This modification proposes a reduction in the demand residual element of the TNUoS £/kW (“Triad”) charge by creating two new charge lines for all demand offtakes: (i) with the level of charge based on a fixed charge per MPAN (or alternatively the import meter size of each consumer) and (ii) a simple per kWh charge on all consumers. Currently demand residual is the cost bucket which is left to capture all TO costs that cannot be otherwise allocated. Unless there is change the current methodology this is forecast to lead to high demand TNUoS payments at the time of Triads, which are widely recognised to be unacceptable and unsustainable. Mods CMP264 and CMP265 deal with a subset of the symptoms only, because they define the defect too narrowly. Their definition prohibits the full range of potential solutions being considered, and by excluding certain types of meter and treating some meters differently to others, this inevitably leads to a discriminatory outcome. This modification is defined to address the underlying cause of the escalation in demand residual and proposes a simple, non-discriminatory approach to its resolution which addresses equitable competition in ALL markets, domestic and international, reduces total cost to consumers and has the structure to form an enduring solution. | Alkane Energy Ltd | No | No | No | No | Yes | C | 2017-02-10 | E | TBD | E | TBD | Raised | On Track | - | - | No | Mod | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/CUSC/Modifications/CMP276/ | National Grid | Live | Yes
CUSC | CMP277 | Special License Condition 4J | This modification seeks to update Section 14.30.6 and 14.32 of the CUSC to reflect the changes made to the terms of the external BSUoS charges recoverable by the SO due to new License Condition 4J and changes to Special License Condition 4C.1. | National Grid | No | No | No | No | Yes | C | 2017-03-31 | E | TBD | E | TBD | Raised | On Track | - | - | No | Mod | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/CUSC/Modifications/CMP276/ | National Grid | Live | Yes
CUSC | CMP278 | BSIS 2017 Housekeeping | Update CUSC sections 14.30.11 and 14.32 to reflect the changed cap and collar and sharing factors of the Balancing Services Incentive Scheme as detailed in the current Ofgem Statutory License Consultation and; update 14.32 example BSUoS calculation to reflect changed terms within external BSUoS costs detailed in License change | National Grid | No | No | No | No | Yes | C | 2017-03-31 | E | TBD | E | TBD | Raised | On Track | - | - | No | Mod | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/CUSC/Modifications/CMP278/ | National Grid | Live | Yes
CUSC | CUSC Potential Change 1 | European Energy Balancing Guidelines - Replacement Reserves | European Energy Balancing Guidelines - Replacement Reserves | National Grid | No | No | Yes | No | Yes | E | 2017-10-01 | E | TBD | E | 2018-10-01 | Upcoming | On Track | This mod is set to be raised in Q4 2017. This mod is set to be implemented in Q4 2018. | EU Regulation/Law | Yes | Mod | N/A | National Grid | Upcoming | Yes
CUSC | CUSC Potential Change 2 | European Energy Balancing Guidelines - Manual Frequency Restoration Reserves (mFRR) | European Energy Balancing Guidelines - Manual Frequency Restoration Reserves (mFRR) | National Grid | No | No | Yes | No | Yes | E | 2020-07-01 | E | TBD | E | 2021-07-01 | Upcoming | On Track | This mod is set ot be raised Q3 2020. This mod is set to be implemented in Q3 2021 | EU Regulation/Law | Yes | Mod | N/A | National Grid | Upcoming | Yes
Dcode | DCRP1702 | Implementation of the Ofgem CGR3 recommendation on Significant Code Review | This Modification, therefore, seeks to align the Distribution Code and the Distribution Code Constitution and Rules with the amended provisions for Significant Code Review. The creation of this Modification was directed by Ofgem as part of the CGR3. Although it will impact the governance of the Distribution Code and the Distribution Code Constitution and Rules Distribution Code with specific changes applied to DIN 2.1 of the Code and Section 21 of the Constitution and Rules these changes will be focussed on the SCR process | ENA | No | No | No | No | Yes | C | 2017-12-08 | C | 2017-03-31 | C | 2017-04-01 | Implemented | On Track | RTA submitted on 09/03/17 | CGR3 | None | Mod | http://www.dcode.org.uk/dcrp/17/02.html | ENA | Closed | Yes
Dcode | DCRP1701 | Entry into Force of the EU Network Code “Transmission System Operational Guideline | The GB Distribution Code requires two minor modifications to DOC5 and DOC7 to ensure it is compliant with the EU Network Code “Transmission System Operation Guidelines” (TSOG). The TSOG is expected to enter into force in early summer 2017 and some parts of it are effective immediately. | ENA | No | No | Yes | No | Yes | E | 2016-12-08 | E | TBC | E | TBC | Awaiting authority Determination | On Track | RTA submitted on 09/03/17 | EU Regulation/Law | None | Mod | http://www.dcode.org.uk/dcrp/17/01.html | ENA | Live | Yes
Dcode | Dcode Potential Change 1 | Implementation of the requirements of the European Network Code - Demand Connection | This modification will cater for the introduction of the new ER G99 which will replace ER G59 for all new geneartaion connections from May 2019 | ENA | No | No | Yes | No | Yes | E | TBD | E | TBD | E | TBD | Upcoming | On Track | Will be raised at the the time of the GC0048 housekeeping mods | EU Regulation/Law | Grid Code | Mod |  | ENA | Upcoming | Yes
Dcode | Dcode Potential Change 2 | Changes to DOC 5 of the Distribution Code | This modification seek to take cognisance of the consequential Changes to the Distribution Code on Entry into Force of the Transmission System Operation Guidelines EU Network Code.For the Distribution Code and its scope, there are two places where specific articles in the TSOG require activities that are probably implicit in the GB arrangements, but are infrequently (if ever) exercised and are not explicitly recognized in the D Code drafting.Article 54.2 requires a User to notify the DNO if there is any “operational disturbance” which affects itability to retain compliance. It is suggested that a simple amendment to the definition of “event” as used predominantly in DOC7 (and DOC9) of the D Code would cover off this requirement. Article 54.3 requires the DNO to recognize a User initiated test plan so that the User can establish compliance (or for other reasons). The ability of a User to initiate such tests, separate from those jointly undertaken at commissioning etc, is only implicit in the D Code (and G59). A simple modification to DOC5 would make the testing provisions of DOC5 reciprocal in that they can be initiated formally by either DNO or the User. | ENA | No | No | Yes | No | Yes | E | 2017-12-08 | E | TBD | E | TBD | Upcoming | On Track | RTA submitted on 09/03/17 | EU Regulation/Law | Grid Code | Mod | http://www.dcode.org.uk/dcrp/17/01.html | ENA | Upcoming | Yes
Dcode | Dcode Potential Change 3 | To Implement within the Dcode the Fast Fault Current Injection requirements contained within the EU Network Code - Requirements for Generators | This modification will cater for the application of Fast Fault Current Injection requirements to Power Generating Modules. | GC 0048 | No | No | Yes | No | Yes | E | 2017-06-30 | E | TBD | E | TBD | Upcoming | TBC | Depends on National Grid GC 0048 modification | EU Regulation/Law | Grid Code | Mod | TBC | ENA | Upcoming | Yes
Dcode | Dcode Potential Change 4 | To Implement within the Dcode the Fault Ride Through requirements contained within the EU Network Code - Requirements for Generators | This modification will cater for the application of voltage / reactive power capability requirements to Power Generating Modules which are of Type B or above within the Dcode. | GC 0048 | No | No | Yes | No | Yes | E | TBD | E | TBD | E | TBD | Upcoming | TBD | Depends on National Grid GC 0048 modification | EU Regulation/Law | Grid Code | Mod | TBC | ENA | Upcoming | Yes
Dcode | Dcode Potential Change 5 | To Implement within the Dcode the Frequency Response requirements contained within the EU Network Code - Requirements for Generators | This modification will cater for the application of voltage / reactive power capability requirements to Power Generating Modules. | GC 0048 | No | No | Yes | No | Yes | E | TBD | E | TBD | E | TBD | Upcoming | TBD | Depends on National Grid GC 0048 modification | EU Regulation/Law | Grid Code | Mod | TBC | ENA | Upcoming | Yes
Dcode | Dcode Potential Change 6 | To Implement within the Dcode the Reactive Power and Voltage Control requirements contained within the EU Network Code - Requirements for Generators | This modification will cater for the application of voltage / reactive power capability requirements to Power Generating Modules which are of Type B or above within the Dcode. | GC 0048 | No | No | Yes | No | Yes | E | TBD | E | TBD | E | TBD | Upcoming | TBD | Depends on National Grid GC 0048 modification | EU Regulation/Law | Grid Code | Mod | TBC | ENA | Upcoming | Yes
Dcode | Dcode Potential Change 7 | Implementation of the new Engineering Recommendation G98 | This modification will cater for the introduction of the new ER G98 which will replace ERG83 for all new geneartaion connections from May 2019 | ENA | No | No | Yes | No | Yes | E | TBD | E | TBD | E | TBD | Upcoming | TBD | Target for public consultation Sept 2017 | EU Regulation/Law | Grid Code | Mod | TBC | ENA | Upcoming | Yes
Dcode | Dcode Potential Change 8 | Implementation of the new Engineering Recommendation G99 | This modification will cater for the introduction of the new ER G99 which will replace ER G59 for all new geneartaion connections from May 2019 | ENA | No | No | Yes | No | Yes | E | TBD | E | TBD | E | TBD | Upcoming | TBD | TBC | EU Regulation/Law | Grid Code | Mod | TBC | ENA | Upcoming | Yes
Dcode | Dcode Potential Change 9 | Implementation of the Transmission System Operators Guidelines | This modification will cater for the introduction of the new ER G99 which will replace ER G59 for all new geneartaion connections from May 2019 |  | No | No | Yes | No | Yes | E | TBD | E | TBD | E | TBD | Upcoming | TBD | TBC | EU Regulation/Law | Grid Code | Mod | TBC | ENA | Upcoming | Yes
DCUSA | DCP 138 | Implementation of alternative network use factor (NUF) calculation method in EDCM | This CP seeks to amend the method of calculating Network Use Factors for EDCM demand customers as defined within DCUSA to address the concerns raised by Ofgem in Condition 3 of the Ofgem decision document on EDCM import charges published in September 2011. | SSE Energy Supply Limited | No | No | No | No | No | C | 2012-06-18 | C | 2015-10-09 | C | 2017-04-01 | Implemented | On Track | - | - | No | CP | DCP 138 Working Group | ElectraLink | Live | Yes
DCUSA | DCP 160 | Non-Half Hourly (NHH) Notional Capacity | This CP seeks to revise Schedule 16 (along with appropriate CDCM and ARP Modelling changes) to introduce a notional spare capacity requirement to be applied to the average maximum demand when calculating NHH tariffs. The notional spare capacity should align with the same proportions which are calculated and allocated to Half Hourly (HH) tariffs. | UK Power Networks | No | Yes | No | No | No | C | 2013-01-08 | C | 2016-10-18 | n/a | n/a | Authority Rejected the change | On Track | Authority Rejected the change | - | No | CP | DCP 160 Working Group | ElectraLink | Closed | No
DCUSA | DCP 161 | Excess Capacity Charges | To improve the cost reflectivity of the excess capacity charge calculation within the CDCM and EDCM by removing the customer contributions and adding in any additional costs that should be attributed to this charge. Also, to consider applying the excess capacity charge on either a monthly, seasonal or time of day basis. | Electricity North West Limited | No | No | No | No | No | C | 2013-02-06 | C | 2015-10-21 | C | 2018-04-01 | Awaiting Implementation | On Track | - | - | No | CP | DCP 161 Working Group | ElectraLink | Live | Yes
DCUSA | DCP 169 | Seasonal Time of Day (SToD) HH Metered Tariffs in the CDCM | This CP seeks remove the restriction in paragraph 135 of Schedule 16 of DCUSA in order to allow the use of Seasonal Time of Day (SToD) tariffs to be calculated and applied. | UK Power Networks | No | Yes | No | No | No | C | 2013-03-13 | E | TBD | E | TBD | Assessment | At Risk | CP on Hold - Working Group is awaiting Ofgem decision on DCP 228 before deciding on how to proceed with DCP 169. DCP 225 is due to be implemented 1 Apr 2018 | - | No | CP | DCP 169 Working Group | ElectraLink | Live | Yes
DCUSA | DCP 181 | Previous Connection Terms Enduring | Where a distributor has agreed a bi-lateral connection agreement with an owner or occupier in respect of a connection point, those terms should bind on change of ownership or occupation. | UK Power Networks | No | No | No | No | No | C | 2013-06-17 | C | 2016-06-15 | C | 2016-10-01 | Implemented | On Track | - | - | No | CP | DCP 181 Working Group | ElectraLink | Closed | No
DCUSA | DCP 204 | Smart Metering Related Amendments to Schedule 8 | The intent of this Change Proposal (CP) is to amend DCUSA Schedule 8 to reflect the migration of load switching technologies deployed by Suppliers in customer premises from established devices, such as radio teleswitches (RTS) and timeswitches, to smart metering technologies. | Scottish and Southern Electric Power Distribution | Yes | No | No | No | No | C | 2014-02-27 | C | 2016-02-23 | C | 2016-09-01 | Implemented | On Track | - | - | No | CP | DCP 204 Working Group | ElectraLink | Closed | No
DCUSA | DCP 209 | Resolving Unregistered Customers | This CP seeks to improve communications with unregistered customers, set out processes for managing unregistered customers up to, but excluding, the registration process itself and where necessary new obligations on parties. | Nothern Powergrid | No | No | No | No | No | C | 2014-05-08 | C | 2016-08-30 | C | 2016-10-01 | Implemented | On Track | - | - | Proposed addition of a note to the MRA dataflows. | CP | DCP 209 Working Group | ElectraLink | Closed | No
DCUSA | DCP 222 | Non Billing Of Excess Reactive Power Charges | This CP proposes the removal of the excess reactive power charge when a DNO requests that a generator operates outside of the 0.95 power factor limit. | Western Power Distribution | No | No | No | No | No | C | 2014-12-02 | C | 2016-08-15 | C | 2018-04-01 | Awaiting Implementation | On Track | - | - | No | CP | DCP 222 Working Group | ElectraLink | Live | Yes
DCUSA | DCP 226 | Housekeeping 66/72/73/77/80 | This CP seeks to review and revise the DCUSA document to incorporate housekeeping log items 66/72/73/77/80 | UK Power Networks | No | No | No | No | Yes | C | 2015-01-05 | E | TBD | E | TBD | Assessment | At Risk | CP on Hold - housekeeping change to review refrences throuout the DCUSA Document. Work on this is to be carried out after the 1 October 2016 DCUSA Release. | - | No | CP | DCP 226 | ElectraLink | Live | Yes
DCUSA | DCP 227 | Removing the inconsistency in the application of Peaking Probabilities in the CDCM | ​The proposal changes the way that peaking probabilities are applied in the CDCM and therefore affects CDCM tariffs. | British Gas | No | No | No | No | No | C | 2015-01-13 | C | 2015-10-21 | C | 2017-04-01 | Implemented | On Track | - | - | No | CP | DCP 227 Working Group | ElectraLink | Live | Yes
DCUSA | DCP 228 | Revenue Matching in the CDCM | ​The intent of this proposal is to change the way revenue matching (scaling) is achieved within the CDCM to accurately reflect the price differentials produced by the cost-reflective incremental 500MW model. Currently this is achieved in a manner which primarily affects only the day/red unit prices. This change proposal intends to replace the current method of revenue matching such that all unit rates face the same absolute p/kWh adjustment (except where any unit rates are subject to a floor price). | British Gas | No | No | No | No | No | C | 2015-01-13 | C | 2016-09-08 | C | 2018-04-01 | Awaiting Implementation | On Track | - | - | No | CP | DCP 228 Working Group | ElectraLink | Live | Yes
DCUSA | DCP 234 | Merging the PCDM and extended PCDM | To replace the Price Control Disaggregation (PCDM) and extended PCDM models with one model.To create a new schedule in DCUSA which contains the legal text that relates to IDNO charging that is currently contained in Schedules 16, 17 and 18. | Electricity North West Limited | No | No | No | No | No | C | 2015-02-27 | C | 2016-08-03 | C | 2018-04-01 | Awaiting Implementation | On Track | - | - | No | CP | DCP 234 Working Group | ElectraLink | Live | Yes
DCUSA | DCP 243 | Treatment of Customer Contributions in the CDCM | ​This CP seeks to revise DCUSA Schedule 16 to utilise current source data to determine a common industry set of modelling inputs in order to improve clarity in the approach to be used in calculating ‘Customer contribution under the current connection charging policy’ for use in CDCM table 1060. | UK Power Networks | No | No | No | No | No | C | 2015-06-05 | E | TBD | E | TBD | Assessment | On Track | Under Development - Working Group developing the CP solution | - | No | CP | DCP 243 Working Group | ElectraLink | Live | Yes
DCUSA | DCP 244 | MOP Leaving Site for Cat A Situations | ​This CP seeks to remove the DNO Intervention SLA for attending Category A jobs where the MOP operative will not or has not remained on site. And to address housekeeping issues with the DCP 195A legal text | UK Power Networks | No | No | No | No | No | C | 2015-06-19 | E | TBD | E | TBD | Assessment | At Risk | CP on Hold - Working Group is waiting for Operational Delivery Group (ODG) to develop MOP guidance on leaving site where there is a category A situation. | - | No | CP | DCP 244 Working Group | ElectraLink | Live | Yes
DCUSA | DCP 251 | Clarification And Extension Of The Application Of LDNO Tariffs Under The CDCM | The intent of this proposal is to Correct drafting errors in the specification of the distribution systems that are eligible for LDNO tariffs under the CDCM and under the EDCM.2. Ensure that there the charging methodologies do not impose undue discrimination between licensed and licence-exempt distribution systems.3. Restore the 50 per cent LDNO discount on indirect costs which was removed by the approved legal text for DCP 185 in cases where the fixed adder is negative.​ | The Electricity Network Company | No | No | No | No | No | C | 2015-10-15 | E | TBD | E | TBD | Assessment | On Track | Under Development - Working Group developing the CP solution DCP251/2 WG meeting indicated that the change declaration may be issued in June 2017, with an Ofgem decision anticipated in August 2017 | - | BSC & MRA -Change of arrangements to how Unlicensed Customers are charged could have an impact upon both the MRA and BSC in relation to data flows or arrangements for operation | CP | DCP 251 & DCP 252 Working Group | ElectraLink | Live | Yes
DCUSA | DCP 252 | Clarification And Extension Of The Application Of Portfolio Tariffs Under The EDCM | The intent of this proposal is toCorrect drafting errors and inconsistencies in the specification of the distribution systems that are eligible for Portfolio tariffs under the EDCM (schedules 17 and 18).2. Establish arrangements that ensure that methodologies in schedules 17 and 18 do not impose undue discrimination between licensed and licence exempt distribution systems.​ | The Electricity Network Company | No | No | No | No | No | C | 2015-10-15 | E | TBD | E | TBD | Assessment | On Track | Under Development - Working Group developing the CP solution DCP251/2 WG meeting indicated that the change declaration may be issued in June 2017, with an Ofgem decision anticipated in August 2017 | - | BSC & MRA - Change of arrangements to how Unlicensed Customers are charged could have an impact upon both the MRA and BSC in relation to data flows or arrangements for operation | CP | DCP 251 & DCP 252 Working Group | ElectraLink | Live | Yes
DCUSA | DCP 253 | Retightening and remaking of whole current metering system terminal connections. | ​This Change Proposal seeks to permit a DNO/IDNO, when it replaces its service cut-out, to retighten the meter tails and customer tails connecting into and out of a whole current meter and/or remake connections to meter terminals as necessary prior to re-energisation. | UK Power Networks | No | No | No | No | No | C | 2015-11-03 | C | 2016-09-21 | C | 2016-09-01 | Implemented | On Track | - | - | No | CP | DCP 253 Working Goup | ElectraLink | Closed | No
DCUSA | DCP 255 | Changes to Electricity (Connection Charges) Regulations 2002 | ​This Change Proposal (CP) seeks to incorporate changes in the CCCM as a result of changes to the Electricity (Connection Charges) Regulations 2002​. | Electricity North West Limited | No | No | No | No | No | C | 2015-11-06 | E | TBD | E | TBD | Assessment | On Track | The Working Group are awaiting the receipt of the final ECCR 2016 legal text from BEIS (formaly DECC) before progressing this change. | - | No | CP | DCP 255 Working Group | ElectraLink | Live | Yes
DCUSA | DCP 256 | Change to DCUSA to mitigate risks of non-payment of non-payment of DCUSA invoices | ​This DCP seeks to improve the transparency of likely DCUSA costs to enables Parties to better plan and budget for DCUSA invoices as well as improving the effectiveness of the arrangements for following up of non-payment of DCUSA invoices. | British Gas | No | No | No | No | No | C | 2015-11-10 | C | 2016-09-21 | C | 2016-10-01 | Implemented | On Track | - | - | No | CP | DCP 256 Working Group | ElectraLink | Closed | No
DCUSA | DCP 262 | Schedule 19 Credit/Re-invoice for HH Specific Data | ​The intent of this CP is to include a timeline for credit/re-invoice from DNOs to LDNOs upon the receipt of updated HH DUoS data | ESP Electricity Limited | No | Yes | No | No | No | C | 2016-01-13 | C | 2016-07-29 | C | 2016-09-01 | Implemented | On Track | - | - | No | CP | DCP 262 Working Group | ElectraLink | Closed | No
DCUSA | DCP 263 | NTC DEH Gap | This CP seeks to amend the NTC so that they cater for DNOs’ connections to non-metered DEH networks.There should be no impact from this change on the applicability of the NTC to boundary metered DEHs or on the contractual terms suppliers put in place by virtue of Schedule 2A of DCUSA. | UK Power Networks | No | No | No | No | No | C | 2016-01-22 | E | 17/01/201 | E | 2017-02-23 | Implemented | On Track | Change Report issued for Voting | - | No | CP | DCP 263 Working Group | ElectraLink | Live | Yes
DCUSA | DCP 264 | Introduction of Energy Theft Tip Off Line Service | This CP seeks to include provisions relating to the Energy Theft Tip Off Line Service in the DCUSA. | E.ON UK Plc | No | No | No | No | No | C | 2016-02-15 | C | 2016-08-15 | C | 2016-08-22 | Implemented | On Track | - | - | No | CP | ETTOS Working Group | ElectraLink | Closed | No
DCUSA | DCP 266 | The calculation and application of IDNO discounts | This change seeks to change the way in which DNO tariffs to IDNOs are calculated in the CDCM. Instead of calculating an IDNO percentage discount by comparing the avoided total cost (p/kWh) with the total cost (p/kWh) in the CDCM “Price Control Disaggregation Model” (PCDM), the intent of this change proposal is that the avoided total cost (p/kWh) calculated in the PCDM is compared with the average p/kWh figure for each All The Way (ATW) CDCM tariff in order to determine the IDNO % discount factor to be applied to each of the tariff components of the CDCM ATW tariff. | British Gas | No | No | No | No | No | C | 2016-03-09 | E | n/a | E | n/a | Assessment | On Track | Under Development - Working Group developing the CP solution | - | No | CP | DCP 266 Working Group | ElectraLink | Live | Yes
DCUSA | DCP 267 | Introduction of a new definition for 'Confirmed Theft' | This CP introduces a definition for Confirmed Theft under DCUSA to ensure consistency across Suppliers in submitting confirmed theft detections under TRAS. | British Gas | No | No | No | No | No | C | 2016-03-09 | C | 2016-09-14 | C | 2016-11-03 | Implemented | On Track | - | - | No | CP | DCP 267 Working Group | ElectraLink | Closed | No
DCUSA | DCP 268 | DUoS Charging Using HH settlement data | This CP seeks to facilitate a transition to half-hourly (HH) settlement for non-half hourly (NHH) customers by moving to a time band charging basis, based on the HH (profiled) data used in settlement. | Nothern Powergrid | No | Yes | No | No | No | C | 2016-03-14 | E | TBD | E | 2018-04-01 | Assessment | On Track | Under Development - Working Group developing the CP solution | - | BSC - P339 | CP | DCP 268 Working Group | ElectraLink | Live | Yes
DCUSA | DCP 269 | Revenue Protection Service Withdrawal Period | The intent of this CP is to require 3 months’ notice to be given by a DNO in the event that they wish to withdraw the Revenue Protection service they provide under DCUSA. | Npower Ltd | No | No | No | No | No | C | 2016-04-25 | C | 2016-07-12 | C | 2016-09-01 | Implemented | On Track | - | - | No | CP | DCP 269 Working Group | ElectraLink | Closed | No
DCUSA | DCP 270 | Removal of HV Medium tariff from CDCM | This CP seeks for the removal of the HV Medium Non-domestic tariff and consideration of the removal of both the LV and LV Sub Medium Non Domestic tariffs from the CDCM. | Nothern Powergrid | No | No | No | No | No | C | 2016-04-28 | C | 2017-11-16 | n/a | n/a | Rejected | On Track | Authority Rejected the change | - | No | CP | DCP 270 Working Group | ElectraLink | Closed | No
DCUSA | DCP 271 | TRAS - Process and Costs of Providing Additional Hunter Facilities | This change seeks to introduce a process for Suppliers who wish to procure additional Hunter facilities from the TRAS Service Provider and to make those costs transparent to the Supplier community | Npower Ltd | No | No | No | No | No | C | 2016-05-11 | C | 2016-09-15 | C | 2016-11-03 | Implemented | On Track | - | - | No | CP | TRAS Expert Group | ElectraLink | Closed | No
DCUSA | DCP 272 | TRAS – Amendment of Schedule 25 Appendix 2 | This CP seeks to introduce a clear data item list in DCUSA for delivery of the TRAS solution. | E.ON UK Plc | No | No | No | No | No | C | 2016-05-11 | C | 2016-09-15 | C | 2016-11-03 | Implemented | On Track | - | - | No | CP | TRAS Expert Group | ElectraLink | Closed | No
DCUSA | DCP 273 | Align CDCM table 1001 (target revenue) to latest Schedule 15 template | The intent of this proposal is to align table 1001 in the CDCM to the current format of table in Schedule 15. | Nothern Powergrid | No | No | No | No | No | C | 2016-05-18 | C | 2016-10-14 | C | 2018-04-01 | Awaiting Implementation | On Track | - | - | No | CP | DCP 273 Working Group | ElectraLink | Live | Yes
DCUSA | DCP 274 | The application of export capacity charges in the EDCM | The intent of this change proposal is to amend the EDCM methodology to ensure that distributed generation and storage sites do not pay distribution use of system charges for the import and export from a site where the same assets are used. | Neas Energy Limited | No | No | No | No | No | C | 2016-06-10 | E | TBD | E | 2018-04-01 | Assessment | On Track | Under Development - Working Group developing the CP solution | - | No | CP | DCP 274 Working Group | ElectraLink | Live | Yes
DCUSA | DCP 275 | Code Governance Review 3 & SLC 22 | The CP seeks to implement the distribution licence changes arising from Ofgem’s Code Governance Review Phase 3 Final Proposals impacting DCUSA governance. | UK Power Networks | No | No | No | No | No | C | 2016-06-10 | C | 2016-11-15 | C | 2017-02-23 | Implemented | On Track | - | - | No | CP | DCP 275 | ElectraLink | Live | Yes
DCUSA | DCP 276 | Amendments to CDCM LV Substation Tariff ‘Note 5’ | This Change Proposal intends to amend the text of Note 5 to Paragraph 144 of Schedule 16 (the CDCM), to: 1)Remove the customer or supplier evidence terms in Note 5, to better reflect responsibilities for allocation of a customer’s DUoS tariff; and 2)Require LV Substation tariff charges to be applied from when a customer became eligible for this tariff, subject to limitations legislation. | Scottish and Southern Electric Power Distribution | No | No | No | No | No | C | 2016-07-04 | C | 2016-09-14 | C | 2016-11-03 | Implemented | On Track | - | - | No | CP | DCP 276 | ElectraLink | Closed | No
DCUSA | DCP 277 | Schedule 25 – Amendment to Appendix 2 - Conditionality | Following on from the changes in DCP272 the TRAS Expert Group has reviewed the conditionality for data items within the TRAS Service Providers Programming Manual and seeks to update some of the data items conditional/mandatory status because the current conditionality cannot be always met. Additionally, some JCode/RGMA Codes also require back population as they were missed on the original drafting. | E.ON UK Plc | No | No | No | No | No | C | 2016-07-13 | C | 2016-11-17 | C | 2017-02-23 | Implemented | On Track | - | - | No | CP | TRAS Expert Group | ElectraLink | Live | Yes
DCUSA | DCP 278 | Allocation of Users to the ETTOS Secure Email Service | This CP seeks to include the rules for allocation of user accounts for the ETTOS secure email service in the DCUSA | Npower Ltd | No | No | No | No | No | C | 2016-07-13 | C | 2016-12-15 | C | 2017-02-23 | Implemented | On Track | - | - | No | CP | ETTOS Working Group | ElectraLink | Live | Yes
DCUSA | DCP 279 | Linking Credit Cover to the Annual Iteration Process | This change proposal has been submitted in order to update those clauses in DCUSA Schedule 1 (Credit Cover) that refer to the ‘Regulatory Asset Value (RAV)’ as the new price control, RIIO-ED1, redefines the calculation of a DNO’s Regulatory Asset Value. | Electricity North West Limited | No | No | No | No | No | C | 2016-07-29 | C | 2016-12-23 | C | 2017-02-23 | Implemented | On Track | - | - | No | CP | DCP 279 Working Group | ElectraLink | Live | Yes
DCUSA | DCP 280 | Clarification of TRAS Accession Process | This CP proposes to amend the TRAS Schedules to clarify the TRAS accession process. It has been assessed that there is a three-month time lag between a new Supplier starting to register metering systems and actually submitting data into TRAS. This time lag has not been reflected within the current TRAS Schedule and a change is required to explicitly reference the time lag so new parties are clear when they need to provide their initial data submission. The three-month time lag will also ensure that the new Supplier has time to work with the Service Provider to start submitting data. | British Gas | No | No | No | No | No | C | 2016-08-18 | C | 2016-12-15 | C | 2017-02-23 | Implemented | On Track | The voting period was extended to align with the equivilent SPAA CP (CP16/346) | - | No | CP | DCP 280 Working Group | ElectraLink | Live | Yes
DCUSA | DCP 281 | Changes to Schedule 19 – Portfolio Billing | This CP seeks to ensure that HH Portfolio data is reported to DNOs in a consistent manner by all embedded LDSOs and to define how revised data must be reported. | UK Power Networks | No | Yes | No | No | No | C | 2016-09-14 | E | TBD | E | 2019-04-01 | Assessment | On Track | Under Development - Working Group developing the CP solution | - | No | CP | DCP 281 Working Group | ElectraLink | Live | Yes
DCUSA | DCP 282 | Embedded Distribution Network Operator (EDNO) UMSO | This CP seeks to facilitate the management and trading of UMS apparatus connected to EDNO networks via the “host” DNO’s UMSO service on one combined inventory, without the need for additional MPANs, following a request from the customer to the EDNO to do so. The EDNO will be deemed to have passed such a request to the DNO, through DCUSA wording, such that the DNO does not need to perform further checking or validation on any inventory it receives (i.e. to the extent of checking whether the inventory contains data for the correct EDNO or not). | UK Power Networks | No | No | No | No | No | C | 2016-09-14 | E | 2017-03-14 | E | TBD | Assessment | On Track | Under Development - Working Group developing the CP solution | - | No | CP | DCP 282 Working Group | ElectraLink | Live | Yes
DCUSA | DCP 283 | The calculation of generation credits in the CDCM | The intent of this CP is to amend the calculation of credits for embedded generation to more closely reflect the benefits they bring to Distribution Network Operators. | MVV Environment Services Limited | No | No | No | No | No | C | 2016-10-12 | E | TBD | E | 2019-04-01 | Assessment | On Track | Under Development - Working Group developing the CP solution | - | No | CP | DCP 283 Working Group | ElectraLink | Live | Yes
DCUSA | DCP 284 | The application of scaling to generation credits in the CDCM | The intent of this CP is to amend the calculation of credits for embedded generation to more closely reflect the benefits they bring to Distribution Network Operators by including an element of scaling. | MVV Environment Services Limited | No | No | No | No | No | C | 2016-10-12 | E | TBD | E | 2019-04-01 | Assessment | On Track | Under Development - Working Group developing the CP solution | - | No | CP | DCP 284 Working Group | ElectraLink | Live | Yes
DCUSA | DCP 285 | Schedule 23, Appendix 1 SLC References | The intent of this change is to remove references to Supply Licence Condition (SLC) 12.16 in Schedule 23, Appendix 1 and replace them with the updated SLCs. | British Gas | No | No | No | No | No | C | 2016-10-12 | E | 2017-01-24 | E | 2017-02-23 | Implemented | On Track | Under Development - legal text being updated | - | No | CP | DCP 285 Change Proposal | ElectraLink | Live | Yes
DCUSA | DCP 286 | Formalising the Theft Steering Group | This change proposes to formally delegate the DCUSA Panel and DCUSA Ltd Board powers in relation to the Theft Risk Assessment Service (TRAS) and Energy Theft Tip Off Line Service (ETTOS) to the Theft Steering Group (TSG) | E.ON UK Plc | No | No | No | No | No | C | 2016-11-09 | E | TBD | E | TBD | Assessment | On Track | Under Development - Definition Stage | - | SPAA | CP | DCP 286 Change Proposal | ElectraLink | Live | Yes
DCUSA | DCP 287 | Generation Credits in the EDCM | The intent of this Change Proposal is to amend the calculation of credits for embedded generation in the EDCM to take account of potential cost savings for DNOs that can be attributed to embedded generation in the areas of transmission exit charges, direct costs, indirect costs and network rates. | MVV Environment Services Limited | No | No | No | No | No | C | 2016-11-11 | E | TBD | E | 2019-04-01 | Assessment | On Track | - | - | No | CP | DCP 287 Change Proposal | ElectraLink | Live | Yes
DCUSA | DCP 288 | Introduction of the Electricity Theft Detection Incentive Scheme | The intent of this Change Proposal (CP) is to introduce an Electricity Theft Detection Incentive Scheme in line with Ofgem’s decision document entitled “Tackling electricity theft – the way forward” published on 4th March 2014 | British Gas | No | No | No | No | No | C | 2016-12-12 | E | TBD | E | TBD | Assessment | On Track | - | - | No | CP | DCP 288 Change Proposal | ElectraLink | Live | Yes
DCUSA | DCP 289 | Creation of Distribution Charging Methodology Development Group | The intent of this CP is to formalise the creation of a new single Standing Issues Working Group for the Use of System charging methodologies and related topics within DCUSA. | South Eastern Power Networks plc | No | No | No | No | No | C | 2016-12-16 | E | TBD | E | TBD | Assessment | On Track | - | - | No | CP | DCP 289 Change Proposal | ElectraLink | Live | Yes
DCUSA | DCP 290 | Housekeeping Change to Update PCDM Model References | The intent of this Change Proposal is to facilitate the updating of the title, model number and issue date of the PDCM as referenced in Schedules 16, 17 and 18, which was not correctly applied in the legal text of DCP234. | South Eastern Power Networks plc | No | No | No | No | No | C | 2017-01-17 | E | TBD | C | 2018-04-01 | Awaiting Implementation | On Track | - | - | No | CP | DCP 290 Change Proposal | ElectraLink | Live | Yes
DCUSA | DCP 291 | Application of Generation Credits to EDCM Customers | The intent of this Change Proposal is to apply EDCM generation credits to all generators whether intermittent or non-intermittent, on the basis that a LRIC/FCP charge 1 exists. | Western Power Distribution (East Midlands) plc | No | No | No | No | No | E | 2017-02-17 | E | TBD | E | 2019-04-01 | Definition | On Track | - | - | No | CP | DCP 291 Change Proposal | ElectraLink | Live | Yes
DCUSA | DCP 292 | Align DCUSA Schedule 15 table 3 to the CDCM tariff structure following the approval DCP 222 ‘Non billing of Excess Reactive Power Charges’ | This CP seeks to amend DCUSA Schedule 15 to reflect the CDCM tariffs introduced as a result of the approval of DCP 222 ‘Non billing of Excess Reactive Power Charges’. | Northern Powergrid (Northeast) Ltd | No | No | No | No | No | E | 2017-02-10 | E | TBD | E | 2017-06-29 | Change Report | On Track | - | - | No | CP | DCP 292 Change Proposal | ElectraLink | Live | Yes
DCUSA | DCP 293 | Charging Methodology Cut-off Date | DCUSA has a requirement for DNOs to provide fifteen months’ notice of changes to Use of System charges. This necessitates DNOs to have complete and final versions of the charging methodologies and a complete and final suite of fully tested charging models (CDCM, EDCM, PCDM and ARP) for the relevant charging year prior to initiating the calculation and validation of revised charges. This change looks to establish a cut-off date for the finalisation of the charging methodologies at 17 months prior to the date that the methodology would become effective. Establishing this cut-off date will provide a 2-month time window for DCUSA to provide charging models and DNOs to test the new charging models and then to calculate, test and approve revised charges. | South Eastern Power Networks plc | No | No | No | No | No | E | 2001-02-14 | E | TBD | E | 2017-10-01 | Definition | On Track | - | - | No | CP | DCP 293 Change Proposal | ElectraLink | Live | Yes
DCUSA | DCP 294 | Capacity Management following acceptance of Connection Offer | This change seeks to put arrangements in place that set out the principles under which the unutilised maximum capacity specified in connection offers or in bilateral connection agreements with IDNOs can be managed in an economic and efficient manner whilst protecting the legitimate requirements of parties requiring Capacity which was agreed in connection offers. | The Electricity Network Company | No | No | No | No | No | C | 2017-03-01 | E | 2017-10-17 | E | 2017-11-02 | Definition | On Track |  | N/A | N/A | CP | DCP 294 Working Group | ElectraLink | Live | Yes
DCUSA | DCP 295 | CVA Registrants acceding to the DCUSA | This change seeks to facilitate BSC Modification PXXX which is to oblige CVA Registrants connecting to a Distribution System to accede to the DCUSA which will negate the need for a bilateral Use of System Agreements between the LDSO and the CVA Registrants saving administrative cost and effort and promoting efficiency and consistency. | Western Power Distribution (East Midlands) plc | No | No | No | No | No | C | 2017-03-07 | E | TBC | E | TBC | Raised | On Track |  | N/A | N/A | CP | DCP 295 Change Proposal | ElectraLink | Live | Yes
GC | GC0048 | Requirements for Generators - Implementation of European Network Code | Requirements for Generators (RfG) – which sets functional requirements that new generators connecting to the network (both distribution and transmission) will need to meet, as well as responsibilities on TSOs and DNOs. This includes: Fault Ride Through, Fast fault Current Injection, Voltage & Reactive, Compliance and system management. Additional items to be included as this progresses are: Banding Threshold Setting, Frequency response and House Keeping | National Grid | No | No | Yes | No | Yes | C | 2013-07-01 | C | TBD | C | 2018-05-17 | Raised | On Track | This is a workgroup, and it is expected that this workgroup will manage the raising of all additional modifications required to deliver The deadline for EIF is fixed. National Implementation Compliance date is 17/05/2018 | European Regulation/Law | Yes | Joint Working Group | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/Grid-code/Modifications/GC0048/ | National Grid | Live | Yes
GC | GC0077 | Suppression of Sub-Synchronous Resonance from Series Capacitive Compensation | It is proposed that the Grid Code is changed to provide clarity that Transmission Licensees installing Series Capacitive Compensation devices or HVDC Convertors will ensure that Sub-synchronous Resonance and Sub-synchronous Torsional Interaction risks are appropriately mitigated. | National Grid | No | No | No | No | Yes | C | 2013-08-14 | E | 2017-03-01 | E | 2017-04-01 | Assessment | On Track | - | - | SQSS | Mod | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/Grid-code/Modifications/GC0077/ | National Grid | Live | Yes
GC | GC0079 | GC0035 / GC0079 Frequency Changes during Large Disturbances and their effect on the total system - Phase 1 & 2 | GC0035 / GC0079 Frequency Changes during Large Disturbances and their effect on the total system - Phase 1 & 2 | National Grid | No | No | No | No | Yes | C | 2008-05-21 | E | TBD | E | TBD | Assessment | At Risk | Ongoing for 8 years with with deliberations over funding arrangements to be decided. | - | No | Mod | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/Grid-code/Modifications/GC0079/ | National Grid | Live | Yes
GC | GC0086 | Open Governance | This seeks to allow parties other than NGET to raise Modification Proposals to the Grid Code and to introduce a number of principles that currently exist in some of the other industry codes. | National Grid | No | No | No | No | Yes | C | 2014-07-02 | E | 2017-02-01 | E | 2017-03-01 | Assessment | On Track | - | - | No | Mod | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/Grid-code/Modifications/GC0086/ | National Grid | Live | Yes
GC | GC0087 | Requirements for Generators Frequency Provisions | Proposals to develop the Frequency Response provisions of the Grid Code under GC0022 did not reach a conclusion. National Grid believes that there are a number of outstanding defects with the Frequency Response provisions of the Grid Code which should be addressed in a new Workgroup. | National Grid | No | No | No | No | Yes | C | 2014-11-04 | E | 2017-07-01 | E | 2017-08-01 | Assessment | On Track | - | GC0022 | No | Mod | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/Grid-code/Modifications/GC0087/ | National Grid | Live | Yes
GC | GC0090 | HVDC - Implementation of European Network Code | HVDC – sets functional requirements for HVDC connections including offshore HVDC networks which connect Offshore generation schemes. This will include: Fault Ride Through, Voltage & Reactive, Frequency Response, Compliance & House Keeping | National Grid | No | No | Yes | No | Yes | C | 2015-07-01 | C | TBD | C | 2018-09-29 | Raised | On Track | This is a workgroup, and it is expected that this workgroup will manage the raising of all additional modifications required to deliver Deadline for EIF is fixed. National Implementation Compliance date is 29/09/2018 | European Regulation/Law | No | Issues Working Group | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/Grid-code/Modifications/GC0090/ | National Grid | Live | Yes
GC | GC0091 | Application of the the Demand Connection Code - Implementation of European Network Code | Demand Connection Code (DCC) – which sets out the functional requirement for new demand users and Distribution Network connections, as well as responsibilities on TSOs and DNOs. This will include: Technical requirements, Demand Side Response and housekeeping | National Grid | No | No | Yes | No | Yes | C | 2016-03-01 | C | TBD | C | 2018-09-07 | Raised | On Track | This is a workgroup, and it is expected that this workgroup will manage the raising of all additional modifications required to deliver. Deadline for EIF is fixed. National Implementation Compliance date is 07/09/2018 | European Regulation/Law | Yes | Joint Working Group | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/Grid-code/Modifications/GC0091/ | National Grid | Live | Yes
GC | GC0095 | GB implementation workgroup for Transmission System Operation Guideline (TSOG) European Network Code | This is a workgroup to deliver the requirements TSOG Implementation - this includes: Blackout State Threshold, Roles an Responsibilities of the SGUs and Operational Testing, Data Exchange, Coordinated Security Analysis, Regional Outage Coordination, Operational Agreements, Reserve Providers | National Grid | No | No | Yes | No | Yes | C | 2016-05-27 | E | TBD | C | 2018-10-01 | Assessment | On Track | All areas of TSOG are curently held within one workgroup, this may change as modification are raised to deliver respective areas are completed There is a range of Entry into Force dates ranging to October 2018 | EU Regulation/Law | Yes | Working Group | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/Grid-code/Modifications/GC0095/ | National Grid | Live | Yes
GC | GC0096 | Energy Storage | This is a Grid Code Workgroup to consider the appropriate technical requirements for Energy Storage technologies connecting to the Transmission system | National Grid | No | No | No | No | Yes | C | 2016-05-18 | E | 2017-05-01 | E | 2017-06-01 | Assessment | On Track | - | - | No | Mod | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/Grid-code/Modifications/GC0096/ | National Grid | Live | Yes
GC | GC0097 | European Energy Balancing Guidelines - Replacement Reserves - TERRE | Compliance with changes introduced from the European Energy Balancing Guidelines assocoaited with Project TERRE | National Grid | No | No | Yes | No | Yes | E | 2016-11-16 | C | TBD | E | 2019-07-01 | Assessment | On Track | This modification maybe required to address changes associated with project TERRE Deadline for EIF is fixed. This mod is set to be implemented Q3 2019. | EU Regulation/Law | Yes | Working Group | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/Grid-code/Modifications/GC0097/ | National Grid | Live | Yes
GC | Grid Code Potential Change 1 | Implementation of CACM European Network Code | Enable data provision between NGET and other TSOs to align with European requirements (provisional) | National Grid | No | No | Yes | No | Yes | E | 2017-01-01 | C | TBD | E | 2018-01-01 | Upcoming | On Track | This modification may be required to address the requirements of the Common Grid Model This mod is currently set to be raised in Q1 2017 Deadline for EIF is fixed. Compliance for CGM is Jan 2018 - and TBC based on methodologies | European Regulation/Law | Yes | Mod |  | National Grid | Upcoming | Yes
GC | Grid Code Potential Change 2 | European Energy Balancing Guidelines - General Compliance | Compliance with changes introduced from the European Energy Balancing Guidelines | National Grid | No | No | Yes | No | Yes | E | 2017-01-01 | E | TBD | E | 2018-07-01 | Upcoming | On Track | This modification maybe required to address general compliance requirements of the EB GL The mod if currently set to be raised in Q1 2020. Deadline for EIF is fixed. The mod if set to be implemented in Q3 2021. | EU Regulation/Law | Yes | Mod |  | National Grid | Upcoming | Yes
GC | Grid Code Potential Change 3 | European Energy Balancing Guidelines - Manual Frequency Restoration Reserves (mFRR) | Compliance with changes introduced from the European Energy Balancing Guidelines | National Grid | No | No | Yes | No | Yes | E | 2020-01-01 | E | TBD | E | 2021-07-01 | Upcoming | On Track | This modification maybe required to address mFRR requirements of the EB GL This mod is set to be raised in Q1 2020. Deadline for EIF is fixed. This mod is set to be implemented in Q3 2021. | EU Regulation/Law | Yes | Mod |  | National Grid | Upcoming | Yes
GC | Grid Code Potential Change 4 | European Emergency & Restoration Code - System Defence & Restoration Plan | European Emergency & Restoration Code - System Defence and Restoration Plan, resulntant mods dependeant on plan contents | National Grid | No | No | Yes | No | Yes | E | 2017-07-01 | E | TBD | E | 2018-07-01 | Upcoming | On Track | This mod is set to be raised in Q2 2017. This mod is set to be implemente din Q3 2018. | EU Regulation/Law | TBD | Mod |  | National Grid | Upcoming | Yes
GC | Grid Code Potential Change 5 | European RfG Banding and RfG/HVDC requirements | Changes needed resulting from RfG Banding and Fast Fault Current Injection, as well as RfG and HVDC Fault Ride Through | National Grid | No | No | Yes | No | Yes | E | 2017-04-19 | E | TBD | E | 2018-04-01 | Upcoming | On Track | This mod is set to be raised in Q2 2017. This mod is set to be implementedin Q2 2018. | EU Regulation/Law | TBD | Mod |  | National Grid | Upcoming | Yes
GC | Grid Code Potential Change 6 | RfG and HVDC Voltage and Frequency Response requirements | Resultant changes in relation to RfG and HVDC Voltage/Reactive and Frequency Response requirements | National Grid | No | No | Yes | No | Yes | E | 2017-04-19 | E | TBD | E | 2018-01-01 | Upcoming | On Track | This mod is set to be raised in Q2 2017 Deadline for EIF is fixed. This mod is set to be implemented in Q1 2018. | EU Regulation/Law | TBD | Mod |  | National Grid | Upcoming | Yes
GC | Grid Code Potential Change 7 | RfG and HVDC Compliance and System Management | Compliance and System Management | National Grid | No | No | Yes | No | Yes | E | 2017-06-21 | E | TBD | E | 2018-01-01 | Upcoming | On Track | This mod is set to be raised in Q2 2017 Deadline for EIF is fixed. This mod is set to be implemented in Q1 2018. | EU Regulation/Law | TBD | Mod |  | National Grid | Upcoming | Yes
GC | Grid Code Potential Change 8 | DCC Technical & Demand Side Response | DCC Technical & Demand Side Response Requirements | National Grid | No | No | Yes | No | Yes | E | 2017-06-21 | E | TBD | E | 2018-09-01 | Upcoming | On Track | This mod is set to be raised in Q2 2017 Deadline for EIF is fixed. This mod is set to be implemented in Q3 2018. | EU Regulation/Law | TBD | Mod |  | National Grid | Upcoming | Yes
GC | Grid Code Potential Change 9 | Interconnector Data Provision | Interconnector Data Provision to NGET after GB Gate Closure | National Grid | No | No | Yes | No | Yes | E | 2017-06-21 | E | TBD | E | 2019-01-01 | Upcoming | On Track | This mod is set to be raised in Q2 2017 Deadline for EIF is provisionally Q1 2019 | EU Regulation/Law | TBD | Mod |  | National Grid | Upcoming | Yes
GC | Grid Code Potential Change 10 | Frequency Restoration Reserves | Manual Frequency Restoration Reserves | National Grid | No | No | Yes | No | Yes | E | 2020-01-01 | E | TBD | E | 2021-10-01 | Upcoming | On Track | This mod is set to be raised in Q1 2020 Deadline for EIF is provisionally Q3 2021 | EU Regulation/Law | TBD | Mod |  | National Grid | Upcoming | Yes
GC | Grid Code Potential Change 11 | European TSOG Implementation -Regional Outage Coordination | European TSOG Implementation -Regional Outage Coordination | National Grid | No | No | Yes | No | Yes | E | 2018-01-01 | E | TBD | E | 2018-10-01 | Upcoming | On Track | This mod is set to be raised in Q1 2018 Deadline for EIF is provisionally Q4 2018 | EU Regulation/Law | TBD | Mod |  | National Grid | Upcoming | Yes
GC | Grid Code Potential Change 12 | European TSOG - Requirements | TSOG requirements in relation to reserve providers and operational agreements | National Grid | No | No | Yes | No | Yes | E | 2018-01-01 | E | TBD | E | 2018-10-01 | Upcoming | On Track | This mod is set to be raised in Q1 2018 Deadline for EIF is provisionally Q4 2018 | EU Regulation/Law | TBD | Mod |  | National Grid | Upcoming | Yes
GC | Grid Code Potential Change 13 | Market Suspension | Market Suspension | National Grid | No | No | Yes | No | Yes | E | 2017-07-01 | E | TBD | E | 2018-10-01 | Upcoming | On Track | This mod is set to be raised in Q3 2017 Deadline for EIF is provisionally Q3 2018 | EU Regulation/Law | TBD | Mod |  | National Grid | Upcoming | Yes
SEC | SECMP0002 | Add New Command to Reset Debt Registers | This proposal recommends a new single DCC command to allow Supplier Users to directly reset the Debt Registers on a smart meter. A new remote command would be added to SMETS2 and a new Use Case to GBCS to allow a user to reset the Debt Registers on a meter that is operating in Prepayment mode. | RWE npower | Yes | No | No | No | Yes | C | 2016-02-19 | E | TBD | E | 2018-11-01 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | - | No | Path 2 - Authority Determined | SECMP0002 | SECAS (Gemserv) | Live | No
SEC | SECMP0004 | Inclusion of Device Serial Number data item in the Smart Metering Inventory | This proposal recommends the addition of Device Serial Number to the Smart Metering Inventory to enable mapping between data held in the DCC systems, and industry data flows. The DUIS will be updated to include DSN as a data item in the SMI, and to expose this data item to DCC Users via the relevant Service Requests and the Self-Service Interface. | EDF Energy | Yes | No | No | No | Yes | C | 2016-02-19 | E | TBD | E | 2018-06-28 | Modification Report consultation | On Track | SECMP0004 has been issued for Modification Report Consutlation until 5th April 2017. The Change Board will vote on SECMP0004 on 19th April 2017. | - | No | Path 2 - Authority Determined | SECMP0003 | SECAS (Gemserv) | Live | No
SEC | SECMP0005 | Include Tariff and Register Labels in SMETS2 Devices | The proposal seeks to include Tariff Label and Register Labels in smart metering devices and to allow them to be published on the Home Area Network (HAN) for display to the customer via HAN devices (e.g. an IHD). | E.ON | Yes | No | No | No | Yes | C | 2016-03-01 | E | TBD | E | 2018-11-01 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | - | No | Path 2 - Authority Determined | SECMP0005 | SECAS (Gemserv) | Live | No
SEC | SECMP0006 | Specifying the number of digits for device display | Include a specification for the number of digits for devices’ display of meter registers in SMETS2 in relation to the provision of energy measurement information. | SSE | Yes | No | No | No | Yes | C | 2016-03-01 | E | TBD | E | 2018-11-01 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | - | BSC - potential consequntial change | Path 2 - Authority Determined | SECMP0006 | SECAS (Gemserv) | Live | No
SEC | SECMP0007 | Firmware updates to mandated HAN devices | This Modification Proposal proposes including the capability to update firmware Over-The-Air (OTA) for mandated HAN devices (IHD / PPMID / HCALCS) via the DCC’s infrastructure. | RWE npower | Yes | No | No | No | Yes | C | 2016-03-01 | E | TBD | E | 2018-11-01 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | - | No | Path 2 - Authority Determined | SECMP0007 | SECAS (Gemserv) | Live | No
SEC | SECMP0008 | Provision of a Service Request error response for quarantined Service Requests | Provide a new DUIS Service Request error response to give DCC Service Users visibility of quarantined Service Requests following a breach of the DCC’s Anomaly Detection Threshold and / or the individual DCC Service User’s Anomaly Detection Threshold. | Scottish Power | Yes | No | No | No | Yes | C | 2016-03-01 | E | TBD | E | 2018-06-28 | Modification Report consultation | On Track | SECMP0008 has been issued for Modification Report Consutlation until 5th April 2017. The Change Board will vote on SECMP0008 on 19th April 2017. | - | No | Path 2 - Authority Determined | SECMP0008 | SECAS (Gemserv) | Live | No
SEC | SECMP0009 | Centralised Firmware Library | Establishment of a repository of firmware images, with access provided to all Parties responsible for the management of SMETS1 and/or SMETS2 meters. | RWE npower | Yes | No | No | No | Yes | C | 2016-03-01 | E | TBD | E | 2018-11-01 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | - | No | Path 2 - Authority Determined | SECMP0009 | SECAS (Gemserv) | Live | No
SEC | SECMP0010 | Introduction of triage arrangements for Communication Hubs | SEC Supplier parties should be permitted to carry out basic ‘triage’ checks on Communications Hubs following their removal from a consumer’s property. | British Gas | Yes | No | No | No | Yes | C | 2016-03-02 | E | TBD | E | 2018-11-01 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | - | No | Path 2 - Authority Determined | SECMP0010 | SECAS (Gemserv) | Live | No
SEC | SECMP0011 | Inclusion of Meter Asset Provider Participant Code (MAP ID) Participant Codes in the Smart Metering Inventory | Proposes to add Meter Asset Provider Identifier (MAP ID) in the Smart Metering Inventory to enable the efficient management of electricity and gas meters. | Utility Funding Limited | Yes | No | No | No | Yes | C | 2016-03-22 | E | TBD | E | 2018-06-28 | Modification Report consultation | On Track | SECMP0011 has been issued for Modification Report Consutlation until 5th April 2017. The Change Board will vote on SECMP0011 on 19th April 2017. | - | No | Path 2 - Authority Determined | SECMP0011 | SECAS (Gemserv) | Live | No
SEC | SECMP0012 | Channel selection to support Shared HAN solutions | Seeks to enable channel selection at the mandated 2.4GHz frequency to facilitate the efficient provision, installation, operations and interoperability of Smart Metering Systems in premises where standard HAN solutions are unsuitable and Shared HAN solutions necessary. | Siemens Plc | Yes | No | No | No | Yes | C | 2016-05-05 | E | TBD | E | 2018-11-01 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | - | No | Path 2 - Authority Determined | SECMP0012 | SECAS (Gemserv) | Live | No
SEC | SECMP0013 | Smart meter device diagnostics and triage | The proposal seeks to amend the SEC and DCC’s systems to provide Suppliers with a means of performing quality assurance and fault diagnostics on SMETS2 devices returned by meter operatives | E.ON | Yes | No | No | No | Yes | C | 2016-05-04 | E | TBD | E | 2018-11-01 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | - | No | Path 2 - Authority Determined | SECMP0013 | SECAS (Gemserv) | Live | No
SEC | SECMP0015 | GPF timestamp for reading instantaneous Gas values | The Gas Instantaneous Prepay Values are retrieved from the Gas Proxy Function and as such, these may not be in-line with the Gas Meter. Without a timestamp to indicate the timeliness of these values, it prevents the supplier from knowing how up to date the information is. | E.ON | Yes | No | No | No | Yes | C | 2016-05-31 | E | TBD | E | 2018-11-01 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | - | No | Path 2 - Authority Determined | SECMP0015 | SECAS (Gemserv) | Live | No
SEC | SECMP0016 | Consideration of "Maximum Credit" value in credit cover calculation | This Modification Proposal seeks to make changes to the SEC Credit Cover Requirement calculation so that it takes into account the credit value specified by an independent credit assessor. | First Utility Limited | Yes | No | No | No | Yes | C | 2016-06-03 | C | 2017-01-28 | C | 2018-04-01 | Implemneted | On Track | SECMP0016 was implemented on 1sdt April 2017. | - | No | Path 2 - Authority Determined | SECMP0016 | SECAS (Gemserv) | Live | No
SEC | SECMP0018 | Standard Electricity Distributor Configuration Settings | Amendments to the Great Britain Companion Specification (GBCS) to specify the standard Electricity Distributor configuration settings to be applied to an electricity smart meter by the Manufacturer. Application of default configuration settings will reduce the need for Electricity Distributor to apply settings immediately after commissioning. | Northern Powergrid | Yes | No | No | No | Yes | C | 2016-06-23 | E | TBD | E | 2018-11-01 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | - | No | Path 2 - Authority Determined | SECMP0018 | SECAS (Gemserv) | Live | No
SEC | SECMP0019 | ALCS Description Labels | This Proposal recommends that there should be some form of guidance / rules (Naming Conventions) / standardisation when defining any of the 5 Auxiliary Load Control Switches (ALCS) or HAN Connected Auxiliary Load Control Switch (HCALCS). | SSE | Yes | No | No | No | Yes | C | 2016-07-14 | E | TBD | E | 2018-11-01 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | - | No | Path 2 - Authority Determined | SECMP0019 | SECAS (Gemserv) | Live | No
SEC | SECMP0021 | Increase Other SEC Party representation for TABASC and SSC | The Proposer would like to increase the “Other SEC Party” representation on the SSC to three and on the TABASC to four. | Landis & Gyr | Yes | No | No | No | Yes | C | 2016-10-04 | E | TBD | E | 2017-05-11 | Modification Report Consutlation | On Track | SECMP0021 has been issued for Modification Report Consutlation until 5th April 2017. The Change Board will vote on SECMP0021 on 19th April 2017. | - | No | Path 3 - Self Governance | SECMP0021 | SECAS (Gemserv) | Live | No
SEC | SECMP0023 | Correct Units of Measure for Uncontrolled Gas Flow Rate | Currently GBCS limits the values of the Uncontrolled Gas Flow rate to be in whole numbers of m3. This modification proposes to change that to allow m3 with accuracy to 3 decimal places to be specified. | RWE npower | Yes | No | No | No | Yes | C | 2016-10-26 | E | TBD | E | 2018-11-01 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | - | No | Path 2 - Authority Determined | SECMP0023 | SECAS (Gemserv) | Live | No
SEC | SECMP0024 | Enduring Approach to Communication Hub Firmware Management | The Proposer seeks to develop requirements for an enduring solution for a Supplier-controlled release of firmware to Communication Hubs (CHs). The Proposer’s solution is to develop and implement a CH Firmware Deployment and Activation ‘Safe Launch’ Plan, supported by new DUIS Service Requests. | E.ON | Yes | No | No | No | Yes | C | 2016-10-27 | E | TBD | E | 2018-11-01 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | - | No | Path 2 - Authority Determined | SECMP0024 | SECAS (Gemserv) | Live | No
SEC | SECMP0025 | Electricity Network Party Access to Load Switching Information | This proposal seeks to enable Electricity Network Parties to have access to information from the Smart Metering System relating to load switching carried out by Smart Meters or Smart Meter connected Devices. It also proposes that the Smart Metering System informs Electricity Network Parties when changes are made to existing load switching regimes. | Western Power Distribution | Yes | No | No | No | Yes | C | 2016-11-18 | E | TBD | E | 2018-06-01 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | - | No | Path 2 - Authority Determined | SECMP0025 | SECAS (Gemserv) | Live | No
SEC | SECMP0026 | Changes to the Security Sub-Committee Nomination Process | This modification seeks to alter the current Security Sub-Committee’s (SSC) member nomination process in three areas to: • require that nominators must hold a relevant senior position within their organisation; • grant the SSC authority to reject nominees if they lack relevant security expertise; and • require that nominees undergo security vetting. | E.ON | Yes | No | No | No | Yes | C | 2016-12-12 | E | TBD | C | 2017-03-16 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | - | No | Path 3 - Self Governance | SECMP0026 | SECAS (Gemserv) | Live | No
SEC | SECMP0027 | Amending Service Request Forecasting | The Proposer has highlighted that forecasting the number of individual Service Requests is going to be very challenging for DCC Users, especially for top ups. This modification seeks to amends the forecasting rules. | Utilita Energy | Yes | No | No | No | Yes | C | 2016-12-16 | E | TBD | E | TBD | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | - | No | Path 2 - Authority Determined | SECMP0027 | SECAS (Gemserv) | Live | No
SEC | SECMP0028 | Prioritising Service Requests | This Modification Proposal seeks to introduce Service Request prioritisation with the rationale that some Service Requests are fundamental to the customer experience of the market and should take priority over other, non-critical Service Requests. | Utilita Energy | Yes | No | No | No | Yes | C | 2016-12-07 | E | TBD | E | TBD | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | - | No | Path 2 - Authority Determined | SECMP0028 | SECAS (Gemserv) | Live | No
SEC | SECMP0029 | Business Continuity and Disaster Recovery Testing Amendments | This Modification Proposal seeks to amend the DCC obligations on the Business Continuity and Disaster Recovery (BCDR) to ensure that Service Requests (SRs) are processed as soon as possible to reduce customer impacts. | Utilita Energy | Yes | No | No | No | Yes | C | 2016-12-19 | E | TBD | E | TBD | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | - | No | Path 3 - Self Governance | SECMP0029 | SECAS (Gemserv) | Live
SEC | SECMP0030 | Demand Management of DCC Systems | This modification proposes establishing appropriate rules to enable the prioritisation of Service Requests and Service Responses across the DCC User Interface and the prioritisation by the DCC of Commands to be sent to Communications Hub Functions and Certificate Signing Request volumes in an equitable, fair and transparent way. Rules by which DCC will actively control Device Alert volumes will also be considered. | Smart DCC Ltd | Yes | No | No | No | Yes | C | 2017-01-04 | E | TBD | E | TBD | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | - | No | Path 2 - Authority Determined | SECMP0030 | SECAS (Gemserv) | Live | No
SEC | SECMP0031 | Adding UTRN Functionality to SMETS | SMETS1 Unique Transaction Reference Numbers (UTRNs) can be used for a number of functions beyond adding credit, which currently is the only use for UTRNs on a SMETS2 meter. This Modification Proposal seeks to increase the UTRN functionality associated to a UTRN for SMETS2 devices. | Utilita Energy | Yes | No | No | No | Yes | C | 2017-02-20 | E | TBD | E | TBD | Initial Modification Report | On Track | This Modification was presented to the March 2017 Panel. The Panel referred the Modification Proposal to BEIS to seek a view on whether transitional powers set out in Section X2.3(d) should be applied. Subject to the response from BEIS, the Panel will take the appropriate action. | - | No | Path 2 - Authority Determined | SECMP0031 | SECAS (Gemserv) | Live | No
SEC | SECMP0032 | Prioritising Prepayment Customers in No WAN Situations | This Mod seeks to introduce a requirement on the DCC to prioritise achieving SM WAN coverage in areas where customers signed up to prepayment contracts with their suppliers, where a Communications Hub is installed at a premises but does not connect to SM WAN, and the SM WAN Coverage Database indicated (at any time during the 30 days prior to the date of installation) that the SM WAN is (or would be) available in the area in which the premises is located on the installation date. | Utilita Energy | Yes | No | No | No | Yes | C | 2017-02-20 | E | TBD | E | TBD | Initial Modification Report | On Track | This Modification was presented to the March 2017 Panel. The Panel referred the Modification Proposal to BEIS to seek a view on whether transitional powers set out in Section X2.3(d) should be applied. Subject to the response from BEIS, the Panel will take the appropriate action. | - | No | Path 2 - Authority Determined | SECMP0032 | SECAS (Gemserv) | Live | No
SEC | SECMP0033 | Update to CH Handover Support Materials | This Modification Proposal seeks to update the Consignment labelling and information table as well as the Smart Meter Wide Area Network (SM WAN) Coverage Information section in Appendix H 'CH Handover Support Materials'. This update is to align the 'CH Handover Support Materials' document with the implementation of the DCC Solution. | Smart DCC Ltd | Yes | No | No | No | Yes | C | 2017-02-22 | E | TBD | E | 2017-05-11 | Modification Report Consutlation | On Track | SECMP0033 has been issued for Modification Report Consutlation until 5th April 2017. The Change Board will vote on SECMP0033 on 19th April 2017. | - | No | Path 3 - Self Governance | SECMP0033 | SECAS (Gemserv) | Live | No
SPAA | CP 14/268 | Introduction of The Gas Theft Incentive Scheme | The intent of this change is to introduce into the SPAA a Gas Theft Incentive Scheme, in line with the principles set out by Ofgem within their decision document entitled ‘Tackling gas theft: the way forward’ published on 26th March 2012. | British Gas | No | No | No | No | No | C | 2014-03-01 | C | n/a | E | TBD | Implemented | On Track | Confirmation of go-live date required Mod will be implemented 5 WDs after Authority Decision, with the Scheme Year to start on the first day of the calendar month two months after Authority Decision. | Gas Theft | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 15/305 | Additional MDD Rejection Codes for UKLP | Proposal to add additional rejection codes to accommodate requirements identified by Shippers through the Nexus requirements process and consequential changes to UK Link Systems | WWU | No | No | No | No | No | C | 2015-05-01 | C | 2016-07-21 | E | TBD | Awaiting implementation | On Track | Confirmation of go-live date required Project Nexus Implementation Date | Nexus | No | Mod | SPAA | ElectraLink | Live | Yes
SPAA | CP 15/306 | Inclusion of new definition – Project Nexus Implementation Date | Inclusion of definition so change proposal delivery can be linked and aligned to the delivery of Project Nexus | E.ON | No | No | No | No | No | C | 2016-06-01 | C | 2016-07-21 | E | TBD | Awaiting implementation | On Track | Confirmation of go-live date required Project Nexus Implementation Date | Nexus | No | Mod | SPAA | ElectraLink | Live | Yes
SPAA | CP 15/307 | Amendment to the Implementation date of CP14/284 | Amendments of the implementation date for CP14/284 due to its dependency on the delivery of Project Nexus | E.ON | No | No | No | No | No | C | 2015-06-01 | C | 2016-07-21 | E | TBD | Awaiting implementation | On Track | Confirmation of go-live date required Project Nexus Implementation Date | Nexus | No | Mod | SPAA | ElectraLink | Live | Yes
SPAA | CP 15/308 | Removal of Schedule 7 (Cooperative Objections) as a result of Nexus | This change seeks to make Schedule 7 removed from SPAA Documents. As a result of Nexus, LSPs will now be able to use Cancellation Confirmation option instead of Cooperative Objections. The use of this process will prevent ETs being raised | EDF | No | No | No | No | No | C | 2016-03-01 | C | 2016-04-01 | E | TBD | Awaiting implementation | On Track | Confirmation of go-live date required Project Nexus Implementation Date | Nexus | No | Mod | SPAA | ElectraLink | Live | Yes
SPAA | CP 15/317 | Amendment to Schedule 23 to reflect Changes at Project Nexus Implementation | At Project Nexus Implementation the Data Enquiry Service will change as a result of: • additional services being provided and consequently different data being available, • Single Service Provision will enhance data access to provide users of the Data Enquiry Service with greater visibility of Small Transporter Supply Meter Point data. This change documents the changes to Schedule 23 as a result | NGN | No | No | No | No | No | C | 2015-11-01 | C | 2015-12-01 | E | TBD | Awaiting implementation | On Track | Confirmation of go-live date required Project Nexus Implementation Date | Nexus | No | Mod | SPAA | ElectraLink | Live | Yes
SPAA | CP 16/327 | Revision and Implementation of the Gas Theft Detection Incentive Scheme | Support the introduction of a Gas Theft Detection Incentive Scheme by seeking to implement further amendments to the legal drafting for previously Authority approved CP14/268 | British Gas | No | No | No | No | No | C | 2016-06-01 | C | 2016-07-21 | C | 2017-06-05 | Awaiting implementation | On Track | - | Gas Theft | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 16/329 | Introduction of Schedule 38 and a new defined term in Schedule 29 | This change has been developed by the Schedule 25 Review Group and seeks to introduce a new Schedule in order to place obligations on Suppliers to undertake prepayment assurances measure on non-smart prepayment meters as well as introducing a new defined term in Schedule 29 | Npower | No | No | No | No | No | C | 2016-05-01 | C | 2017-02-01 | C | 2017-02-24 | Implemented | On Track | - | n/a | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 16/334 | Introduction of Smart Prepayment Change of Supplier Exceptions Process | This change has been developed by the Smart Prepayment Issues Group (SPIG) to introduce a new Schedule, which sets out a number of Supplier obligations in relation to the smart prepayment Change of Supplier exceptions process. | E.ON | Yes | No | No | No | No | C | 2016-05-01 | C | 2016-10-20 | E | TBD | Implemented | On Track | Confirmation of authority approval 1 WD after Authority Consent received | n/a | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 16/336 | Amendments to the SPAA change process v1.1 | This change proposes that the SPAA Change Board is responsible for agreeing the next steps for a Change Proposal or Draft Change Proposal | Wales and West Utilities | No | No | No | No | No | C | 2016-06-01 | C | 2016-10-20 | C | 2017-02-24 | Implemented | On Track | - | n/a | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 16/338 | Process and Costs of Providing Additional Hunter Facilities | This change seeks to introduce a process for Suppliers who wish to procure additional Hunter facilities from the TRAS Service Provider and to make those costs transparent to the Supplier community. This change also seeks to introduce specific measures for additional Hunter costs for these Services to be charged to the individual Supplier. | Npower | No | No | No | No | No | C | 2016-05-01 | C | 2016-09-15 | C | 2017-02-24 | Implemented | On Track | - | TRAS | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 16/339 | TRAS Amendment of Schedule 34 Appendix 2 | Currently the Programming Manual contained within Schedule 34 Appendix is an outdated version. This CP seeks to update the information with a data items table and reference utilising the most current version of the Service Providers Programming Manuals. | E.ON | No | No | No | No | Yes | C | 2016-05-01 | C | 2016-09-15 | E | TBD | Issued | On Track | Confirmation of authority approval 5WDs after decision to align with DCUSA | TRAS | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 16/343 | Housekeeping amendment to redundant Schedules | Seeks to amend the covering page of Schedule 7 to state that the schedule is no longer in use. | EDF | No | No | No | No | Yes | C | 2016-06-01 | C | 2016-07-21 | C | TBD | Awaiting implementation | On Track | Confirmation of go-live date required Project Nexus Implementation Date | Nexus | No | Mod | SPAA | ElectraLink | Live | Yes
SPAA | CP 16/344 | Requirement on Gas Transporters to Provide Data to the ETTOS Service Provider | To deliver the ETTOS service, the ETTOS Service Provider requires data from Gas Transporters. This CP places a requirement on Gas Transporters to provide the required data. | E.ON | No | No | No | No | No | C | 2016-06-01 | C | 2016-07-21 | E | TBD | Awaiting implementation | On Track | Confirmation of authority approval 5 Working Days following Authority approval (aligned with the DCUSA change) | TRAS | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 16/346 | Inclusion of User Allocation Rules for ETTOS Secure Email System (Draft) | ETTOS tip-offs are disseminated to Parties by means of a secure email service. This CP seeks defines rules for allocation of user accounts for the secure email service. | Npower | No | No | No | No | No | C | 2016-07-01 | C | 2016-12-15 | E | 2017-02-24 | Implemented | On Track | - | TRAS | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 16/346 | Inclusion of User Allocation Rules for ETTOS Secure Email System | This seeks to define rules for allocation of user accounts for the secure email service define rules for allocation of user accounts for the secure email service | Npower | No | No | No | No | No | C | 2016-11-01 | C | 2016-12-15 | C | 2017-02-24 | Implemented | On Track | - | TRAS | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 16/347 | Amendments to Pre-Payment tariff pages (Draft) | This change proposal seeks to bring in amendments to the use of tariff pages, following CMA remedies required. | Npower | No | No | No | No | No | C | 2016-07-01 | C | n/a | E | TBD | Awaiting implementation | On Track | Confirmation of authority approval 5WD after Authority Consent received | - | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 16/349 | Introduction of OAMI into SPAA EC Vires | The Ofgem Approved Meter Installers (OAMI) Scheme is currently managed and overseen by Ofgem. At the April 2017 EC meeting, it was agreed that the Scheme should be incorporated into SPAA governance, with the OAMI Scheme transitioning by April 2017, in line with the expiration of the current Scheme Co-ordinators contract. CP 16/349 will enable the SPAA EC to effectively and efficiently manage the Ofgem Approved Meter Installer Scheme when it is transitioned into SPAA governance, as directed by Ofgem | TBD | No | No | No | No | No | C | 2017-01-01 | C | TBD | E | TBD | Issued in Change Pack | On Track | Modication due to be implemented 5 Working Days after Authority Decision | - | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 16/350 | Clarification of TRAS Accession Process | Now that TRAS is in live operation, there are a number of elements that have been identified in the TRAS Schedules, specifically within clause 8 and the definitions section of the SPAA Main Body that should be clarified, amended or included for the efficient operation of TRAS. | British Gas | No | No | No | No | No | C | 2016-11-01 | C | 2016-12-15 | C | 2017-02-24 | Implemented | On Track |  | TRAS | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 16/352 | Changes to SLC 30 of SPAA | On 14 June 2016, Ofgem published its decision to modify the Gas Supply Licence (SLC 30. Supply Point Administration Agreement) in order to implement CGR3 Final Proposals. In summary the licence condition changes reflect changes to the Significant Code Review process | Scottish Power | No | No | No | No | No | C | 2016-08-01 | C | 2016-10-20 | C | 2017-02-24 | Implemented | On Track | - | - | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 16/354 | Mandate that all Suppliers shall use the DTN for the exchange of RET Flows | This CP has been raised with the intent to make the use of the Data Transfer Network (DTN) mandatory for the exchange for respectively the RET Flow | Scottish Power | No | No | No | No | No | C | 2016-09-01 | C | 2016-10-20 | C | 2017-06-05 | Awaiting implementation | On Track | - | - | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 16/355 | Mandate that all Suppliers shall use the DTN for the exchange of SAR Flows | This CP has been raised with the intent to make the use of the Data Transfer Network (DTN) mandatory for the exchange for respectively the SAR Flow | Scottish Power | No | No | No | No | No | C | 2016-09-01 | C | 2016-10-20 | C | 2017-06-05 | Awaiting implementation | On Track | - | - | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 16/360 | Schedule 33, Appendix 1 SLC References | The intent of this change is to add Supply Licence Reference (SLCs) 12.A to Schedule 33, Appendix 1 of the SPAA. | British Gas | No | No | No | No | Yes | C | 2016-11-01 | C | 2016-12-15 | C | 2017-02-24 | Deferred | On Track | - | - | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 16/363 | Adding Meter Serial Number (MSN) to the Supplier Agreed Read (SAR) flow. | To add MSN to SAR | Utilita | No | No | No | No | No | C | 2016-11-01 | C | 2016-12-15 | C | 2017-06-05 | Awaiting implementation | On Track | - | - | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 16/364 | Amendment to Actual Reading Definition | The definition of Actual Reading in SPAA Schedule 27 – Technical Glossary contains capitalised defining for an Automated Meter Reading which is not defined anywhere within the SPAA. This proposal seeks to update this definition to remove incorrect defining. |  | No | No | No | No | Yes | C | 2016-11-01 | C | 2016-12-15 | C | 2017-02-24 | Implemented | On Track | - | - | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 17/371 | To reference ‘MAP 24’ within Schedule 38 | This CP seeks to amend a reference within Schedule 38. | Gas Plus Supply Limited | No | No | No | No | No | C | 2017-01-01 | C | 2017-02-01 | C | 2017-06-30 | Issued in Change Pack | On Track | - | - | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 17/372 | Implementation of the Approved Meter Installer Governance | To implement the Approved Meter Installer governance arrangements as a new SPAA Schedule, as directed by Ofgem. | ESPipelines | No | No | No | No | No | C | 2017-01-01 | C | 2017-02-01 | C | 2017-04-01 | Issued in Change Pack | On Track | - | - | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 17/373 | Reordering Schedule 32 | To reorder SPAA Schedule 32 such that it follows in a logical order, as directed by the SPAA EC. | E.ON | No | No | No | No | No | C | 2017-01-01 | C | 2017-02-01 | C | 2017-06-30 | Issued in Change Pack | On Track | - | - | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 17/374 | Introducing a funding mechanism into Schedule 32 | To introduce a funding mechanism into SPAA Schedule 32. | Npower | No | No | No | No | No | C | 2017-01-01 | C | 2017-02-01 | C | 2017-09-01 | Issued in Change Pack | On Track | - | - | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 17/375 | Removal of reference to commercial disputes from Schedule 32 | To remove references to commercial disputes from SPAA Schedule 32. | British Gas | No | No | No | No | No | C | 2017-01-01 | C | 2017-02-01 | C | 2017-06-30 | Issued in Change Pack | On Track | - | - | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 17/376 | Xoserve funding and Governance Impacts | CP 17/376 seeks to set out the consequential changes which are required to the SPAA in light of the forthcoming implementation of UNC modification 0565 | WWU | No | No | No | No | No | C | 2017-01-01 | C | 2017-02-01 | C | 2017-04-01 | Withdrawn | On Track | - | - | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 17/377 | Amendments to Prepayment Tariff Pages | To update SPAA Schedule 25 in line with the CMA remedies regarding prepayment Tariff Pages, which will also include two new definitions within the Technical Glossary (Schedule 29). This Change Supersedes CP 16/347 to take into account the additional CMA revisions made. | Npower | No | No | No | No | No | C | 2017-01-01 | C | 2017-02-01 | C | 2017-04-01 | Issued in Change Pack | On Track | - | - | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 17/378 | Amendments to Prepayment Tariff Pages | To update SPAA Schedule 25 in line with the CMA remedies regarding prepayment Tariff Pages, which will also include two new definitions within the Technical Glossary (Schedule 29). This Change Supersedes CP 16/347 to take into account the additional CMA revisions made. | Npower | No | No | No | No | No | C | 2017-01-01 | C | 2017-02-01 | E | TBD | Issued in Change Pack | On Track | Modication due to be implemented 5 Working Days after Authority Decision | - | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 17/379 | Introduction of an Unidentified Funds Process in Schedule 25 | This change seeks to introduce a process to allocate the monies associated with unidentified prepayment transactions within SPAA Schedule 25. | British Gas | No | No | No | No | No | C | 2017-02-16 | C | 2017-03-14 | E | 2017-06-30 | Issued in Change Pack | On Track | - | - | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 17/380 | Amendments to Schedule 32 in relation to the Provision of Services Regulations | This change seeks to updated the initial assessment process for Meter Asset Managers (MAMs) within Schedule 32 such that it is compliant with the Provision of Services Regulations 2009. | ESP | No | No | No | No | No | C | 2017-02-17 | C | 2017-03-14 | E | 2017-07-01 | Issued in Change Pack | On Track | - | - | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 17/381 | Introducing Failed Status in the Asset Status Code (A0037) for In Home Display. | This change seeks to introduce a new status of ‘Failed’ in the IHD Installed Status for Supplier to capture when it has not been possible to provide an IHD to the customer as part of the smart metering installation visit. | EDF | No | No | No | No | No | C | 2017-02-18 | C | 2017-03-14 | E | 2017-11-03 | Issued in Change Pack | On Track | - | - | MRA | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 17/382 | Amendments to Prepayment Tariff Pages – Updated following legal review | The purpose of this CP is to update the SPAA in line with the CMA remedies regarding prepayment Tariff Pages. The drafting associated to this change has been legally reviewed to ensure that it is sufficiently robust, and accurately transposes the CMA obligations into the SPAA. This change seeks to supersede CP 16/347, which has been previously sent back by the Authority; this change also seeks to supersede CP 17/378, which was raised in response to Ofgem’s send back of CP 16/347, and approved at the February 2017 Change Board. Whilst reviewing CP 17/378, industry parties acknowledged that it would be opportune for the drafting of CP 17/378 to be legally reviewed. This CP seeks to implement the updated drafting following legal review. | British Gas | No | No | No | No | No | C | 2017-03-03 | C | 2017-03-15 | E | TBD | Issued in Change Pack | On Track | Urgent The proposed implementation date is 5 working days after Authority approval | CMA | No | Mod | SPAA | ElectraLink | Live | No
SQSS | GSR012 | Treatment of Interconnectors | There are significant new interconnections to external systems currently under construction and more are planned. Interconnectors can result in large changes in flows within short timescales across the transmission system. It is therefore important to understand the implications and means of managing greater interconnection and market coupling with other European nations, including the extent to which interconnector flow can be relied upon to meet demand and avoid constraining generation. | National Grid | No | No | Yes | No | Yes | C | 2010-10-05 | E | TBD | E | TBD | Assessment | At Risk | Workgroup meetings need to re-convene following 1 year hiatus. | - | No | Mod | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/SQSS/Modifications/GSR012/ | National Grid | Live | Yes
SQSS | GSR014 | Offshore Transformer Requirements | GSR014 was raised to investigate whether the current requirements for two transformers and two substation bays where offshore cables connect to the onshore transmission system is necessary or whether two transformers connected to a single bay or even a single transformer and single bay would be sufficient. | National Grid | No | No | No | No | No | C | 2012-11-19 | E | TBD | E | TBD | Assessment | At Risk | Finalising report | - | No | Mod | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/SQSS/Modifications/GSR014/ | National Grid | Live | Yes
SQSS | GSR016 | Embedded Generation Scaling | GSR016 was raised to specify how embedded generation should be treated in Chapter 4 MITS studies. The GSR009 modification to the NETS SQSS in 2011 specified certain scaling factors for various types of generation (based on fuel type) with different scaling factors under the economy and security criteria. These scaling factors are only considered for “large” power stations (i.e. generation over 100MW in England and Wales). | National Grid | No | No | No | No | Yes | C | 2013-07-22 | E | TBD | E | TBD | Assessment | On Track | - | - | CUSC | Mod | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/SQSS/Modifications/GSR016/ | National Grid | Live | Yes
SQSS | GSR017 | Treatment of Switch Faults in Operational Timescales | Under the current version of the NETS SQSS, switch faults are secured for new generation connections but only with respect to limiting the loss of power infeed to the infrequent infeed loss risk. Switch faults can potentially cause wider system issues such as instability, system splits, cascade tripping and voltage collapse depending on the substation at which they occur, the network running arrangement and the generation and demand levels at the time of the fault. GSR017 will therefore undertake a review of the current NETS SQSS and will determine the need case for securing against the above challenges in the event of switch faults in operational timescales. | National Grid | No | No | No | No | No | C | 2014-02-05 | E | TBD | E | TBD | Raised | On Track | - | - | No | Mod | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/SQSS/Modifications/GSR017/ | National Grid | Live | Yes
SQSS | GSR018 | Treatment of Sub-Synchronous Oscillations in the NETS SQSS | A number of Transmission Licensees and Transmission Users are in the process of enhancing their networks or connecting generation using Series Capacitor and / or HVDC technology. Both of these types of equipment can cause sub-synchronous oscillations (SSO) to occur by interacting with other User’s equipment in the form of sub-synchronous resonance (SSR) or sub-synchronous torsional interaction (SSTI). The Grid Code Review Panel Paper: “Suppression of Sub-Synchronous Resonance from Series Compensators” (pp13/54) proposed changes to the Grid Code to place obligations on Transmission Licensees to mitigate SSR where Series Compensation is deployed. The Grid Code Review Panel asked that these proposals be given further consideration in light of concerns raised by Transmission Licensees about how and where any SSR related obligations are expressed within the transmission frameworks. The Grid Code Review Panel also asked whether there was a need to capture SSR and SSTI within the NETS SQSS. | National Grid | No | No | No | No | Yes | C | 2014-12-04 | E | TBD | E | TBD | Raised | On Track | - | GC0077 | GC |  | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/SQSS/Modifications/GSR018/ | National Grid | Live | Yes
SQSS | GSR022 | Review of Security and Economy Planned Transfer Conditions | The workgroup considers issues and interactions that arise when applying NETS SQSS Section 4 criteria due to the availability of generation and due to generation technology. | National Grid | No | No | No | No | Yes | C | 2016-06-01 | E | TBD | E | TBD | Raised | On Track | - | - |  |  | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/SQSS/Modifications/GSR022/ | National Grid | Live | Yes
SQSS | SQSS Potential Change 1 | European TSOG -Minimum Required Inertia | Determination of Minimum Required Inertia | National Grid | No | No | No | No | No | E | 2017-10-01 | E | TBD | E | 2018-10-01 | Upcoming | On Track | - | - | TBD | Mod |  | National Grid | Upcoming | Yes
SQSS | SQSS Potential Change 2 | European TSOG Implementation -Regional Outage Coordination | European TSOG Implementation -Regional Outage Coordination | National Grid | No | No | No | No | No | E | 2018-01-01 | E | TBD | E | 2018-10-01 | Upcoming | On Track | - | - | TBD | Mod |  | National Grid | Upcoming | Yes
SQSS | SQSS Potential Change 3 | European TSOG - Requirements | TSOG requirements in relation to reserve providers and operational agreements | National Grid | No | No | No | No | No | E | 2018-01-01 | E | TBD | E | 2018-10-01 | Upcoming | On Track | - | - | TBD | Mod |  | National Grid | Upcoming | Yes
STC | CM059 | Changes to Section C and H following OFGEM Response to Adjudication Request | Correct the Section C Paragraph 5.9.5 for refer to Section H and to update Section H to allow a referable clause to the Authority. | National Grid | No | No | No | No | No | C | 2016-09-21 | E | TBD | E | TBD | Assessment | On Track | - | - | No | Mod | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/STC/Modifications/CM059/ | National Grid | Live | Yes
STC | STC Potential Change 1 | European TSOG - Multi TSO Training Cooperation | European TSOG - Multi TSO Training Cooperation | National Grid | No | No | Yes | No | Yes | E | 2017-10-01 | E | TBD | C | 2018-10-01 | Upcoming | On Track | - | EU Regulation/Law | No | Mod |  | National Grid | Upcoming | Yes
STC | STC Potential Change 2 | European TSOG Implementation - Data Exchange | European TSOG Implementation - Data Exchange | National Grid | No | No | Yes | No | Yes | E | 2017-10-01 | E | TBD | C | 2018-10-01 | Upcoming | On Track | - | EU Regulation/Law | Yes | Mod |  | National Grid | Upcoming | Yes
STC | STC Potential Change 3 | European TSOG Implementation -Regional Outage Coordination | European TSOG Implementation -Regional Outage Coordination and Security Anaysis | National Grid | No | No | Yes | No | Yes | E | 2018-01-01 | E | TBD | C | 2018-12-01 | Upcoming | On Track | This mod is set to be raised in Q1 2018 | EU Regulation/Law | Yes | Mod |  | National Grid | Upcoming | Yes
STC | STC Potential Change 4 | SO/TO Funding Mechanism | Changes to Section C & D to incorporate changes from BSIS incentive scheme for Scottish TOs | SPT | No | No | No | n | Yes | E | n/a | N/A | TBD | E | N/A | Upcoming | On Track | Still under review to confirm if any changes needed | Update to STC to reflect changes identified by NAP workgroup | No | Mod |  | National Grid | Upcoming | Yes
STC | STC Potential Change 5 | Changes to incorporate changes from ECIT | Changes required to the STC to implement ECIT into multiple sections of the STC | TBC | No | No | No | N | Yes | E | n/a | N/A | TBD | E | TBD | Upcoming | On Track | Waiting information from Ofgem on scope of change and change mechanism to be used | Regulatory change | Yes | Mod |  | National Grid | Upcoming | Yes
STC | STC Potential Change 6 | Changes to Section K as a result of Grid Code Modification GC075 | Review whether changes are required to Section K of the STC as a result of Grid Code Modification GC0075 | TBC | No | No | No | N | Yes | E | n/a | N/A | TBD | E | TBD | Upcoming | On Track | Review being performed | Industry review | No | Mod |  | National Grid | Upcoming | No
STC | PM0094 | Housekeeping to STCP18-2 | Update to STCP18-2 to amend the concept of Application Steering Group | SHE Transmission | No | No | No | n | No | C | 2017-03-29 | 2017-04-26 | 2017-04-26 | C | 2017-04-26 | Awaiting implementation | On Track | Waiting updated form to sign off | Improve process to reflect current working practices | No | STCP change | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/STC/Modifications/PM094/ | National Grid | live | Yes
STC | PM0095 | Housekeeping to STCP18-3 | Update to STCP18-3 to amend the concept of Application Steering Group | SHE Transmission | No | No | No | n | No | C | 2017-03-29 | 2017-04-26 | 2017-04-26 | C | 2017-04-26 | Awaiting implementation | On Track | Waiting updated form to sign off | Improve process to reflect current working practices | No | STCP change | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/STC/Modifications/PM095/ | National Grid | live | Yes
STC | STCP Potential Change 1 | Housekeeping to STCP18-1 | Update to STCP18-1 to amend the concept of Application Steering Group | SHE Transmission | No | No | No | n | No | E | n/a | N/A | TBD | E | N/A | Upcoming | On Track | Still under review to confirm if any changes needed | Improve process to reflect current working practices | No | STCP change |  | National Grid | Upcoming | Yes
STC | STCP Potential Change 2 | Housekeeping to STCP18-4 | Update to STCP18-4 to amend the concept of Application Steering Group | SHE Transmission | No | No | No | n | No | E | n/a | N/A | TBD | E | N/A | Upcoming | On Track | Still under review to confirm if any changes needed | Improve process to reflect current working practices | No | STCP change |  | National Grid | Upcoming | Yes
STC | STCP Potential Change 3 | Housekeeping to STCP08-2 | Update to the Appendix of STCP08-2 to re-insert missing diagram page | National Grid | No | No | No | n | No | E | n/a | N/A | TBD | E | N/A | Upcoming | On Track | Still under review to confirm if any changes needed | Improve process to reflect current working practices | No | STCP change |  | National Grid | Upcoming | Yes
STC | STCP Potential Change 4 | SO/TO Funding Mechanism | Changes to STCP11-3 & STCP11-4 in relation to the STC change to Section C & D to incorporate changes from BSIS incentive scheme for Scottish TOs | SPT | No | No | No | n | No | E | n/a | N/A | TBD | E | N/A | Upcoming | On Track | Still under review to confirm if any changes needed | Update to STC to reflect changes identified by NAP workgroup | No | STCP change |  | National Grid | Upcoming | Yes
STC | STCP Potential Change 5 | Review of STCP09-1 | Review of STCP09-1 and proximity outage | TBC | No | No | No | n | No | E | n/a | N/A | TBD | E | TBD | Upcoming | On Track | Further Workgroup needed to refine any changes | Industry review | No | STCP change |  | National Grid | Upcoming | Yes
STC | STCP Potential Change 6 | Review of STCP19-3 | Review of STCP19-3 and reviewing checklist for embedded connections | TBC | No | No | No | n | No | E | n/a | N/A | TBD | E | TBD | Upcoming | On Track | Further Workgroup needed to refine any changes | Industry review | No | STCP change |  | National Grid | Upcoming | Yes
STC | STCP Potential Change 7 | Review of STCP22-1 | Review of STCP22-1 and reviewing single Scottish model for ETYS production | TBC | No | No | No | n | No | E | n/a | N/A | TBD | E | TBD | Upcoming | On Track | Further Workgroup needed to refine any changes | Industry review | No | STCP change |  | National Grid | Upcoming | Yes
UNC | 0565A | Central Data Service Provider: General framework and obligations | This Alternate Modification Proposal is identical to UNC 0565 except for the representation structure in the Data Services Contract structure | E.ON UK | No | No | No | No | Yes | C | 2016-10-10 | E | 2017-01-31 | E | 2017-04-01 | Awaiting Implementation | On Track | Goes live on 01 April 2017 | Licence - FGO | iGT UNC | Mod | http://www.gasgovernance.co.uk/0565 | Joint Office | LIVE | Yes
UNC | 0570 | Obligation on Shippers to provide at least one valid meter reading per meter point into settlement once per annum | This modification proposes to create a condition in the UNC to correspond with the requirement on Suppliers under the Supply Licence (SLC 21B.4) to take a meter reading at least once every year for billing purposes. In the case of the UNC this would be for use within gas industry settlement | Scottish Power | No | No | No | No | Yes | C | 2015-12-03 | E | 2017-08-30 | E | 2017-09-01 | Assessment | On Track | Workgroup assessment timetable has been extended | CMA Order | No | Mod | http://www.gasgovernance.co.uk/0570 | Joint Office | LIVE | Yes
UNC | 0571 | Application of Ratchets Charges to Class 1 Supply Points Only | Recognising the introduction of 4 new classes of Supply Points under Project Nexus and the wider availability of daily read sites with lower AQs, this modification limits the application of Ratchets Charges to Class 1 Supply Points whose operation may be material to the safe operation of the Network. | Gazprom | No | No | No | No | Yes | C | 2015-12-24 | E | 2017-05-30 | E | 2017-08-01 | Assessment | On Track | Returned to the Workgroup for consideration of an issue identified in the consultation | - | No | Mod | http://www.gasgovernance.co.uk/0571 | Joint Office | LIVE | Yes
UNC | 0571A | Application of Ratchet Charges to Class 1 Supply Points and Class 2 with an AQ above 73,200kWhs | Recognising the introduction of 4 new classes of Supply Points under Project Nexus and the wider availability of daily read sites with lower AQs, this modification limits the application of Ratchets Charges to Class 2 Supply Points with an AQ above 73,200 kWhs. | E.ON UK | No | No | No | No | Yes | C | 2016-05-05 | E | 2017-05-30 | E | 2017-08-01 | Assessment | On Track | Returned to the Workgroup for consideration of an issue identified in the consultation | - | No | Mod | http://www.gasgovernance.co.uk/0571 | Joint Office | LIVE | Yes
UNC | 0587 | Seasonal Energy Balancing Credit Cover | This modification proposes to amend the Energy Balancing Credit Rules so that a User’s credit cover, which is currently set based on the maximum requirement in the past 12 months, is only set based on months in the same season as the current one | Opus Energy | No | No | No | No | Yes | C | 2016-06-06 | C | 2016-11-24 | C | 2017-05-01 | Implemented | - | Minor changes required - and elective as required | - | No | Mod | http://www.gasgovernance.co.uk/0587 | Joint Office | Closed | No
UNC | 0593 | Provision of access to data for Price Comparison Websites and Third Party Intermediaries | This modification seeks to create provisions in the UNC to permit the release of data to Price Comparison Websites (PCWs) and Third Party Intermediaries (TPIs) to satisfy the CMA Energy Market Investigation requirements. The release of data would be subject to contractual agreement with Transporters that would include validations and be pursuant to data protection principles. It is believed that by providing data directly to such non-Code parties the service provided will improve, leading to more switching with consequential benefits to the competitive marketplace. | Northern Gas Networks | No | No | No | No | Yes | C | 2016-08-08 | E | 2017-08-30 | E | 2017-09-01 | Assessment | On Track | Returned to the Workgroup for consideration of issues raised in Ofgem's 'sendback' letter | CMA Order | No | Mod | http://www.gasgovernance.co.uk/0593 | Joint Office | LIVE | Yes
UNC | 0594R | Meter Reading Submission for Advanced & Smart Metering | The rollout of advanced and smart metering in the GB gas market provides an opportunity for more granular consumption data to be provided into central industry systems at marginal cost, which should drive more accurate cost allocation. Currently there are no requirements/obligations for Shippers to provide more frequent meter readings should a Smart/Advanced meter be installed. This Request is to consider options for the provision of data on a more frequent basis to support the Settlement process. It is believed that any proposals should apply to Class 1, 2 and 3 Supply Points; however this would be tested as part of the review. | Gazprom | Yes | No | No | No | No | C | 2016-09-02 |  | n/a |  | n/a | Request | On Track | This is a UNC Request - to review the arrangements for meter reading submission. A modification is one possible output. | None- Review | No | Request | http://www.gasgovernance.co.uk/0594 | Joint Office | LIVE | No
UNC | 0595S | Amendment to the Arrangements between National Grid NTS and GNI at the Moffat IP to Provide for Interruption of Virtual Reverse Flow | This enabling modification seeks to amend the tri-partite Agreement between National Grid, Gas Networks Ireland (GNI UK) – as the owner and operator of the Irish Interconnector - and GNI - as the Transmission System Operator in the Republic of Ireland - to reflect the existing arrangements for interruption (by GNI) of within-day Virtual Reverse Flow (VRF) capacity entitlements. | National Grid NTS | No | No | No | No | Yes | C | 2016-09-02 | C | 2016-11-17 | C | 2016-12-09 | Implemented | - | No action to implement since the service was already available in Ireland | - | No | Mod | http://www.gasgovernance.co.uk/0595 | Joint Office | Closed | No
UNC | 0596 | Implementing CGR3 decisions on Significant Code Reviews and self-governance | This modification seeks to implement Ofgem’s decisions in respect of self-governance and SCR process resulting from the Code Governance Review 3 consultation. | Wales & West Utilities | No | No | No | No | Yes | C | 2016-10-07 | E | 2017-01-31 | C | 2017-02-17 | Implemented | - |  | CGR3 | No | Mod | http://www.gasgovernance.co.uk/0596 | Joint Office | Closed | No
UNC | 0597S | Rules for the release of incremental capacity at Interconnection Points | This modification seeks to provide a process for acquiring incremental capacity at Interconnection Points that is compliant with the amended EU CAM Code. | National Grid NTS | No | No | Yes | No | Yes | C | 2016-10-10 | E | 2017-03-31 | C | 2017-04-06 | Awaiting Implementation | On Track | - | EU CAM | No | Mod | http://www.gasgovernance.co.uk/0597 | Joint Office | LIVE | Yes
UNC | 0598 | Amendments to Capacity Allocations Mechanisms to comply with EU Capacity Regulations | This modification seeks to facilitate compliance with the amended CAM Code at Interconnection Points (IP)s by introducing an amended auction calendar and changes to the treatment of capacity at Storage Exit points. | National Grid NTS | No | No | Yes | No | Yes | C | 2016-10-10 | E | 2017-03-31 | C | 2017-04-06 | Awaiting Implementation | On Track | - | EU CAM | No | Mod | http://www.gasgovernance.co.uk/0598 | Joint Office | LIVE | Yes
UNC | 0599 | Amendments to Capacity Allocations Mechanisms (Interruptible) to comply with EU Capacity Regulations | This modification seeks to facilitate compliance with the amended CAM Code by changing the rules for releasing interruptible capacity at Interconnection Points (IPs). | National Grid NTS | No | No | Yes | No | Yes | C | 2016-10-10 | C | n/a | C | n/a | Withdrawn | - | Withdrawn | EU CAM | No | Mod | http://www.gasgovernance.co.uk/0599 | Joint Office | Closed | No
UNC | 0600S | Amend obligation for the acceptance of EPDQD revisions made after D+5 | This modification seeks to amend the requirement in UNC that no revisions can be made to the Entry Point Daily Quantity Delivered (EPDQD) after D+5. The amended text will allow revisions to be made after this date, but any revisions submitted after D+5 will be subject to a reporting obligation. | National Grid NTS | No | No | No | No | Yes | C | 2016-10-10 | E | 2017-03-16 | C | 2017-04-07 | Awaiting Implementation | On Track | - | - | No | Mod | http://www.gasgovernance.co.uk/0600 | Joint Office | LIVE | Yes
UNC | 0601FT | Revision of National Grid Gas plc’s Individual Network Code to reflect the correct company name | This modification amends the Transporter name in the National Grid Gas plc Individual Network Code from ‘Transco plc’ to ‘National Grid Gas plc’. | National Grid NTS | No | No | No | No | No | C | 2016-11-01 | C | 2016-11-17 | C | 2016-12-09 | Implemented | - | - | - | No | Mod | http://www.gasgovernance.co.uk/0601 | Joint Office | Closed | No
UNC | 0602A | Implementation of Non Effective Days and Variant Non-Business Days for Project Nexus Implementation, maintaining two Supply Point Business Days (Project Nexus transitional modification) | This modification identifies arrangements relating to the requirement for ‘non-effective days’ and ‘variant non-Business Days’ to enable an orderly and efficient transition from current UNC arrangements to the UNC regime identified within UNC Modifications 0432, 0434 and 0440. | RWE npower | No | No | No | No | Yes | C | 2016-12-23 | E | 2017-03-31 | C | 2017-02-20 | Implemented | - |  | Nexus | iGT UNC | Mod | http://www.gasgovernance.co.uk/0602 | Joint Office | Closed | No
UNC | 0603S | Removal of liability for members of Performance Assurance Committee | This modification seeks to to give Performance Assurance Committee (PAC) members protection from legal action by Parties that are affected by their actions or decisions. This protection is limited to decisions made in good faith pursuant to members’ duties. Not having this protection may mean that members do not make difficult decisions and thereby limit the effectiveness of PAC in delivering performance assurance. | Wales & West Utilities | No | No | No | No | Yes | C | 2016-11-08 | C | 2016-12-15 | C | 2017-01-11 | Implemented | - | Minor change - no action required | - | No | Mod | http://www.gasgovernance.co.uk/0603 | Joint Office | Closed | No
UNC | 0604S | Central Data Services Provider – Arrangements following implementation of Project Nexus | This modification identifies the measures necessary to ensure the FGO arrangements implemented under Modification 0565/A/B are effective upon implementation of Project Nexus, by aligning the services introduced by Modifications 0432, 0434 and 0440 to the new CDSP direct and agency service structure. | National Grid Gas Distribution | No | No | No | No | Yes | C | 2016-11-30 | C | 2017-04-20 | C | 2017-06-01 | Consultation | On Track | - | Licence - FGO | No | Mod | www.gasgovernance.co.uk/0604 | Joint Office | LIVE | Yes
UNC | 0605S | Amendments to TPD Section K - Additional Methods to Procure and Dispose of Operating Margins Gas | This modification seeks to enable National Grid NTS to procure and dispose of Operating Margins Gas in a more efficient and economical way | National Grid NTS | No | No | No | No | Yes | C | 2016-12-02 | E | 2017-07-31 | E | 2017-09-01 | Assessment | On Track | Expected to be returned to Workgroup at April Panel for further assessment | - | No | Mod | http://www.gasgovernance.co.uk/0605 | Joint Office | LIVE | No
UNC | 0606S | National Grid Gas plc and National Grid Gas Distribution Limited transitional invoicing arrangement post Project Nexus implementation | This modification seeks to provide for a transitional arrangement for the invoicing of certain Transportation Charges by National Grid Gas plc and National Grid Gas Distribution Limited following implementation of Project Nexus. | National Grid Gas Distribution | No | No | No | No | Yes | C | 2016-12-05 | C | 2017-04-20 | C | 2017-06-01 | Consultation | On Track | - | - | No | Mod | http://www.gasgovernance.co.uk/0606 | Joint Office | LIVE | Yes
UNC | 0607S | Amendment to Gas Quality NTS Entry Specification at the St Fergus NSMP System Entry Point | This (enabling) modification seeks to facilitate a change to the current contractual Carbon Dioxide limit at the St Fergus NSMP System Entry Point, through modification of a Network Entry Provision contained within the Network Entry Agreement (NEA) between National Grid Gas plc. and North Sea Midstream Partners Limited (NSMP) in respect of the St Fergus NSMP Sub Terminal. | National Grid Gas Distribution | No | No | No | No | No | C | 2016-12-07 | E | 2017-08-30 | E | 2017-09-01 | Assessment | On Track | - | - | No | Mod | http://www.gasgovernance.co.uk/0607 | Joint Office | LIVE | No
UNC | 0608S | Implementation of ‘single service provision’ arrangements for iGT connected system exit points (Project Nexus transitional modification) | This ‘transitional’ modification identifies changes to the UNC to facilitate an orderly transition from the existing arrangements governing unmetered connected Independent Gas Transporter (iGT) systems (Connected Systems Exit Points - CSEPs) to the new ‘single service provision’ UNC framework to be implemented under UNC Modification 0440 ‘Project Nexus – iGT Single Service Provision’. | National Grid Gas Distribution | No | No | No | No | No | C | 2017-01-09 | C | 2017-04-20 | E | 2017-05-15 | Consultation | On Track | - | - | iGT UNC | Self Governance Modification | http://www.gasgovernance.co.uk/0608 | Joint Office | LIVE | Yes
UNC | 0609 | Transitional arrangements for gas settlement and replacement of Meter Readings (Project Nexus transitional modification) | This modification identifies arrangements relating to Supply Point classification, energy settlement & reconciliation and replacement of Meter Readings to enable an orderly and efficient transition from current UNC terms to the UNC regime identified within UNC Modification 0432, ‘Project Nexus – Gas Demand Estimation, Allocation, Settlement and Reconciliation reform’ and Modification 0434, ‘Project Nexus – Retrospective Adjustment’. | National Grid Gas Distribution | No | No | No | No | No | C | 2017-01-09 | E | 2017-05-20 | E | 2017-06-01 | Consultation | On Track | - | - | none | Modification | http://www.gasgovernance.co.uk/0609 | Joint Office | LIVE | Yes
UNC | 0610S | Project Nexus - Miscellaneous Requirements | This modification identifies a series of miscellaneous changes to the UNC which are required under Project Nexus arrangements to be implemented under UNC Modifications 0432, 0434 and 0440. | National Grid Gas Distribution | No | No | No | No | No | C | 2017-01-11 | C | 2017-04-20 | E | 2017-05-15 | Consultation | On Track | - | - | none | Self Governance Modification | http://www.gasgovernance.co.uk/0610 | Joint Office | LIVE | Yes
UNC | 0611 | Amendments to the firm capacity payable price at Interconnection Points | This modification seeks to facilitate compliance with the EU tariff code by making amendments to the payable price at Interconnection Points (IP)s. | National Grid NTS | No | No | No | No | No | C | 2017-02-03 | C | 2017-05-18 | E | TBD | Assessment | On Track | - | - | none | Modification | http://www.gasgovernance.co.uk/0611 | Joint Office | LIVE | Yes
UNC | 0613S | Revised UK Link Manual CDSP Data Services Document | This modification seeks to introduce the updated UK Link Manual into the Data Services Contract as envisaged as part of the UNC 0565A implementation activities. | National Grid Gas Distribution | No | No | No | No | Yes | C | 2017-03-07 | E | 2017-06-15 | E | TBD | Assessment | On Track | - | FGO | none | Modification | http://www.gasgovernance.co.uk/0613 | Joint Office | LIVE | Yes
UNC | 0614 | Introducing IHD (In-Home Display) Installed Status of Failed | This modification seeks to obligate Shippers to provide additional information from their Suppliers that will be required for the implementation of Smart Metering. A new status of ‘Failed’ would be provided for the IHD Installed Status, so that Suppliers are able to capture when it has not been possible to provide an IHD to the customer as part of the smart metering installation visit. This is consistent with the arrangements for electricity. | EDF Energy | No | No | No | No | No | C | 2017-03-08 | E | TBD | E | TBD | On Hold | - | Deferred at March Panel as this may not be a UNC matter. Awaiting proposer update | - | none | Modification | http://www.gasgovernance.co.uk/0614 | Joint Office | LIVE | No
Note on P7: All estimated implementation dates are the earliest possible implementation dates. These are subject to change.