## Watch List
Correct as of 04/03/2021
Mod Ref |  | Modification Title | Proposing Organisation | Date Raised | Category | Workgroup | Current Status | Next Stage | Key date* | Legal Text Provider | IGT UNC Workgroup Summary
0762 |  | Adding the Retail Energy Code Performance Assurance Code Manager as a new User type to the Data Permissions Matrix | SGN | 2021-03-12 | Modification | Distribution | New Proposal | Panel Consideration | 2021-04-15 | Scotia Gas Networks | An IGT UNC equivilant Modification will need to be raised in due course to ensure that these permissions cover all meters. BUUK have agreed to sponsor the Modification.
746 |  | Clarificatory change to the AQ amendment process within TPD G2.3 | Gazprom Energy | 2020-09-15 | Modification | Distribution | Allocated to Workgroup | Report to Panel | 2021-04-22 | Cadent | Following the October Panel meeting this Modification was decoupled for UNC736S and given a new Modification number. This is currently still being developed at Workgroup and the Workgroup Report is not due to go to Panel until April 2021. Further business rules have been added to v2.1, however, until the solution is solidified the legal text has not been developed.
734 | S | Reporting Valid Confirmed Theft of Gas into Central Systems | Gazprom Energy | 2020-08-12 | Self-Governance | Distribution | Allocated to Workgroup | Workgroup | 2021-04-22 | Scotia Gas Networks | This Modification has been highlighted to the IGT UNC Panel as a potential impact on the IGT UNC. This was introduced to parties on 27th August at the Distribution Workgroup and we will monitor this closely for identified impacts on obligations on IGT UNC Supply Points. CA has further discussions scheduled with SPAA during the development of this modification to ensure that any cross-overs are identified early. The solution is still in Workgroup for development.

## IGT equivalent Mods
Correct as of 04/03/2021
Mod Ref |  | Modification Title | Proposing Organisation | Date Raised | Current UNC Status | Next UNC Stage | Key date | Legal Text Provider | IGT UNC Mod Ref | Current IGT UNC Status | Next IGT UNC Stage | Key date | IGT UNC Workgroup Summary
0760 |  | Introducing the concept of derogation for Net Zero innovation into Uniform Network Code (UNC) | Northern Gas Networks | 2021-03-09 | Allocated to Workgroup | Report to Panel | 2021-09-16 | Northern Gas Networks | 154 | Allocated to Workgroup | Report to Panel | 2021-07-01 | This Modification has been raised and is due to be discussed as part of the Workgorup for four months in order to align with the timetable for the UNC change.
743 | S | Revisions to User Termination Provisions | National Grid | 2020-11-06 | Implemented | Implementation | 2021-03-12 | N/A | 151 | Consultation | Report to Panel | 2021-04-01 | The Panel sent IGT151 out to consultation at the March Panel. This Modification's consultation will close on 30th April 2021.
0674 |  | Performance Assurance Techniques and Controls | Scottish Power | 2018-11-07 | Allocated to Workgroup | Report to Panel | 2020-01-21 | Cadent | 138 | Allocated to Workgroup | Report to Panel | 2020-01-22 | This Modification has been reviewed against v15 of UNC674S and the latest legal text. The Workgroup report for both mods is likely to go to the April Panels for a decision on consultation.
0664 | VV | Transfer of Sites with Low Read Submission Performance from Class 2 and 3 into Class 4 (adopted) | SSE | 2019-06-28 | Allocated to Workgroup | Report to Panel | 2021-02-18 | Cadent | 145 | Allocated to Workgroup | Report to Panel | TBC | A further variation request has been raised for this modification and this has been sent back to a UNC workgroup for development. The IGT UNC Panel have decided to defer the decision on IGT145s consultation until the work on the new variation develops.
0710 |  | CDSP provision of Class 1 read service | Wales & West Utilities | 2019-11-08 | Representations invited | Implementation | 2021-06-01 | NGN | 148 | Allocated to Workgroup | Report to Panel | 2021-02-26 | This Modification is being developed by the IGT UNC Workgroup and the draft legal text will be discussed in the April 2021 workgroup meeting with the target of completing the Workgroup report at the April meeting.
0692 | S | Automatic updates to Meter Read Frequency | Total GP | 2019-10-22 | Implemented | Implementation | TBC | N/A | 131 | Allocated to Workgroup | Report to Panel | 2020-01-22 | The appeal decision on UNC692S has been returned and the Panel implementation decision upheld. This Modification is currently with the DSC Change Management Committee for a decision on its implementation. Through discussions with both Code Administrators, it is deemed that the legal text for UNC692S sufficiently covers the obligations on IGT Supply Points, therefore, there is no need for a legal text change in the IGT UNC. Once a date for implementation is set for UNC692S the Proposer of IGT131 will withdraw the Modification. An email will be sent out to industry to ensure all parties are aware of the implementation of UNC692S and its impacts on IGT Supply Points.

## Live Review Groups
Correct as of 04/03/2021
Mod Ref |  | Modification Title | Proposing Organisation | Date Raised | Category | Workgroup | Current Status | Next Stage | Key date* | Legal Text Provider | IGT UNC Workgroup Summary
0749 | R | Increased DM SOQ Flexibility | Barrow Shipping Ltd | 2020-12-11 | Request | Distribution | Allocated to Workgroup | Report to Panel | 2021-07-15 | n/a | This Review group could have impacts on IGT Supply points, therefore it is important for IGT parties to track the progress of this Review group and feed in where necessary.
0693 | R | Treatment of kWh error arising from statutory volume-energy conversion | Scottish Power | 2019-05-23 | Request | UIG | Allocated to Workgroup | Report to Panel | 2020-10-15 | n/a | IGTs should assess whether their attendance is needed at this Review group to monitor and feed into any changes, specifically around the IGTAD.
0754 | R | Investigate Advanced Analytic Options to improve NDM Demand Modelling | Gazprom Energy | 2021-02-04 | Request | Other | Allocated to Workgroup | Report to Panel | 2021-11-18 | N/A - Request | This new Review group is to look at UIG and the improvement of UIG volatility by machine learning. The Proposer notes that any Code changes are likely to impact Section H, which the IGT does reference at secific clausal levels. The Review group is projected to last nine months, therefore, the CA will follow developement in this space.
0763 | R | Review of Gas Meter By-Pass Arrangements | Scottish Power | 2021-03-29 | Request | Other | New Proposal | Panel Consideration |  | 2021-04-15 | This Review group was raised on 29th March 2021. We will track this through to completion.