## Watch List
Correct as of 03/06/2021
Mod Ref |  | Modification Title | Proposing Organisation | Date Raised | Category | Workgroup | Current Status | Next Stage | Key date* | Legal Text Provider | IGT UNC Workgroup Summary
769 |  | Adding Local Authorities as a new User type to the Data Permissions Matrix | Cadent | 2021-06-01 | Modification | Distribution | New Proposal | Panel Consideration | 2021-06-17 | Cadent | The IGT UNC will need an equivalent Modification in order to add this to the DPM for IGT UNC Meters.
746 |  | Application of Clarificatory change to the AQ amendment process within TPD G2.3 from 1st April 2020 | Gazprom Energy | 2020-09-15 | Modification | Distribution | Allocated to Workgroup | Report to Panel | 2021-06-17 | Cadent | A full walkthrough of the final Legal Text will be completed at the May 2021 Workgroup. At the meeting the Workgroup determined that there were no IGT implications. As the legal text has not yet been published for this Modification this change will stay on the watch list until the legal text can be reviewed by the Code Administrator to ensure there are no unintended consequences of the change.
734 | S | Reporting Valid Confirmed Theft of Gas into Central Systems | Gazprom Energy | 2020-08-12 | Self-Governance | Distribution | Allocated to Workgroup | Report to Panel | 2021-06-17 | Scotia Gas Networks | This Modification has been highlighted to the IGT UNC Panel as a potential impact on the IGT UNC. This was introduced to parties on 27th August 2020 at the Distribution Workgroup and we will monitor this closely for identified impacts on obligations on IGT UNC Supply Points. CA has further discussions scheduled with SPAA during the development of this modification to ensure that any cross-overs are identified early. The solution is still in Workgroup for development and there has been no legal text released, therefore the Code Administrator cannot assess whether changes will be needed to the code.

## IGT equivalent Mods
Correct as of 03/06/2021
Mod Ref |  | Modification Title | Proposing Organisation | Date Raised | Current UNC Status | Next UNC Stage | Key date | Legal Text Provider | IGT UNC Mod Ref | Current IGT UNC Status | Next IGT UNC Stage | Key date | IGT UNC Workgroup Summary
762 | S | Adding the Retail Energy Code Performance Assurance Code Manager as a new User type to the Data Permissions Matrix | SGN | 2021-03-12 | Representations invited | Consultation end | 2021-06-04 | Scotia Gas Networks | 155 | Consultation | Panel decision | 2021-06-22 | IGT155 has been sent for consultation closing on 22nd June 2021.
0760 |  | Introducing the concept of derogation for Net Zero innovation into Uniform Network Code (UNC) | Northern Gas Networks | 2021-03-09 | Allocated to Workgroup | Report to Panel | 2021-09-16 | Northern Gas Networks | 154 | Allocated to Workgroup | Workgroup | 2021-07-01 | This Modification was last discussed at the 21-05 Workstream meeting, planned to be discussed at two further meetings to align the timeline with UNC0760. An amended Modification and Ancillary Document to the IGT UNC was published on 5th May 2021 which looks to widen the scope of the Modification away from exclusively Net Zero activities.
0674 |  | Performance Assurance Techniques and Controls | Scottish Power | 2018-11-07 | Awaiting Panel decision | Panel decision | 2021-06-17 | Cadent | 138 | Awaiting Panel decision | Panel decision | 2021-06-25 | This Modification will be discussed at the July 2021 Panel meeting following an extended consultation period.
0664 | V | Transfer of Sites with Low Read Submission Performance from Class 2 and 3 into Class 4 (adopted) | SSE | 2020-09-17 | Allocated to Workgroup | Report to Panel | 2021-06-17 | Cadent | 145 | Allocated to Workgroup | Report to Panel | TBC | UNC664V is due to go back to Panel following further development n 17th June 2021. The Proposer of IGT145 is due to attend the June Workstream meeting in order to update the group on what has changed in both areas and to confirm the next steps for both Modifications.
0710 |  | CDSP provision of Class 1 read service | Wales & West Utilities | 2019-11-08 | Implementation | Implementation | TBC | NGN | 148 | Notice of implementation published | Implementation | TBC | Panel agreed to proceed to implementation on 25th June 2021. The Final Modification Report and Implementation Notice for this Modification have been published. The Panel agreed that this modification should be aligned with UNC710 and XRN5218 and therefore a further notice of implementation will be issued once an implementation date is confirmed for the whole suite of changes. This is provisionally no earlier than 1st August 2021, resulting in an extraordinary release for the IGT UNC.
0692 | S | Automatic updates to Meter Read Frequency | Total GP | 2019-10-22 | Implemented | Implementation | TBC | N/A | 131 | Allocated to Workgroup | Report to Panel | TBC | The appeal decision on UNC692S has been returned and the Panel implementation decision upheld. This Modification is currently with the DSC Change Management Committee for a decision on its implementation. Through discussions with both Code Administrators, it is deemed that the legal text for UNC692S sufficiently covers the obligations on IGT Supply Points, therefore, there is no need for a legal text change in the IGT UNC. Once a date for implementation is set for UNC692S the Proposer of IGT131 will withdraw the Modification. An email will be sent out to industry to ensure all parties are aware of the implementation of UNC692S and its impacts on IGT Supply Points. Mod also has a dependency on the implementation of SEC mod MP077 ‘DCC Service Flagging’ which could be implemented in November 2021.

## Live Review Groups
Correct as of 03/06/2021
Mod Ref |  | Modification Title | Proposing Organisation | Date Raised | Category | Workgroup | Current Status | Next Stage | Key date* | Legal Text Provider | IGT UNC Workgroup Summary
0749 | R | Increased DM SOQ Flexibility | Barrow Shipping Ltd | 2020-12-11 | Request | Other | Allocated to Workgroup | Report to Panel | 2021-07-15 | n/a | This Review group could have impacts on IGT Supply points, therefore it is important for IGT parties to track the progress of this Review group and feed in where necessary.
0754 | R | Investigate Advanced Analytic Options to improve NDM Demand Modelling | Gazprom Energy | 2021-02-04 | Request | Other | Allocated to Workgroup | Report to Panel | 2021-11-18 | N/A - Request | This new Review group is to look at UIG and the improvement of UIG volatility by machine learning. The Proposer notes that any Code changes are likely to impact Section H, which the IGT does reference at specific clausal levels. The Review group is projected to last nine months, therefore, the CA will follow development in this space.
0763 | R | Review of Gas Meter By-Pass Arrangements | Scottish Power | 2021-03-29 | Request | Distribution | Allocated to Workgroup | Report to Panel | 2021-10-21 | N/A - Request | This Review group was raised on 29th March 2021. We will track this through to completion.