## Watch List
Correct as of 05/08/2021
Mod Ref |  | Modification Title | Proposing Organisation | Date Raised | Category | Workgroup | Current Status | Next Stage | Key date* | Legal Text Provider | IGT UNC Workgroup Summary
0777 |  | Removal of Obstacles to Market Withdrawal | Carlos Aguirre, Pavilion Energy | 2021-08-11 | Modification | Transmission | New Proposal | Report to Panel | 2021-11-18 | National Grid | Panel Members recommended that this Modification should go to Transmission Workgroup for 3 months reporting back to Panel in November 2021.
0746 |  | Application of Clarificatory change to the AQ amendment process within TPD G2.3 from 1st April 2020 | Gazprom Energy | 2020-09-15 | Modification | Distribution | Awaiting OfGEM decision | Ofgem Decision |  | Cadent | The modification has a retrospective element. Panel Members recommended that Modification 0746 should not be implemented at the July 2021 meeting. As the modification is considered a material change it has been sent to the Authority for decision.
0734 | S | Reporting Valid Confirmed Theft of Gas into Central Systems | Gazprom Energy | 2020-08-12 | Self-Governance | Distribution | Allocated to Workgroup | Report to Panel | 2021-11-18 | Scotia Gas Networks | Completion of the Workgroup Report is scheduled for the 23rd September 2021 meeting. IGT Workgroup to consider IGT UNC equivalent mod.

## IGT equivalent Mods
Correct as of 01/07/2021
Mod Ref |  | Modification Title | Proposing Organisation | Date Raised | Current UNC Status | Next UNC Stage | Key date | Legal Text Provider | IGT UNC Mod Ref | Current IGT UNC Status | Next IGT UNC Stage | Key date | IGT UNC Workgroup Summary
0769 | S | Adding Local Authorities as a new User type to the Data Permissions Matrix | Cadent | 2021-06-01 | Implemented | Effective Date | TBC | Cadent | 157 | Implemented | Effective Date | TBC | Both the IGT UNC and the UNC mods have been implemented and the target effective date is 19th October 2021.
0760 |  | Introducing the concept of derogation for Net Zero innovation into Uniform Network Code (UNC) | Northern Gas Networks | 2021-03-09 | Out for consulation | Panel decision | 2021-10-21 | Northern Gas Networks | 154 | Out for consulation | Panel decision | 2021-10-29 | This Modification was issued for Consultation with a 20 day consultation period closing on 20 September 2021 and will be considered at the October 2021 Panel
0674 |  | Performance Assurance Techniques and Controls | Scottish Power | 2018-11-07 | Allocated to Workgroup | Report to Panel | 2021-12-16 | Cadent | 138 | Deferred decision | Panel decision | 2021-10-29 | UNC0674 has been sent back to workgroup for up to a further six months. The IGT UNC Panel deferred decision on IGT138 to align with the UNC modification. The Panel agreed that if any changes were made to UNC0674 then IGT138 would need to be sent back to the Workgroup for further development. It has confirmed that UNC 0674 will be varied, so IGT 138 has been added to the IGT UNC Panel agenda in October.
0664 | VVS | Transfer of Sites with Low Read Submission Performance from Class 2 and 3 into Class 4 (adopted) | SSE | 2020-09-17 | Implemented | Effective Date | TBC | Cadent | 145S | Out for consulation | Panel decision | 2021-10-29 | UNC 0664VVS has been implemented. UNC Panel Members recommended implementation should take place no earlier than November 2022. The IGT UNC Panel will be making a decision on IGT145 at the October Panel. The implementation of the two modifications will be aligned and on the date that Xoserve deliver the systems changes required.

## Live Review Groups
Correct as of 01/07/2021
Mod Ref |  | Modification Title | Proposing Organisation | Date Raised | Category | Workgroup | Current Status | Next Stage | Key date* | Legal Text Provider | IGT UNC Workgroup Summary
0781 | R | Review of the Unidentified Gas process | Corona Energy | 2021-09-13 | Request | TBC | New Proposal | Panel Consideration | 2021-10-21 | N/A - Request | This new request is to be considered by the UNC Panel. If the Review Group is initiated, any recommendations could have implications for the settlement of IGT meter points governed through the UNC.
0749 | R | Increased DM SOQ Flexibility | Barrow Shipping Ltd | 2020-12-11 | Request | Other | Allocated to Workgroup | Report to Panel | 2021-07-15 | N/A - Request | This Review group could have impacts on IGT Supply points, therefore it is important for IGT parties to track the progress of this Review group and feed in where necessary. The group is due to report at the October UNC Panel and an application for an extension at September Panel was not granted.
0754 | R | Investigate Advanced Analytic Options to improve NDM Demand Modelling | Gazprom Energy | 2021-02-04 | Request | Other | Allocated to Workgroup | Report to Panel | 2021-11-18 | N/A - Request | This new Review group is to look at UIG and the improvement of UIG volatility by machine learning. The Proposer notes that any Code changes are likely to impact Section H, which the IGT does reference at specific clausal levels. The Review group is projected to last nine months, therefore, the CA will follow development in this space.
0763 | R | Review of Gas Meter By-Pass Arrangements | Scottish Power | 2021-03-29 | Request | Distribution | Allocated to Workgroup | Report to Panel | 2022-01-22 | N/A - Request | The Workgroup has been extended and is expected to report by January 2022.
0778 | R | Gas Vacant Sites Process review | Centrica | 2021-08-09 | Request | Dedicated | Allocated to Workgroup | Report to Panel | 2022-08-18 | N/A - Request | Review the process and treatment of Long Term Vacant Sites in Settlement