## Watch List
Correct as of 04/11/2021
Mod Ref |  | Modification Title | Proposing Organisation | Date Raised | Category | Workgroup | Current Status | Next Stage | Key date* | Legal Text Provider | IGT UNC Workgroup Summary
0784 | S | Transition to the Central Switching Service and the Retail Energy Code v3.0 | Cadent | 2021-10-12 | Self-Governance | Distribution | Allocated to Workgroup | Report to Panel | 2022-02-17 | Cadent | An IGT UNC equivalent mod will be required as gas switching lead transitions from UKLink to the CSS
0777 |  | Removal of Obstacles to Market Withdrawal | Carlos Aguirre, Pavilion Energy | 2021-08-11 | Modification | Transmission | Withdrawn |  |  | National Grid | Withdrawn
0746 |  | Application of Clarificatory change to the AQ amendment process within TPD G2.3 from 1st April 2020 | Gazprom Energy | 2020-09-15 | Modification | Distribution | Awaiting OfGEM decision | Ofgem Decision |  | Cadent | The modification has a retrospective element. Panel Members recommended that Modification 0746 should not be implemented at the July 2021 meeting. As the modification is considered a material change it has been sent to the Authority for decision.
0734 | S | Reporting Valid Confirmed Theft of Gas into Central Systems | Gazprom Energy | 2020-08-12 | Self-Governance | Distribution | Allocated to Workgroup | Report to Panel | 2021-11-18 | Scotia Gas Networks | The UNC modification has been amended, the workgroup report completed and the mod will be going to the November UNC Panel. To ensure IGT sites are treated in the same way as UNC sites, and IGT UNC modification will be required. IGT Workgroup must consider IGT UNC equivalent mod.

## IGT equivalent Mods
Correct as of 04/11/2021
Mod Ref |  | Modification Title | Proposing Organisation | Date Raised | Current UNC Status | Next UNC Stage | Key date | Legal Text Provider | IGT UNC Mod Ref | Current IGT UNC Status | Next IGT UNC Stage | Key date | IGT UNC Workgroup Summary
0769 | S | Adding Local Authorities as a new User type to the Data Permissions Matrix | Cadent | 2021-06-01 | Implemented | Effective Date | TBC | Cadent | 157 | Implemented | Effective Date | TBC | Both the IGT UNC and the UNC mods have been implemented and the target effective date is 19th October 2021.
0760 |  | Introducing the concept of derogation for Net Zero innovation into Uniform Network Code (UNC) | Northern Gas Networks | 2021-03-09 | Out for consulation | Panel decision | 2021-10-21 | Northern Gas Networks | 154 | Awaiting OfGEM decision | Ofgem Decision |  | UNC & IGT UNC Panels recommended implementation.
0674 |  | Performance Assurance Techniques and Controls | Scottish Power | 2018-11-07 | Allocated to Workgroup | Report to Panel | 2021-12-16 | Cadent | 138 | Considered by Workgroup | Panel decision | 2021-12-17 | UNC0674 has been sent back to workgroup for up to a further six months. The IGT UNC Panel deferred decision on IGT138 to align with the UNC modification. The Panel agreed that if any changes were made to UNC0674 then IGT138 would need to be sent back to the Workgroup for further development. It has confirmed that UNC 0674 will be varied, so IGT 138 has been returned to Workgroup to discuss the UNC 0674 variation drafting when it becomes available.
0664 | VVS | Transfer of Sites with Low Read Submission Performance from Class 2 and 3 into Class 4 (adopted) | SSE | 2020-09-17 | Implemented | Effective Date | TBC | Cadent | 145S | Implemented | Effective Date | TBC | UNC 0664VVS has been implemented. UNC Panel Members recommended implementation should take place no earlier than November 2022. The IGT UNC Panel also recommended implentation. The implementation of the two modifications will be aligned and on the date that Xoserve deliver the systems changes required.

## Live Review Groups
Correct as of 04/11/2021
Mod Ref |  | Modification Title | Proposing Organisation | Date Raised | Category | Workgroup | Current Status | Next Stage | Key date* | Legal Text Provider | IGT UNC Workgroup Summary
0749 | R | Increased DM SOQ Flexibility | Barrow Shipping Ltd | 2020-12-11 | Request | Other | Allocated to Workgroup | Closed | 2021-10-14 | N/A - Request | This Review group could have impacts on IGT Supply points, therefore it is important for IGT parties to track the progress of this Review group and feed in where necessary. The group is due to report at the October UNC Panel and an application for an extension at September Panel was not granted. The Review Group was Closed at the October Panel
0754 | R | Investigate Advanced Analytic Options to improve NDM Demand Modelling | Gazprom Energy | 2021-02-04 | Request | Other | Allocated to Workgroup | Report to Panel | 2021-11-18 | N/A - Request | This new Review group is to look at UIG and the improvement of UIG volatility by machine learning. The Proposer notes that any Code changes are likely to impact Section H, which the IGT does reference at specific clausal levels. The Review group is projected to last nine months, therefore, the CA will follow development in this space.
0763 | R | Review of Gas Meter By-Pass Arrangements | Scottish Power | 2021-03-29 | Request | Distribution | Allocated to Workgroup | Report to Panel | 2022-01-22 | N/A - Request | The Workgroup has been extended and is expected to report by January 2022.
0778 | R | Gas Vacant Sites Process review | Centrica | 2021-08-09 | Request | Dedicated | Allocated to Workgroup | Report to Panel | 2022-08-18 | N/A - Request | Review the process and treatment of Long Term Vacant Sites in Settlement
0781 | R | Review of the Unidentified Gas process | Corona Energy | 2021-09-13 | Request | TBC | New Proposal | Panel Consideration | 2022-04-21 | N/A - Request | This new request is to be considered by the UNC Panel. If the Review Group is initiated, any recommendations could have implications for the settlement of IGT meter points governed through the UNC.
783 | R | Review of AQ Correction Processes | Cadent | 2021-10-06 | Live | Other | Allocated to Workgroup | Report to Panel | 2022-07-21 | N/A - Request | A review of the Annual Quantity (AQ) correction processes which are set out within the Uniform Network Code (UNC). This review should assess whether the current arrangements meet the objectives for the setting of the AQ and identify and consider possible amendments that are required to UNC. This may have implications for the IGT UNC.