## Watch List
Correct as of 04/08/2022
Mod Ref |  | Modification Title | Proposing Organisation | Date Raised | Category | Workgroup | Current Status | Next Stage | Key date* | Legal Text Provider | IGT UNC Workgroup Summary
0815 | S | DSC Committee Quoracy | SEFE Energy Limited | 2022-08-12 | Modification | 2022-08-31 | Allocated to Workgroup | Report to Panel | 2022-10-20 | Gazprom | This Modification was raised on 12 Aug 2022 and seeks to amend the minimum quoracy requirements for Data Services Contract (DSC) Committees for Shippers and Transporters from three to two in line with the Uniform Network Code (UNC) Modification Rules for the Modification Panel and UNC Committee. The first Workgroup meeting took place on 31st August 2022. The Workgroup Report is due to be presented to Panel on 20th October 2022.
0813 |  | Revision of Virtual Last Resort User and Contingent Procurement of Supplier Demand Event Triggers | National Grid NTS | 2022-07-12 | Modification | Transmission | Allocated to Workgroup | Report to Panel | 2023-01-19 | National Grid | This modification is likely to be relevant to and include the IGT sites within a Shippers' portfolio, however the solution will be effected through the UNC and an IGT UNC modification is unlikely. The first Workgroup Meeting was held on 25th August 2022. The next Workgroup meeting is scheduled for 6th October 2022.
0811 | S | Shipper Agreed Read (SAR) exceptions process | SEFE Energy Limited | 2022-06-23 | Modification | Distribution | Allocated to Workgroup | Report to Panel | 2022-10-20 | Wales & West Utilities | Any solution identified in the UNC that processes at Supply Point level will likely require a modification in the IGT UNC to effect the solution within the IGT UNC similarly. The first Workgroup meeting took place on 25th August 2022. The Workgroup Report is expected to be developed during the next Workgroup meeting (22nd September 2022).
0809 | S | Distribution of Last Resort Supplier Payment (LRSP) claims to include IGT sites | Northern Gas Networks | 2022-06-01 | Modification | Distribution | Report to Panel | Panel Decision | 2022-09-15 | Northern Gas Networks | This solution will be in the UNC but there will be an impact to the IGT sites in a Shipper's portfolio. The need for a modification in the IGT UNC connected to this modification is unlikely. The Panel will consider the Final Modification Report and make final determination on 15th September 2022.
0799 |  | UNC arrangements for the H100 Fife project (100% hydrogen) | Scotland Gas Networks plc | 2022-01-07 | Modification | Distribution | Awaiting Ofgem decision | Ofgem Decision | TBC | Scotia Gas Networks | The Code Administrator does not currently see a direct impact on IGT UNC based on the information provided as: - the intention is for this solution to be completely ringfenced, which means things like a change to the definition of gas for example will only apply to Supply Meter Points and parties involved in the project; and - that there are currently no IGTs involved in the project. However, if the provisions do have a wider impact and/or an IGT gets involved in the project in future we will need to revisit. The solution implemented could set industry precedent for the use of hydrogen. The July Panel have recommended implementation and the modification now awaits Ofgem decision. Related DSC Change: XRN 5298.
0746 |  | Application of Clarificatory change to the AQ amendment process within TPD G2.3 from 1st April 2020 | SEFE Energy Limited | 2020-09-15 | Modification | Distribution | Awaiting Ofgem decision | Ofgem Decision | TBC | Cadent | Post consultation the mod was returned to the Workgroup to discuss further questions from the Panel. The Workgroup met and the mod was returned to Panel in July 2022 and is now with Ofgem for decision.
0734 | S | Reporting Valid Confirmed Theft of Gas into Central Systems | SEFE Energy Limited | 2020-08-12 | Self-Governance | Distribution | Awaiting Implementation | Implementation | TBC | Scotia Gas Networks | The Final Modification Report was considered by UNC Panel at its February 2022 meeting. The Panel agreed that the Modification should be implemented (on a date to be confirmed). The UNC legal drafting will need to be reviewed the impact of which will need to be considered by the IGT UNC. To ensure IGT sites are treated in the same way as UNC sites, an IGT UNC modification will be required. UNC0734s was approved by the UNC Panel on 17th February and is awaiting implementation on a date to be confirmed. Following discussion with IGT parties, a sponsor for an equivalate IGT UNC Modification has come forward. The timetable for this Modification is not yet know but the Code Administrator will continue to engage with the party. Oct/Nov 2022 implementation date expected due to CMS rebuild and the interim solution being rejected. Proposer waiting on Xoserve to confirm what will happen with the IGT settlement process before a Modification is taken forward for the IGT UNC. Related DSC Change: XRN 5236

## IGT equivalent Mods
Correct as of 04/08/2022
Mod Ref |  | Modification Title | Proposing Organisation | Date Raised | Current UNC Status | Next UNC Stage | Key date | Legal Text Provider | IGT UNC Mod Ref | Current IGT UNC Status | Next IGT UNC Stage | Key date | IGT UNC Workgroup Summary
0674 |  | Performance Assurance Techniques and Controls | Scottish Power | 2018-11-07 | Awaiting Implementation | Implementation | 2022-11-01 | Cadent | 138V | Awaiting Implementation | Implementation | 2022-11-01 | Both IGT138V and UNC674V were sent to Ofgem, following unanimous recommendations to implement from their respective Panels, in the week beginning 20th June 2022. Ofgem directed (on 29th July 2022) that both mods be implemented on 1st November 2022. At their August 2022 meeting the Panel considered changing the November 2022 Release Date from 4th November to 1st November to limit the number of Code releases in the same week. The Panel are currently seeking views on this potential change, which are due by 16th September 2022.
0664 | VVS | Transfer of Sites with Low Read Submission Performance from Class 2 and 3 into Class 4 (adopted) | SSE | 2020-09-17 | Awaiting Implementation | Implementation | 2023-02-23 | Cadent | 145S | Awaiting Implementation | Implementation | 2023-02-23 | UNC 0664VVS has been implemented. UNC Panel Members recommended implementation should take place no earlier than November 2022. The IGT UNC Panel also recommended implementation. The implementation of the two modifications will be aligned and on the date that Xoserve deliver the systems changes required. Related Xoserve Change XRN4990 (Transfer of Sites with Low Read Submission Performance from Class 2 and 3 into Class 4 (MOD0664)) has been given an implementation date of 23rd February 2023. The Implementation Date for IGT145S and UNC0664VVS will also be 23rd February 2023.
0800 |  | Introducing the concept of a derogation framework into Uniform Network Code (UNC) (Authority Direction) |  |  | Awaiting Implementation | Implementation | 2022-10-01 | Cadent | 160 | Awaiting Implementation | Implementation | 2022-11-04 | UNC0800 has been raised as a result of UNC764 being rejected. IGT160 was raised as a result of IGT154 being rejected. Both modifications were issued to Ofgem for Authority decision by their respective Panels. Ofgem published the Authority decisions to approve UNC0800 on 30th May 2022 and to approve IGT160 on 5th July 2022. UNC0800 has been given an implementation date of 1st October 2022.

## Live Review Groups
Correct as of 04/08/2022
Mod Ref |  | Modification Title | Proposing Organisation | Date Raised | Category | Workgroup | Current Status | Next Stage | Key date* | IGT UNC Workgroup Summary
0754 | R | Investigate Advanced Analytic Options to improve NDM Demand Modelling | SEFE Energy Limited | 2021-02-04 | Request | Other | Allocated to Workgroup | Report to Panel | TBC | This new Review group is to look at UIG and the improvement of UIG volatility by machine learning. The Proposer notes that any Code changes are likely to impact Section H, which the IGT does reference at specific clausal levels. The review group has been extended for a further year. The CA will follow development in this space. The next meeting is scheduled for 29th September 2022, where the Workgroup Report is expected to be developed.
0763 | R | Review of Gas Meter By-Pass Arrangements | Scottish Power | 2021-03-29 | Request | Distribution | Closed | - | - | The Panel considered and approved a 1 month extension at its July 2022 meeting for this review, meaning the report will be considered at the August Panel. The Workgroup Report was presented to Panel in August, where the Panel voted to close the request.
0778 | R | Gas Vacant Sites Process review | Centrica | 2021-08-09 | Request | Distribution | Closed | - | - | The Workgroup Report was presented to Panel in July, where Panel voted to close the request.
0783 | R | Review of AQ Correction Processes | Cadent | 2021-10-06 | Live | Other | Closed | - | - | A review of the Annual Quantity (AQ) correction processes which are set out within the Uniform Network Code (UNC). This review should assess whether the current arrangements meet the objectives for the setting of the AQ and identify and consider possible amendments that are required to UNC. This may have implications for the IGT UNC. The Workgroup Report was presented to Panel in August, where the Panel voted to close the request.
0812 | R | Review of Alternatives to “Must Read” Arrangements | Wales & West Utilities | 2022-07-01 | Live | Distribution | Allocated to Workgroup | Report to Panel | 2023-04-20 | A review of the 'must read' requirements and provisions in the UNC i.e. to review the options should a Shipper breach its meter reading obligations and alternatives to the current must read service provided by transporters. The first Workgroup meeting took place on 25th August 2022. An action was taken by the IGT UNC Code Administrator to seek views from IGT's on the use of their Must Read Process. The Code Administrator will report back to the UNC Workgroup at its next meeting and continue to monitor the development in this space. At the moment there is no intention of expanding the discussion from DN to IGT.