## Watch List
Correct as of 06/10/2022
Mod Ref |  | Modification Title | Proposing Organisation | Date Raised | Category | Workgroup | Current Status | Next Stage | Key date* | Legal Text Provider | IGT UNC Workgroup Summary
0824 | U | Appointment of CDSP as the Scheme Administrator for the Energy Price Guarantee (EPG) for Domestic Gas Consumers (Gas) | Northern Gas Networks | 2022-09-15 | Modification | - | Implemented | - | 2022-09-26 | Northern Gas Networks | To enable Central Data Service Provider (CDSP) to be appointed as Scheme Administrator for implementation and administration of the payment scheme for part of the Government’s Energy Price Guarantee (EPG) for Domestic Gas Consumers (Gas) scheme within Great Britain, which takes effect from 01 October 2022.This Modification had been progressed as and Urgent Modification. The Panel recommended implememtation on 21st September and the Authority approved the Modification on 22nd September with a designated implementaiton date of 26th September. The Modification was implemented on 26th September 2022. The UNC Panel are due to consider Workgroup Referral for this Modification at its meeting on 20th October 2022. IGT UNC Panel, at its September meeting, agreed that a Modification is also needed to the IGT UNC to ensure that the scheme and the role of the CDSP and IGTs is acknowledged within Code.
0822 | U | Reform of Gas Demand Side Response Arrangements | National Grid NTS | 2022-09-01 | Modification | - | Authority Decision | Awaiting Decision | - | National Grid NTS | This Modification was raised to include provisions within the UNC for National Grid NTS to: • Administer an invitation to offer process for Gas Demand Side Response (DSR), • Introduce option payments to Users that arrange with consumers to provide DSR in advance of winter, and • Extend the trigger for opening the DSR market from the issue of a Gas Balancing Notification to also include issue of a Margins Notice at the day ahead stage. This Modification had been progressed as and Urgent Modification. The Panel considered the FMR on 28th September and agreed to recommend implementation to the Authority. The IGT UNC Panel, at its September meeting, agreed that a Modification is also needed to the IGT UNC as the Code Administrator has had confirmation from Xoserve that there are infact IGT sites on the system now that meet the eligibility criteria of the Modification.
0819 |  | Establishing/Amending a Gas Vacant Site Process | British Gas | 2022-07-12 | Modification | 2022-09-22 | Allocated to Workgroup | Report to Panel | 2023-01-19 | TBC | This Modification seeks to provide Shippers with the ability to effectively manage their Settlement Performance Obligations and Transportation Costs for Vacant sites.
0816 |  | Update to AQ Correction Processes | E.ON Next | 2022-08-08 | Modification | 2022-08-25 | Allocated to Workgroup | Report to Panel | 2022-11-17 | TBC | This Modification was raised to add two further ‘eligible clauses’ to the Annual Quantity (AQ) amendment process within TPD G2.3.21 and to prevent AQ amendments being processed where there is no change in value to the AQ.
0815 | S | DSC Committee Quoracy | SEFE Energy Limited | 2022-08-12 | Modification | 2022-08-31 | Allocated to Workgroup | Report to Panel | 2022-10-20 | Gazprom | This Modification was raised on 12 Aug 2022 and seeks to amend the minimum quoracy requirements for Data Services Contract (DSC) Committees for Shippers and Transporters from three to two in line with the Uniform Network Code (UNC) Modification Rules for the Modification Panel and UNC Committee. The first Workgroup meeting took place on 31st August 2022. The Workgroup Report is due to be presented to Panel on 20th October 2022.
0813 |  | Revision of Virtual Last Resort User and Contingent Procurement of Supplier Demand Event Triggers | National Grid NTS | 2022-07-12 | Modification | Transmission | Allocated to Workgroup | Report to Panel | 2023-01-19 | National Grid | This modification is likely to be relevant to and include the IGT sites within a Shippers' portfolio, however the solution will be effected through the UNC and an IGT UNC modification is unlikely. The first Workgroup Meeting was held on 25th August 2022. The next Workgroup meeting is scheduled for 6th October 2022.
0811 | S | Shipper Agreed Read (SAR) exceptions process | SEFE Energy Limited | 2022-06-23 | Modification | Distribution | Allocated to Workgroup | Report to Panel | 2022-10-20 | Wales & West Utilities | Any solution identified in the UNC that processes at Supply Point level will likely require a modification in the IGT UNC to effect the solution within the IGT UNC similarly. The latest Workgroup meeting took place on 22nd September 2022. Extention request expected (to December 2022).
0809 | S | Distribution of Last Resort Supplier Payment (LRSP) claims to include IGT sites | Northern Gas Networks | 2022-06-01 | Modification | Distribution | Report to Panel | Panel Decision | 2022-09-15 | Northern Gas Networks | This solution will be in the UNC but there will be an impact to the IGT sites in a Shipper's portfolio. The need for a modification in the IGT UNC connected to this modification is unlikely. The Panel considered the Final Modification Report on 15th September. They determined that the Modification should be changed from Self-Governance to Authority Decision and agreed a recommendation to the Authority that the Modification should be implemented. Awaiting Authority Decision.
0799 |  | UNC arrangements for the H100 Fife project (100% hydrogen) | Scotland Gas Networks plc | 2022-01-07 | Modification | Distribution | Awaiting Ofgem decision | Ofgem Decision | TBC | Scotia Gas Networks | The Code Administrator does not currently see a direct impact on IGT UNC based on the information provided as: - the intention is for this solution to be completely ringfenced, which means things like a change to the definition of gas for example will only apply to Supply Meter Points and parties involved in the project; and - that there are currently no IGTs involved in the project. However, if the provisions do have a wider impact and/or an IGT gets involved in the project in future we will need to revisit. The solution implemented could set industry precedent for the use of hydrogen. The July Panel have recommended implementation and the modification now awaits Ofgem decision. Related DSC Change: XRN 5298.
0746 |  | Application of Clarificatory change to the AQ amendment process within TPD G2.3 from 1st April 2020 | SEFE Energy Limited | 2020-09-15 | Modification | Distribution | Awaiting Ofgem decision | Ofgem Decision | TBC | Cadent | Post consultation the mod was returned to the Workgroup to discuss further questions from the Panel. The Workgroup met and the mod was returned to Panel in July 2022 and is now with Ofgem for decision. Rejected by the Authority on 28th September 2022.
0734 | S | Reporting Valid Confirmed Theft of Gas into Central Systems | SEFE Energy Limited | 2020-08-12 | Self-Governance | Distribution | Awaiting Implementation | Implementation | TBC | Scotia Gas Networks | The Final Modification Report was considered by UNC Panel at its February 2022 meeting. The Panel agreed that the Modification should be implemented (on a date to be confirmed). The UNC legal drafting will need to be reviewed the impact of which will need to be considered by the IGT UNC. To ensure IGT sites are treated in the same way as UNC sites, an IGT UNC modification will be required. UNC0734s was approved by the UNC Panel on 17th February and is awaiting implementation on a date to be confirmed. Following discussion with IGT parties, a sponsor for an equivalate IGT UNC Modification has come forward. The timetable for this Modification is not yet know but the Code Administrator will continue to engage with the party. Oct/Nov 2022 implementation date expected due to CMS rebuild and the interim solution being rejected. Proposer waiting on Xoserve to confirm what will happen with the IGT settlement process before a Modification is taken forward for the IGT UNC. Related DSC Change: XRN 5236. Technical solution due to be delivered in October 2022, REC change needed to support and to allow files to be sent to CDSP from REC. Technical solution not going to be used until REC change goes in.

## IGT equivalent Mods
Correct as of 06/10/2022
Mod Ref |  | Modification Title | Proposing Organisation | Date Raised | Current UNC Status | Next UNC Stage | Key date | Legal Text Provider | IGT UNC Mod Ref | Current IGT UNC Status | Next IGT UNC Stage | Key date | IGT UNC Workgroup Summary
0674 |  | Performance Assurance Techniques and Controls | Scottish Power | 2018-11-07 | Awaiting Implementation | Implementation | 2022-11-01 | Cadent | 138V | Awaiting Implementation | Implementation | 2022-11-01 | Both IGT138V and UNC674V were sent to Ofgem, following unanimous recommendations to implement from their respective Panels, in the week beginning 20th June 2022. Ofgem directed (on 29th July 2022) that both mods be implemented on 1st November 2022.
0664 | VVS | Transfer of Sites with Low Read Submission Performance from Class 2 and 3 into Class 4 (adopted) | SSE | 2020-09-17 | Awaiting Implementation | Implementation | 2023-02-23 | Cadent | 145S | Awaiting Implementation | Implementation | 2023-02-23 | UNC 0664VVS has been implemented. UNC Panel Members recommended implementation should take place no earlier than November 2022. The IGT UNC Panel also recommended implementation. The implementation of the two modifications will be aligned and on the date that Xoserve deliver the systems changes required. Related Xoserve Change XRN4990 (Transfer of Sites with Low Read Submission Performance from Class 2 and 3 into Class 4 (MOD0664)) has been given an implementation date of 23rd February 2023. The Implementation Date for IGT145S and UNC0664VVS will also be 23rd February 2023.
0800 |  | Introducing the concept of a derogation framework into Uniform Network Code (UNC) (Authority Direction) |  |  | Awaiting Implementation | Implementation | 2022-10-01 | Cadent | 160 | Awaiting Implementation | Implementation | 2022-11-01 | UNC0800 has been raised as a result of UNC764 being rejected. IGT160 was raised as a result of IGT154 being rejected. Both modifications were issued to Ofgem for Authority decision by their respective Panels. Ofgem published the Authority decisions to approve UNC0800 on 30th May 2022 and to approve IGT160 on 5th July 2022. UNC0800 has been given an implementation date of 1st October 2022. At their August 2022 meeting the Panel considered changing the November 2022 Release Date from 4th November to 1st November to limit the number of Code releases in the same week. The Panel sought views on this potential change and agreed at its September meeting that the release date should be changed from 4th November to 1st November 2022. THis means that IGT160 will be implemented on 1st November 2022.

## Live Review Groups
Correct as of 06/10/2022
Mod Ref |  | Modification Title | Proposing Organisation | Date Raised | Category | Workgroup | Current Status | Next Stage | Key date* | IGT UNC Workgroup Summary
0754 | R | Investigate Advanced Analytic Options to improve NDM Demand Modelling | SEFE Energy Limited | 2021-02-04 | Request | Other | Allocated to Workgroup | Report to Panel | 2022-10-20 | This new Review group is to look at UIG and the improvement of UIG volatility by machine learning. The Proposer notes that any Code changes are likely to impact Section H, which the IGT does reference at specific clausal levels. The review group has been extended for a further year. The CA will follow development in this space. The next meeting is scheduled for 29th September 2022, where the Workgroup Report was developed. The Workgroup Report will be presented to the Panel on 20th October 2022. Modification is not currently expected.
0812 | R | Review of Alternatives to “Must Read” Arrangements | Wales & West Utilities | 2022-07-01 | Live | Distribution | Allocated to Workgroup | Report to Panel | 2023-04-20 | A review of the 'must read' requirements and provisions in the UNC i.e. to review the options should a Shipper breach its meter reading obligations and alternatives to the current must read service provided by transporters.At the moment there is no intention of expanding the discussion from DN to IGT. The latest Workgroup meeting took place on 22nd September 2022. An action was taken by the IGT UNC Code Administrator to seek views from IGT's on the use of their Must Read Process. The Code Administrator reported back to the UNC Workgroup at this meeting and will continue to monitor the development in this space.