## Slide 1: IGT173 – Gateway Delivery of RPC Data
Testing Approach Overview
August Workgroup Update

## Slide 2: Background
Modification IGT173 aims to update the mechanism of delivery of the RPC files from email/portal to IX delivery.
IGT173 has been approved by the IGT UNC Panel, and XRN 5720 has been approved by the DSC Committee. Both changes are targeting the Nov 2024 release for implementation.
To support delivery, a testing window for volunteering parties is being created ahead of delivery.
Only a small number of parties have expressed interest in testing as part of the modification responses.
Pre implementation testing is not planned for all IGT modifications; the approach for IGT173 will be bespoke. As part of IGT173 approval, the testing approach will require panel review ahead of commencement of the testing window.

## Slide 3: Workgroup considerations / recommendations – *Updated*
Confirmation of testing window duration – suggestion 3 weeks (may conclude quicker).
  Window to be just under three weeks – 2 weeks testing and the remaining as contingency.
Confirmation of testing window commencement date – suggestion 7th – 25th October.
  Xoserve are aiming for the earlier window of 1st -18th Oct (to allow IGTs to simulate live running).
Workgroup recommendation that the testing scenarios deliver confidence for the approved business rules.
  Do any additional scenario tests need including for any of the business rules?
  No additional scenarios identified following last meeting – to be finalised at Aug meeting. Do we now want to test the 5pm cut off business rule?
Do parties want to test anything which is outside of the stated business rules?
  An example of this is a file which is an inconsistent file size e.g. 10 x larger than normal.
  No additional scenarios identified following last meeting – requirement to be finalised at Aug meeting.
Confirmation of testing parties – so far 2 x IGT and 2 x Shipper volunteers, anyone else?
  Updated to 3 x IGT volunteers at July meeting, no additional volunteers have come forward – requirement to be finalised at Aug meeting. Testing leads to be provided to E.ON.
Do volunteering parties want to test with all participants or use a buddy system?
  To replicate live, all participating IGTs will issue to all participating Shippers.
Do volunteering parties want to have daily check in calls or another frequency?
  Suggestion to hold a mid-morning (11am) call. There will be a minimum of a commencement call on the 1st , a weekly wrap up on the 4th, a 2nd week kick off call on the 7th and a weekly wrap up (and decision on contingency need) on the 11th. All other days will be decided by testing participants who will stand up/down call around needs.
How do workgroup and volunteering parties want to capture testing evidence?
  Suggestion to use the testing log template (presented in July). All completed logs to be sent to E.ON at the end of testing to collate to a single log to share with Panel.
How do workgroup and volunteering parties want to recommend release implementation to Panel?
  Suggestion for the final testing daily call to capture a formal recommendation (similar to a Go/No-Go recommendation) which is then submitted to panel with the test log.

## Slide 4: Workgroup considerations / recommendations – Continued
Testing data to be dummy rather than live
  July workgroup supported using test data and agreed to add it as a note to the scenario tests (next slide).
Retention of test data
  As the test data is ‘dummy data’, it has been suggested to delete the data once testing as concluded. This is likely to be parties' data retention policies (and a sensible ask) – to be discuss at the Aug meeting.
CDSP attendance for testing
  The CDSP will have representative (Nov 24 Project Manager) for the initial kick-off call, any additional attendance will be by request.
Issue raising to the CDSP
  This will be via uklinkdelivery@xoserve.com and any correspondence sent to include XRN/Mod info in the title as well as cc the Nov 24 Project Manager. All issues submitted to this mailbox are to be captured in the testing log.
Industry Comms ahead of testing
  It has been suggested to issue comms (via the IGT UNC and CDSP) to confirm the testing approach in a bespoke comms and also do a final call for volunteers – to be discussed at the Aug meeting.

## Slide 5: Initial High-Level Testing Scenarios
The IGTs can successfully create a file using the guidance documentation.
Files are successfully cascaded between the IGT / CDSP / Shipper with successful notifications issued.
Files with invalid file extensions fail as expected and unsuccessful notifications are issued.
Files with invalid naming conventions fail as expected and unsuccessful notifications are issued.
Files with incorrect file numberings e.g. TKAB1234 fail and unsuccessful notifications are issued.
NOTES:
File naming for testing use ‘TN’ rather than production ‘PN’ naming. Should PN files be used this may result in files be loaded into parties live environments.
File data to contain test/dummy data rather than replicating live billing data.

## Slide 6: Business Rules Testing
Business Rule | Scenario Test | Comment
1 | 1 & 2 | IGT only test for creating the file to send
2 | 2 | IGT, Shipper and CDSP test confirming successful IX delivery
3 | 2 | Delivered via scenario 2, no additional scenarios outlined for this
4 | - | IGTs may want to add in scenarios to test, no current scenarios captured
5 | 1, 2 & 3 | IGT, Shipper and CDSP tests for valid and invalid scenarios
6 | 2 & 4 | IGT, Shipper and CDSP tests for valid and invalid scenarios
7 | - | No scenarios currently outlined as timing of the test window does not reflect live
8 | - | Avoidance of date statement, no scenarios outlined for this
9 | - | Offline process, no scenarios outlined for this
10 | 2 | Delivered via scenario 2, no additional scenarios outlined for this
11 | 2 | Delivered via scenario 2, no additional scenarios outlined for this
12 | - | No scenarios as this rule is around completing testing
13 | - | No scenarios as this is relates to the post implementation review

## Slide 7: Thank you