## Watch List
Correct as of 01/07/2024
Mod Ref |  | Modification Title | Proposing Organisation | Date Raised | Live/Closed | Category | Workgroup | Current Status | Next Stage | Key date* | Legal Text Provider | IGT UNC Workgroup Update / Current Status
0894 |  | Facilitating Biomethane entry into the GDN by exporting methane from the GDN into the NTS via Compression | Cadent | 2024-08-06 | Live | Modification | Transmission | Allocated to Workgroup | Report to Panel | 2025-02-20 | 2025-02-20 | This Modification seeks to introduce new criteria of Offtake where gas flows into the National Transmission System (NTS) from the Gas Distribution Network (GDN), and to clarify the treatment of the associated energy.
0893 |  | Reintroduce NTS Capacity Surrender text and update TPD B2.12 | National Gas Transmission | 2024-08-06 | Live | Fast Track | None | New Proposal | Panel Consideration | 2024-09-19 | 2024-09-19 | The title of TPD B2.11 (Surrender of NTS Entry Capacity) was mistakenly changed and two clauses under 2.11 were removed in error due to what appears to be an issue with the implementation of a Modification. This Modification seeks to reintroduce the original text that was erroneously removed and implement the changes contained within Modification 0796 as intended.
0892 |  | Update incorrect NTS Entry Capacity paragraph references and reintroduce Daily Auctions to Entry Overrun Charges | National Gas Transmission | 2024-08-06 | Live | Fast Track | None | New Proposal | Panel Consideration | 2024-09-19 | 2024-09-19 | The purpose of this Modification is to reintroduce reference to Daily NTS Entry Capacity within the entry Overrun Charges section of the UNC and update incorrect paragraph references within TPD B section 2 - NTS Entry Capacity.
0891 |  | Reintroduction of the enhanced pressure service and increased MNEPOR for BBLC (reintroduced by UNC0589 and introduced by UNC0814) | National Gas Transmission | 2024-08-06 | Live | Modification | Transmission | Representations invited | Final Mod Report | 2024-09-19 | 2024-09-19 | The purpose of the Modification is to enable an extension of the temporary arrangements introduced via UNC0859 (which ends on 31 December 2024), and previously introduced by UNC0814 (which ended on 30 September 2023), until 31st December 2025. These arrangements permit BBL Company (BBLC) to increase their export capabilities at the Bacton IP on a temporary basis by gaining access to the existing enhanced pressure service and increasing their Maximum Network Exit Point Offtake Rate (MNEPOR).
0890 |  | Update to AQ Correction Processes - Request for Adjustments (RFA) AQ Change | Centrica | 2024-08-06 | Live | Modification | Distribution | Allocated to Workgroup | Report to Panel | 2025-03-20 | 2025-03-20 | This Modification proposes to add a further ‘eligible cause’ to the Annual Quantity (AQ) amendment process within TPD G2.3.21.
0889 |  | Clarifying Inclusion of the Reserve Price in the System Entry Overrun Charge | National Gas Transmission | 2024-08-05 | Live | Self-Governance | Transmission | Allocated to Workgroup | Report to Panel | 2024-12-19 | 2024-12-19 | This Modification will introduce an explicit reference to the Reserve Price within TPD B2.13.3 the System Entry Overrun Charge to clarify the process.
0888 |  | Correction to the Assessment Period for Demand Side Response (DSR) Option Offers | National Gas Transmission | 2024-08-05 | Live | Fast Track | None | Awaiting Implementation | Implemented | 2024-09-09 | 2024-09-09 | This Modification seeks to correct drafting errors in Modification 0866S ‘Amendments to Demand Side Response (DSR) Arrangements in respect of National Gas Transmission’s (NGT’s) assessment period for DSR Option Offers.
0887 |  | Facilitating Bi-Directional Connections Between IGT Pipelines and the NTS | National Gas Transmission | 2024-07-18 | Live | Modification | Transmission | Allocated to Workgroup | Panel Consideration | 2025-01-16 | 2025-01-16 | This Modification was raised as an alternative to 0871. However, the UNC Panel determined that it was an extension of the 0871 solution and voted that the Modification should be separate and not an alternative. This Modification is likely to impact IGTs and the IGT UNC and seeks to clarify the treatment of energy entering the NTS after entering an IGT network.
0886 |  | Amend the Code Cut-Off Date to a Rolling 3-Year Period | SSE Energy Supply Limited | 2024-06-28 | Live | Modification | Distribution | Allocated to Workgroup | Panel Consideration | 2025-02-20 |  | The purpose of the modification is to shorten the code cut-off date (or line in the sand) from a 3 to 4-year period to a monthly rolling 3-year period. As line in the sand also applies to IGTs this will likely have an impact on IGTs. Code impacts are not yet known.
0885 |  | Amendment to Gas Quality NTS Entry Specification at the St Fergus SAGE System Entry Point | SAGE North Sea Limited | 2024-06-11 | Live | Modification | Transmission | Allocated to Workgroup | Panel Consideration | 2024-10-17 |  | This enabling Modification will facilitate a change to the current contractual oxygen limit at the St Fergus SAGE System Entry Point, through modification of a network entry provision contained within the Network Entry Agreement (NEA) between National Grid Gas plc and SAGE North Sea Limited (SNSL) in respect of the St Fergus SAGE Sub-Terminal. No impact anticipated for IGT UNC.
0884 |  | Extending the PC4 Read Submission Window | OVO Energy | 2024-06-11 | Live | Modification | Distribution | Allocated to Workgroup | Panel Consideration | 2025-01-16 |  | Under UNC TPD, in Profile Class (PC) 4, M, 5.9.4, Shippers have 25 Supply Point System Business Days after the read date to submit a meter read for Settlement. Where there is an issue preventing the read from being validated, and that issue is not resolvable within the 25 Day timeframe, the read becomes unusable. This is problematic for meter reads that are hard to retrieve from the meter. For example, it might take several months to obtain another reading from the meter. This Modification is seeking to extend the submission window for more complex reads. Changes under UNC Mod to TPD, M, 5.9.4 - Several references to M and 5.9. Potential impact to Code as a result of cross references. Though any change to the submission window will impact IGTs as the submission window is for IGT sites is the same.
0883 |  | Update to the Annual Quantity (AQ) amendment process for- Erroneous Domestic AQs | Centrica | 2024-06-11 | Closed | Modification | Distribution | N/A | N/A | N/A |  | This Modification has been withdrawn.
0882 |  | Transparency of non-standard Gas Quality parameters at new entry connections to the NTS | National Gas Transmission | 2024-06-10 | Live | Modification | Transmission | Allocated to Workgroup | Report to Panel | 2024-11-21 |  | This Modification seeks to enable greater transparency where a new entry connection to the National Transmission System (NTS) requests a “non-standard” gas quality specification, outside of the published NTS specification. This is to be more consistent with the rules for consultation at existing sites, whilst not impacting the connection process timelines adversely. Potential code impact as a result of changes to UNC Section V. This Modification could impact IGTs for any future new connections for IGT sites.
0881 |  | Review and consolidation of UNC Transition Document TDIIC - Transitional Rules | National Gas Transmission | 2024-06-07 | Live | Modification | Governance | Allocated to Workgroup | Report to Panel | 2024-10-17 |  | This Modification seeks to review and remove obsolete transitional rules within UNC TDIIC Transitional Rules and introduce additional steps within TDI – General to enable easier reviewing and removal of expired Transitional Rules in the future. Potential IGT UNC impact if there is reference to areas of the Transitional Rules referenced under the IGT UNC that are being remove / changed. IGTs will also need to consider any new clause under the Transition Document being introduced to help with the removal of future changes.
0880 |  | Amendment to Wobbe Index upper limit in the Network Entry Agreement at the York Entry Point | Centrica | 2024-05-28 | Live | Modification | Transmission | Allocated to Workgroup | Report to Panel | 2024-08-15 |  | The Modification will enable the Wobbe Index upper limit set out in the York Network Entry Agreement between National Gas and Centrica Energy Storage to be increased from 51.2 MJ/m3 to 51.4 MJ/m3. Not expected to impact the IGT UNC.
0878 |  | Use of Entry Capacity Holdings at Easington at the Rough Storage ASEP in Winter 2024/2025 | Centrica Energy Storage Limited | 2024-05-20 | Live | Modification | Transmission | Allocated to Workgroup | Report to Panel | 2024-07-18 |  | This Modification Proposal will ensure entry capacity holdings at the Easington Aggregated System Entry Point (ASEP) can be utilised at the Rough Storage ASEP during Winter 2024/25 in the same way as they were during Winter 2022/23 and Winter 2023/24. An enhancement has been proposed to permit any User which secures Rough Storage Capacity can redesignate Easington Entry Capacity to the Rough ASEP. Not expected to impact the IGT UNC.
0876 | S | Updates to the Annual Quantity (AQ) amendment process. | SEFE Energy Limited | 2024-04-29 | Live | Self-Governance | Distribution | Allocated to Workgroup | Report to Panel | 2024-11-21 |  | It is not believed that the IGT UNC requires updating as a result of this Modification as it points to the UNC for this part of the code, however, the updates made to the AQ amendments process will apply to IGT sites as well as DNO sites.
0875 | S | Minor amendment to the Vacant Site exit process & 0819 Legal Text re-numbering | Centrica | 2023-04-05 | Live | Self-Governance | Distribution | Allocated to Workgroup | Report to Panel | 2024-08-15 |  | New UNC Modification to act as as a housekeeping Modification to 0819. The Modification specifically indicates no IGT UNC impact. CDSP had viewed the initial legal text for 0875 and did not think there are any impacts to the IGT UNC because the relevant sections of the IGT UNC text, Sections 6 and 21, both already refer to the relevant sections of the UNC, so when these UNC sections are updated through this new modification, the updates will automatically apply to IGT sites. It was clarified that there is an impact from UNC 0875 on IGT sites, but not the IGT code.
0874 | S | Amendments to UNC to align with Gas Demand Forecasting Methodology | National Gas Transmission | 2024-04-05 | Live | Self-Governance | Transmission | Allocated to Workgroup | Report to Panel | 2024-08-15 |  | 09/05/24 - This is a housekeeping Modification to address out-of-date references within the UNC, the main action for the IGT UNC is to determine whether the IGT UNC Code already points to relevant sections of the UNC. Workgroup agreed to keep this Modification on the Watch List wihls the changes to the UNC are drafted.
0872 |  | Single-sided Nominations for clearing houses of gas exchanges | European Commodity Clearing AG | 2024-04-04 | Live | Self-Governance | Transmission | Allocated to Workgroup | Report to Panel | 2024-08-15
0871 | S | Facilitating IGTs with NTS Entry | Barrow Shipping Ltd | 2024-04-04 | Live | Modification | Transmission | Allocated to Workgroup | Report to Panel | 2024-09-19 |  | Would appear to have an IGT impact. 09/05/24 - The Proposer had been asked to attend the IGT Workgroup, as they did not believe there was an IGT UNC impact. The proposer has not reached out but AJ confirmed that they would try and have a discussion with them. CDSP to provide further updates from Transmission Workgroups. Workgroup agreed to keep a watching brief on the development of this Modification.
0870 |  | Amendments to Wobbe Index and Calorific Value Lower Limits at NTS System National Transmission System (NTS) Entry Points. | National Gas Transmission | 2024-03-11 | Live | Modification | Transmission | Allocated to Workgroup | Report to Panel | 2024-09-19 |  | This was highlighted by UNC Panel as having a potential IGT impact. Phil Hobbins (National Gas Transmissions) does not agree as the Mod does not propose to change any text in UNC. Discussions were undertaken during April IGT Workgroup, however, it was agreed to leave open for now rather than draw conclusion as yet. CDSP to provide update from Transmission Workgroups. Nick King provided an update following the meeting to advise that there is no legal text and the entry points are listed in the mod, all being NTS. Regarding CV, it’s his understanding that billing for consumers connected directly to DNs or indirectly to DNs via IGTs is based on Gas (Calculation of Thermal Energy) Regs methodology and that this ignores NTS entry; the consumer’s bills being based on CV measurement from NTS/DN transfer points (NTS to LDZ offtakes as per OAD) and LDZ entry (including in future UNC 0842 / IGT 172 entry). Hence, he believes that 0870 would have no impact on IGT or DN. 09/05/24 - The CDSP had a representative at the last UNC Transmission Workgroup. KA added that IGTs were not included within the impacted parties on the modification documents, but noted this was the first Workgroup for UNC 0870 and the modification is still in development.
0868 |  | Gas Demand Side Response (DSR) Aggregation Arrangements | SEFE Energy Limited | 2024-02-07 | Live | Modification | Distribution | Allocated to Workgroup | Report to Panel | 2024-08-15
0866 |  | Amendments to Demand Side Response (DSR) Aggregation Arrangements | National Gas Transmission | 2024-01-08 | Closed | Self-Governance | Transmission | Implemented | - | 2024-06-10 | National Gas Transmission | They may require a consequent IGT mod if implemented.
0864 |  | Update of UNC Code Communication Methods | National Gas Transmission | 2023-11-03 | Live | Self-Governance | Governance | Allocated to Workgroup | Report to Panel | 2024-08-15 | 2023-11-16 | This modification seeks to align obligated Code Communication methods with future communication network changes, attributable to national PSTN decommissioning, to prevent undue disruption to the GB gas industry.
0862 | S | Amendments to the current Unidentified Gas Reconciliation Period arrangements | SEFE Energy Limited | 2023-10-26 | Live | Modification | Distribution | Allocated to Workgroup | Report to Panel | 2024-09-19 |  | This Modification proposes amendments to the current Unidentified Gas Reconciliation Period arrangements to reconcile UIG to the same months that the energy originated from (instead of smear over the previous 12 months).
0860 | S | Clarify impact of exit capacity holdings on offtake rights | RWE Trading GmbH | 2023-10-05 | Live | Self-Governance | Transmission | Allocated to Workgroup | Report to Panel | 2024-09-19
0857 | S | Revision to the Determination of Non-Transmission Services Gas Year Target Revenue | National Gas Transmission | 2023-09-13 | Live | Modification | NTSCMF | Awaiting Implementation | Implemented | 2024-10-01
0855 |  | Settlement Adjustments for Supply Point Meter Points impacted by the Central Switching System P1 Incident. | SEFE Energy Limited | 2023-08-08 | Closed | Modification | None | Implemented | - | 2024-06-28 | Cadent | This Modification is being raised to specifically address the Settlement issues arising from the P1 Incident on CSS. Approved for implementation at October's Panel - with Ofgem.
0843 |  | Establishing the Independent Shrinkage Charge and the Independent Shrinkage Expert | OVO Energy | 2023-04-06 | Live | Modification | Other | Allocated to Workgroup | Report to Panel | 2024-09-19 | Scotia Gas Networks | To incentivise the reduction of greenhouse gas emissions and customer bills, this Modification introduces the role of the Independent Shrinkage Expert (ISE) who will establish: the Independent Shrinkage Model (ISM), the Independent Shrinkage Model Methodology (ISMM), the Independent Shrinkage Multiplication Factor (ISMF), and the Independent Shrinkage Charge (ISC).
0842 |  | Gas Entry onto the Total system via an Independent Gas Transporter | SGN | 2023-03-29 | Live | Modification | Distribution | Awaiting Implementation | Implemented | 2024-08-12 | Scotia Gas Networks | This Modification will facilitate gas flow into the Total System via an Independent Gas Transporters (IGT) pipeline.
0819 |  | Establishing/Amending a Gas Vacant Site Process | British Gas | 2022-09-02 | Live | Modification | Distribution | Awaiting Implementation | Implemented | TBC | Cadent | This Modification seeks to provide Shippers with the ability to effectively manage their Settlement Performance Obligations and Transportation Costs for Vacant sites.
0808 | S | Reverse Compression | Barrow Shipping Limited | 2022-05-09 | Live | Modification | Distribution | Awaiting Implementation | Implemented | TBC | Scotia Gas Networks | To modify the UNC to enable a Distribution Network Operator (DNO) and an Independent Gas Transporter (IGT) to enter into a bilateral ‘operator to operator’ agreement, enabled by the iGT Arrangements Document (IGTAD) and containing Network Entry Provisions, to allow physical gas to be offtaken from a DNO by an ITo modify the UNC to enable a Distribution Network Operator (DNO) and an Independent Gas Transporter (IGT) to enter into a bilateral ‘operator to operator’ agreement, enabled by the IGT Arrangements Document (IGTAD) and containing Network Entry Provisions, to allow physical gas to be offtaken from a DNO by an IGT, compressed to a higher pressure, then returned to the same DNO by the IGT, through a process known as reverse compression. Reverse compression has zero net impact on physical flow into or out of the Total System, other than the initial filling (commissioning) of the IGT System, which is already established in IGTAD and the DNO’s associated CSEP Connection Arrangements. Neither reverse compression nor commissioning require User involvement.

## Watchlist (Closed) (hidden)
CLOSED LIST
Mod Ref |  | Modification Title | Proposing Organisation | Date Raised | Live/Closed | Category | Workgroup | Current Status | Next Stage | Key date* | Legal Text Provider | IGT UNC Workgroup Update / Current Status
0867 |  | Gas Demand Side Response (DSR) Aggregation Arrangements | National Gas Transmission | 2024-01-08 | Closed | Modification | Transmission | Withdrawn | End of process | 2024-05-01 | National Gas Transmission | They may require a consequent IGT mod if implemented.
0865 | S | Permitting DNOs to charge Shippers negative Supplier of Last Resort (SoLR) unit rates | Wales & West Utilities | 2023-12-05 | Closed | Self-Governance | Distribution | Implemented | Effective Date | 2024-03-08 |  | UNC TPD (Transportation Principal Document) Section Y part B only permits Distribution Network Operators (DNOs) to charge positive unit rates to Shippers, this modification permits negative rates.
0863 | S | Erroneous Transfers Exception Process | SEFE Energy Limited | 2023-10-26 | Closed | Modification | Distribution | Withdrawn | End of process | 2024-05-21 | 2023-11-16 | To provide a remedy for Erroneous Transfers that have failed to be progressed (exceptions) within a reasonable period to be proactively managed by the Central Data Services Provider (CDSP). Question to Workgroup - Should this be a REC modification?
0861 |  | Clarification of Provisions Regarding Utilisation of the System Without Holding System Capacity | National Gas Transmission | 2023-10-24 | Closed | Self-Governance | None | Implemented | Effective Date | 2024-04-16 |  | The purpose of this Modification is to acknowledge the extent of Transporters’ obligations to accept gas tendered for delivery to (or make gas available for offtake from) the System in the provisions that set out the charges payable where a User utilises the System without holding system capacity.
0859 | S | Reintroduction of the enhanced pressure service and increased MNEPOR for BBLC (as introduced by UNC0814) | National Gas Transmission | 2023-10-09 | Closed | Modification | Transmission | Implemented | Effective Date | 2024-04-19
0858 |  | Amendment to Network Entry Provision at Shell St Fergus Terminal | Shell | 2023-09-13 | Closed | Modification | None | Implemented | Effective Date | 2023-12-08 |  | This Modification will enable the current Wobbe Index upper limit that applies between National Grid and Shell at St Fergus to be increased on an enduring basis from 51.2 MJ/m3 to 51.4 MJ/m3.
0856 |  | Introduction of Trials for Non-Daily Metered (NDM) Demand Side Response (DSR) | National Gas Transmission | 2023-09-13 | Closed | Modification | None | Implemented | Effective Date | 2024-04-22 |  | Issued for a shortened 12 day consulation
0854 |  | Revision of Virtual Last Resort User and Contingent Procurement of Supplier Demand Event Triggers | National Gas Transmission | 2023-08-04 | Closed | Modification | Transmission | Implemented | End of process | 2024-05-22 | National Gas Transmission | The UNC Modification Panel has considered this new Modification, at their meeting on Thursday 17 August 2023 and highlighted that there is a potential IGT-UNC impact.
0853 |  | CDSP permissions to facilitate implementation of UNC0701. | Northern Gas Networks | 2023-07-27 | Closed | Self-Governance | Distribution | Implemented | Effective Date | 04/11/2023 in line with UNC701 | Northern Gas Networks | Modification 0701 (Aligning Capacity booking under the UNC and arrangements set out in relevant NExAs), is being implemented in November 2023, should Shippers not reduce capacity in line with the NExA agreement they will be in breach of Uniform Network Code at this time. This Modification gives permission for the CDSP to reduce the capacity to align with the NExA should the Shipper not do so. Also includes administrative change re use of acronym NExA. At August Panel it was determined that this Modification should proceed to Consultation.
0852 | S | Shipper notification in relation to option exercise for Customer Demand Side Response | SEFE Energy Limited | 2023-07-25 | Closed | Modification | Transmission | Rejected | End of process | 2024-04-29 | National Gas Transmission | To require National Gas to notify the relevant Shipper in the event that a Customer Demand Side Response option is exercised. At August Panel it was determined that this Modification be issued to Workgroup with a Report to be presented to the January 2024 Panel.
0850 |  | Amendments to Allocation of Unidentified Gas Expert (AUGE) arrangements to introduce a new Residual Upstream Contributor | SEFE Energy Limited | 2023-07-07 | Closed | Modification | Distribution | Withdrawn | End of process | 2023-12-11 | Cadent | This Modification proposes to amend the existing Allocation of Unidentified Gas arrangements to introduce a new Residual Upstream Contributor that will be the new daily balancing factor for Unidentified Gas. | 2
0841 |  | Introduction of cost efficiency and transparency requirements for the CDSP Budget, and revisions to DSC change processes | British Gas | 2023-03-06 | Closed | Modification | Governance | Implemented | End of process | 2024-06-03 | Cadent | The purpose of this Modification is to improve the ability of UNC Parties to fulfill their obligation jointly to control and govern the CDSP on an economic and efficient basis (under UNC General Terms, Section D, 1.4.4), through the introduction of explicit requirements for efficiency, greater transparency of the Budget and revised governance processes. The Modification Panel has considered the Alternative Modification above, at their meeting on Thursday 19 October 2023 and highlighted that there is a potential IGT-UNC impact.
0836 | A | Resolution of Missing Messages following Central Switching Service implementation and integration with REC Change R0067. | Cadent | 2023-02-06 | Closed | Self-Governance | Distribution | Implemented | Effective Date | 18/12/2023 in line with RC0067 | Cadent | This Modification clarifies treatment and activities necessary when the CSS Registration Effective from Date does not align to that recorded in the UK Link system due to the issue whereby systems that interface with the Central Switching Service (CSS) have not received expected messages because they have not been generated, or because of issues in transmission or receipt of the messages. At August Panel it was determined that this Modification should proceed to Consultation.
0831 | S | Allocation of LDZ UIG to Shippers (Class 3 and 4) Based on a Straight Throughput Method | Brook Green Trading | 2023-03-06 | Closed | Alternate Modification | Distribution | Rejected | End of process | 2024-02-06 | Cadent | The purpose of this Modification is to remove the current AUGE process and create a permanent weighting table that encourages movement to Daily Metering, reduces levels of UIG and discourages risk premiums for customers.
0831 | A | Allocation of LDZ UIG to Shippers Based on a Straight Throughput Method | SSE | 2022-11-08 | Closed | Modification | Distribution | Rejected | End of process | 2024-02-06 | Cadent | The purpose of this Modification is to change the method by which unidentified gas (UIG) is allocated to Shippers from the current AUGE table of weighting factors to a throughput or universal allocation model. At August 2023 panel it was voted for the Modification to be deferred to September's panel rather than issue for Consultation.
0825 |  | Removal of the remaining Retrospective Asset, Address and Supply Point (RAASP) elements of the Retrospective Adjustment arrangements put in place under Modification 0434 | EDF Energy | 2022-10-10 | Closed | Modification | Distribution | Implemented | End of process | 2023-12-15 | Cadent | Removal of the remaining Retrospective Asset, Address and Supply Point (RAASP) elements of the Retrospective Adjustment arrangements put in place under Modification 0434 | 2023-06-15 | 2023-07-06 | 2022-05-19
0816 |  | Update to AQ Correction Processes | E.ON Next | 2022-08-08 | Closed | Self-Governance | Distribution | Implemented | Effective Date | 2024-02-24 | Scotia Gas Networks | This Modification was raised to add two further ‘eligible clauses’ to the Annual Quantity (AQ) amendment process within TPD G2.3.21 and to prevent AQ amendments being processed where there is no change in value to the AQ.Settlement Performance Obligations and Transportation Costs for Vacant sites. Report due to be taken to Panel in May 2023. Will be fully implemented into the IGT UNC by UNC modification. However one reference is now incorrect in the IGT UNC and this will need to be corrected. In Part C I Section 6 the reference to 2.3.22 should now read 2.3.23.
0811 | S | Shipper Agreed Read (SAR) exceptions process | SEFE Energy Limited | 2022-06-23 | Closed | Self-Governance | Distribution | Implemented | Effective Date | 2024-02-24 | Wales & West Utilities | Any solution identified in the UNC that processes at Supply Point level will likely require a modification in the IGT UNC to effect the solution within the IGT UNC similarly. The FMR was presented to Panel on 19th January 2023 and the Panel determined that this Modification should be implemented on a date to be confirmed. Will be implemented in the IGT UNC by UNC drafting

## IGT UNC Equivalents
Correct as of 06/06/2024
Mod Ref | Modification Title | Proposing Organisation | Date Raised | Current UNC Status | Next UNC Stage | Key date | IGT UNC Mod Ref | Current IGT UNC Status | Next IGT UNC Stage | Key date | IGT UNC Workgroup Summary
0843 | Establishing the Independent Shrinkage Charge and the Independent Shrinkage Expert | OVO Energy | 2023-04-06 | Allocated to Workgroup | Report to Panel | 2024-07-18 | IGT165 | Allocated to Workgroup | Report to Panel | 2024-10-15 | 05/09/2024- At the last 0843 WG meeting, which took place on 20th August, the revised legal drafting was discussed, there were a number of changes made and discussed with regards to IGT related clauses. Next WG meeting for 0843 is expected to take place on 17th September. The Proposer is expected to review the and amend the Framework in the Modification in line with the suggestions from the WG. The Legal Text will also be reviewed further following the WGs discussions. The CA recommends that IGTs review the Legal Text discussed at the meeting on the 20th August and the published meeting minutes.
0819 | Establishing/Amending a Gas Vacant Site Process | British Gas | 2022-09-02 | Awaiting Implementation | Implementation | TBC | IGT168 | Awaiting Implementation | Implementation | TBC

## Live Review Groups
Correct as of 06/06/2024
Mod Ref |  | Modification Title | Proposing Organisation | Date Raised | Category | Workgroup | Current Status | Next Stage | Key date* | IGT UNC Workgroup Summary
0879 | R | Review of current Supply Meter Point Classes (Class 1,2,3 and 4). | Centrica | 2024-05-24 | Live | Distribution | Allocated to Workgroup | Report to Panel | 2025-07-17 | Second Workgroup took place in August, where potental scenarios and things to consider were discussed.
0851 | R | Extending the Annually Read PC4 Supply Meter Point (SMP) read submission window | OVO Energy | 2023-07-10 | Closed | Distribution | - | - | - | UNC Modification Workgroup Report presented to UNC Panel in July where it was agreed that the Review should be closed. UNC0884 - Extending the PC4 Read Submission Window has been raised.
0849 | R | Commercial Framework Review to Enable Hydrogen Blending | National Gas Transmission | 2023-05-09 | Live | Other | Allocated to Workgroup | Report to Panel | 2024-09-19 | To review the market principles and existing commercial framework in order to assess their compatibility with blending hydrogen into the networks and explore the required amendments where necessary. Ensuring the amended regime is simple and easy to implement whilst also remaining adaptable and consistent with relevant obligations. Report expected at Panel on 19th Sep.

## IGT UNC Impact Assess.
IGT UNC Impact Assessments (IAs)
Correct as of 06/06/2024
Mod Ref |  | Modification Title | Proposing Organisation | Date Raised | Category | IA Date | Summary of IA Discussions | IA Outcome | Modification Required | Modification Agreement Date | IGT UNC Modification Proposer | Additional Comments / Updates
0885 |  | Amendment to Gas Quality NTS Entry Specification at the St Fergus SAGE System Entry Point | SAGE North Sea Limited | 2024-06-11
0884 |  | Extending the PC4 Read Submission Window | OVO Energy | 2024-06-11
0883 |  | Update to the Annual Quantity (AQ) amendment process for- Erroneous Domestic AQs | Centrica | 2024-06-11
0882 |  | Transparency of non-standard Gas Quality parameters at new entry connections to the NTS | National Gas Transmission | 2024-06-10
0881 |  | Review and consolidation of UNC Transition Document TDIIC - Transitional Rules | National Gas Transmission | 2024-06-07
0880 |  | Amendment to Wobbe Index upper limit in the Network Entry Agreement at the York Entry Point | Centrica | 2024-05-28
0878 |  | Use of Entry Capacity Holdings at Easington at the Rough Storage ASEP in Winter 2024/2025 | Centrica Energy Storage Limited | 2024-05-20
0877 | S | Alignment of TO Revenue and TO Revenue Adjustment terms to the current Gas Transporter Licence | National Gas | 2024-05-03
0876 | S | Updates to the Annual Quantity (AQ) amendment process. | SEFE Energy Limited | 2024-04-29
0875 | S | Minor amendment to the Vacant Site exit process & 0819 Legal Text re-numbering | Centrica | 2023-04-05
0874 | S | Amendments to UNC to align with Gas Demand Forecasting Methodology | National Gas Transmission | 2024-04-05
0872 |  | Single-sided Nominations for clearing houses of gas exchanges | European Commodity Clearing AG | 2024-04-04
0871 | S | Facilitating IGTs with NTS Entry | Barrow Shipping Ltd | 2024-04-04
0870 |  | Amendments to Wobbe Index and Calorific Value Lower Limits at NTS System National Transmission System (NTS) Entry Points. | National Gas Transmission | 2024-03-11
0868 |  | Gas Demand Side Response (DSR) Aggregation Arrangements | SEFE Energy Limited | 2024-02-07
0866 |  | Amendments to Demand Side Response (DSR) Aggregation Arrangements | National Gas Transmission | 2024-01-08
0864 |  | Update of UNC Code Communication Methods | National Gas Transmission | 2023-11-03 | Live
0862 | S | Amendments to the current Unidentified Gas Reconciliation Period arrangements | SEFE Energy Limited | 2023-10-26
0863 | S | Erroneous Transfers Exception Process | SEFE Energy Limited | 2023-10-26 | Live | 2024-03-14 | Indications from the Proposer that the mod will be raised in the REC. Mod not yet withdrawn. This Mod is still on hold in the UNC until further notice.
0854 |  | Revision of Virtual Last Resort User and Contingent Procurement of Supplier Demand Event Triggers | National Gas Transmission | 2023-08-04 |  | 2024-05-09 | UNC legal text will impact on the IGT UNC. Mod mitigates DN risk. Similar risk may be identified for IGTs which would require an IGT UNC mod for the same purpose. It is not believed that the UNC legal text will impact the IGT UNC, however, the Code Administrator will review the UNC legal text to understand if there are any impacts. IGT's will need to decide if they want a similar mod to cover off their own risk if they believe that they have a risk to themselves. The CDSP confirmed that the solution for 0854 was going to apply to both GT and IGT sites, it will apply to any sites that are owned by the sanction shipper, slash user premises termination user. The Chair agreed that an IGT UNC equivalent modification would not be required but would check the legal drafting to confirm there is no impact. The CA is to review the IGT UNC and the legal text for 0854 to determine if any further action might be needed to be taken by the IGT UNC in relation to this Modification. | TBC
0865 |  | Permitting DNOs to charge Shippers negative Supplier of Last Resort (SoLR) unit rates | Wales & West Utilities | 2023-12-05 |  | 2024-03-14 | IGT sites included through UNC governance and not at supply point level. UNC0865 has now been implemented. The Workgroup doesn't believe that there is any impact. | None
0856 |  | Introduction of Trials for Non-Daily Metered (NDM) Demand Side Response (DSR) | National Gas Transmission | 2023-09-13 |  | None | IGT sites are expected to be included in the trials. Sent out for shortened consultation. Panel did not recommend implementation. Gone to Ofgem for decision. Proposer have decided to cease the trials so no IGT Mod required at this time. | None.
0855 |  | Settlement Adjustments for Supply Point Meter Points impacted by the Central Switching System P1 Incident. | SEFE Energy Limited | 2023-08-08 | Modification | None | See UNC 0836. Modification IGT171 has now been raised. |  | Modification Required. |  | SEFE
0853 |  | CDSP Permissions to facilitate implementation of UNC0701. | Northern Gas Networks | 2023-07-27 |  | 2023-08-10 | The IGT Workgroup, at it's August meeting agreed that an IGT Modification would be required to cover the changes from UNC0701 and UNC0853 and to allow IGT's to manage the NExA implications. A proposer volunteered to sponsor this Modification and will work with the CA to raise and develop this. IGT169 has now been raised. |  | Modification Required. |  | MUA | Legal drafting in the IGT UNC needed in response to the implementation of UNC 0701 and the secondary intention of UNC0853 to allow the CDSP to validate using the relevant information
0852 |  | Shipper notification in relation to option exercise for Customer Demand Side Response | SEFE Energy Limited | 2023-07-25 | Live | 2023-08-10 | The section of the legal text added by the proposer in relation to the Shipper Notification would be encompassed in the IGT UNC by the legal text in IGT167.
0850 |  | Amendments to Allocation of Unidentified Gas Expert (AUGE) arrangements to introduce a new Residual Upstream Contributor | SEFE Energy Limited | 2023-07-07 | Live | 2023-08-10 | Modification is at early stages, it has been to Panel and assigned to Workgroup. There were some questions raised on the IGT side which the proposer would take away and review. Proposer to attend September IGT Workgroup. This has now been withdrawn by the proposer. | None.
0845 |  | Enhancements to Demand Side Response (DSR) Arrangements including a D-5 Product | National Gas Transmission | 2023-04-12 | Modification | 2023-07-13 | This modification is still under development and an equivalent mod IGT167 has been raised in the IGT UNC. |  | Modification Required |  | BUUK
0844 |  | Enabling Direct Contractual Arrangements with Consumers for Demand Side Response | National Gas Transmission | 2023-04-12 | Modification | 2023-07-13 | The IGTs have not been marked as an impacted group. The intention is for the modification to work on IGT Sites. This modification is still under development and an equivalent mod IGT167 has been raised in the IGT UNC. |  | Modification Required |  | BUUK
0843 |  | Establishing the Independent Shrinkage Charge and the Independent Shrinkage Expert | OVO Energy | 2023-04-06 | Modification | 2023-06-08 | WG initially considered the Modification during April 2023 meeting. The Proposer has indicated that they are happy to raise a Modification should there be an IGT/IGT UNC impact. The need for a Modification is dependant on how the UNC Mod Proposer sees Shrinkage Expert Role impacting IGTs/IGT UNC. This modification is still under development and an equivalent mod IGT165 has been raised in the IGT UNC. | TBC | Modification Required | TBC | OVO | Proposer of UNC 0843 has indicated that they are keen to have the same obligations as the UNC with regards to Shrinkage. The UNC Modification Proposer has indicated that they are willing to raise a Modification to enable this. IGT UNC Modification IGT 165 raised
0842 |  | Gas Entry onto the Total system via an Independent Gas Transporter | SGN | 2023-03-29 | Modification | 2023-07-13 | WG initially considered the Modification during May 2023 meeting. The UNC Modification Proposer and the Proposer of 0808 will discuss offline and engage with IGTs. Likely an impact but further information needed, which will be considered at the June 2023 meeting. CDSP advised that that they would look to consult IGT's on this Modification. IGT172 has now been raised. | TBC | Modification Required | TBC | Barrow Shipping | The Legal Draft provider for the UNC mod believes that title for the gas needs to be 'handed off' between the two codes. This will likely require an amendment to Section J of the IGT UNC IGT 172 has been raised
0841 | A | Introduction of cost efficiency and transparency requirements for the CDSP Budget, and revisions to DSC change processes | British Gas | 2023-03-06 | Modification | 2023-11-10 | Cross-code implications anticipated as all parties of the IGT UNC are also parties in the DSC. 0841A has now been withdrawn. 0841 has just gone out for consultation - due back 7th March 2024. No IGT impacts identified. | None.
0836 | S | Resolution of Missing Messages following Central Switching Service implementation and integration with REC Change R0067. | Cadent | 2023-02-06 |  | 2023-08-10 | The implications of this modification and related mod UNC0855 were discussed at the August Workgroup meeting. It was believed that the two UNC Modifications would require two equivalent IGT UNC Modifications. The implications of both UNC Mods would need to be fully understood by IGT UNC parties. The legal drafting for UNC0836 indicates that relatively small changes to the IGT UNC will be required. Specifically TPD Section G 5.9 and 5.18 will need to be referenced in the IGT UNC. UNC0836 was implemented 18/12/23. Modification IGT170 raised. |  | Modification Required |  |  | Need to add Section G 5.9 and Section M5.18 of TPD into the IGT UNC so a modification will be required
0833 |  | Enabling Demand Side Response (DSR) Market Offers to be made by Non-Trading System Transactions | National Grid NTS | 2022-11-29 | Modification | 2023-08-10 | The IGT UNC Panel, at its September meeting, agreed that a Modification is also needed to the IGT UNC as the Code Administrator has had confirmation from Xoserve that there are infact IGT sites on the system now that meet the eligibility criteria of the Modification. A sponsor for this Modification has approach the Code Administrator. We will continue to work with them in the new year to develop the nessessary changes to the IGT UNC. This modification will take into account 0822, 0833 and any other related DSR Modifications raised under the UNC. IGT167 Modification now been raised by BUUK and is out for consultation and due to go to an Extraordinary Panel on 17th August 2023. | Code & Party Impact | Modification Required (Non-Mirror) | 2022-09-23 | Jenny Rawlinson, BUUK | Legal Drafting for the UNC modification removes / amends parts of TPD Section M 4. The IGT UNC points at the entirety of Section M 4, so the mod will be implemented into the IGT UNC.
0825 |  | Removal of remaining Retrospective Asset, Address and Supply Point (RAASP) elements of the Retospective Adjustment Arrangements put in place under Modification 0434. |  | 2022-09-28 |  | 2023-08-10 | At the May 2023 Workgroup it was established that an IGT Modification was not required. However, Legal text to be reviewed by Code Administrator. The Workgroup considered the impact of UNC0825 on the IGT UNC. Following discussion, it was widely agreed that no equivalent IGT UNC Modification would be required, as the relevant references to the UNC would still be accurate in the event that UNC0825 was implemented. Workgroup confirmed that this impacts the IGT sites but it doesn't need the IGT equivalent as there was never an original IGT Modification and this reverses out what the updated Retro was going to put in. Due to go to Panel and then consultation. Need to monitor. | None. | N/A
0808 |  | Reverse Compression | Barrow Shipping Limited | 2022-05-09 | Modification | 2023-08-10 | WG considered the Modification following presentation from the Proposer. The WG agreed that based on the information provided there would not be an impact on the IGT UNC and therefore an IGT UNC Modification was not seen as being needed at this time. Still monitoring and seeking information as to whether there will be any impacts. | No Impact | N/A | N/A | N/A