## Introduction
IGT UNC Horizon Scanner
Date | 5th December 2024
Version | v1.0
Purpose | This document provides visibility of IGT UNC impacting industry activities, as well as the progression of Cross Code impacting Modifications. This document is owned by the IGT UNC Workgroup and is refreshed approximately monthly. Please refer to the IGT UNC Horizon Scanner page of the IGT UNC website for the most up to date version.
Contact | If you have any queries or comments about this Horizon Scanner, please contact the IGT UNC Code Administrator via email, IGTUNC@gemserv.com.
Uplift History | Reason for change | Date
v0.1 | Initial draft for Workgroup consideration | 2024-11-07
v1.0 | Uplift to approved working document | 2024-12-05

## Horizon Scanner
IGT UNC Horizon Scanner
|  |  | IMPACTS | [8 empty] | INDUSTRY CHANGE
Category | Activity | Description / Scope | IGT UNC | UNC | Other Codes | IGT | Shipper | Other Party | Risks / Issues | Current Status | Future Milestones / Key Dates | IGT Changes | UNC Changes | Other Code Changes | Central System Changes | Licences | Other Comments / Useful Context
Code Reform | Code Consolidation (GNC) | Introduction of GNC, which will involve the merging of IGT UNC and UNC. Designation of changes ahead of consolidation is expected. Further information on this will be noted when it is avaiable. | Yes | Yes | CUSC DCUSA SQSS STC | Yes | Yes | All parties to impacted Codes | Introduction of inaccuracies, short notice changes, lack of party engagement. | Ofgem Work Ongoing, last publication on the implementation of energy code reform was on 22nd August 2024. https://www.ofgem.gov.uk/decision/implementation-energy-code-reform-decision | We expect that a series of Ofgem-led industry working groups, beginning in 2025, will be the primary vehicle for engaging industry and developing the code changes necessary to deliver targeted rationalisation. Ofgem's next consultation will provide further detail on the sequencing and steps involved in code consolidation. The aim is for much of the detailed work to create the contractual framework and rationalise code provisions to take place in advance of a code manager being appointed. | Directed changes expected (timeline TBC) | Directed changes expected (timeline TBC) | Directed changes expected (timeline TBC) | TBC | Directed changes expected (timeline TBC) | Ofgem identified the following areas where they believed code provisions should be targeted for rationalisation and simplification as part of any Ofgem-led consolidation activity, using the transitional powers granted by the Energy Act: • Common contractual framework • Contract boilerplate and defined terms • Party accession and exit • Code objectives • Code modification process • Code compliance • Credit cover arrangements • Dispute processes • Derogation provisions
Code Reform | SDS | Introduction of the Ofgem SDS, which is intended to set the direction of travel for the development of codes, in line with Ofgem's overarching vision for the sector. The SDS is required by the Energy act to contain a strategic assessment of government policy and developments which require modifications to the designated codes, and in preparing the SDS Ofgem must have regard to advice given by the NESO. | Yes | Yes | Yes | Yes | Yes | Yes | Risks and issues to be confirmed by Workgroup. | Ofgem Work Ongoing, last publication on the implementation of energy code reform was on 22nd August 2024. https://www.ofgem.gov.uk/decision/implementation-energy-code-reform-decision | Publication of the first SDS expected in spring 2025. Ofgem expected to consult on a draft SDS in winter 2024. The draft will cover all codes that are within the scope of energy code reform. Also expecting a new licence condition related to SDS which Ofgem intend to consult on in due course. | Directed changes expected (timeline TBC) | Directed changes expected (timeline TBC) | Directed changes expected (timeline TBC) | TBC | Directed changes expected (timeline TBC) | Ofgem currently do not propose to introduce an obligation to implement the SDS before code managers are in place, however, they have proposed the introduction of a standard prioritisation process for code panels which will support the introduction of the SDS (see 22nd August 2024 decision publication).
Code Reform | Code Governance | Changes to code governance (inc. matters relating to Code Managers, SAF, prioritisation, objectives, transition to new framework) will be done by Ofgem and with the permission of the SOS. | Yes | Yes | Yes | Yes | Yes | Yes | Risks and issues to be confirmed by Workgroup. | Ofgem Work Ongoing, last publication was a consultation on Code Manager Selection on 28th November 2024. This consultation closes on 30th January 2025. https://www.ofgem.gov.uk/sites/default/files/2024-11/Consultation_on_code_manager_selection.pdf | Code Managers: SAF: Ofgem have recently determined that the membership of SAF will be constituted with a fixed impartial membership including independent parties and a pool of additional members. Further consultations expected in due time. Prioritisation: Ofgem have decided to take forward our proposals to harmonise and extend the ability of code panels to prioritise the assessment of code modification proposals, and to introduce a consistent set of prioritisation criteria. Further consultation on the implementation of this into codes is expected in due course. Objectives: Ofgem are minded to proceed with Option 2 (introduce a code objective to support the delivery of the net zero target for 2050 and five-year carbon budgets) and will obtain views on a proposed way forward in an upcoming consultation. Transition: Ofgem have decided to proceed with our proposal to adopt a phased approach to transitioning the gas and electricity codes to the new governance framework. Phase 1 will include BSC and REC, Phase 2 will include the GNC and ECC and Phase 3 will include ETC and REC. Proposed timings and programme of work will be included in an upcoming consultation. | Directed changes expected (timeline TBC) | Directed changes expected (timeline TBC) | Directed changes expected (timeline TBC) | TBC | Directed changes expected (timeline TBC) | Recent publications on matters of Code Governance: Consultation on Code Manager Selection: https://www.ofgem.gov.uk/sites/default/files/2024-11/Consultation_on_code_manager_selection.pdf Decision on implementation of Energy Code Reform: https://www.ofgem.gov.uk/decision/implementation-energy-code-reform-decision
Code Reform | Pre-Consolidation Code Changes | Ofgem identified the following areas where we believed code provisions should be targeted for rationalisation and simplification as part of any Ofgem-led consolidation activity, using the transitional powers granted by the Act: • Common contractual framework • Contract boilerplate and defined terms • Party accession and exit • Code objectives • Code modification process • Code compliance • Credit cover arrangements • Dispute processes • Derogation provisions | Yes | Yes | Yes | Yes | Yes | Yes | Risks and issues to be confirmed by Workgroup. |  |  | Directed changes expected (timeline TBC) | Directed changes expected (timeline TBC) | Directed changes expected (timeline TBC) | TBC | Directed changes expected (timeline TBC) | Ofgem identified the following areas where they believed code provisions should be targeted for rationalisation and simplification as part of any Ofgem-led consolidation activity, using the transitional powers granted by the Energy Act: • Common contractual framework • Contract boilerplate and defined terms • Party accession and exit • Code objectives • Code modification process • Code compliance • Credit cover arrangements • Dispute processes • Derogation provisions
Xoserve | Project Trident | Project Trident is an Xoserve project, looking to modernise UK Link, the platform they use to connect information, technology and communications systems for the retail gas market. UK Link is used and managed by Xoserve in its role as CDSP. It ensures the industry operates smoothly, effectively and efficiently, in accordance with the Uniform Network Code and its IGT equivalent. | TBC | TBC | TBC | TBC | TBC | TBC | Risks and issues to be confirmed by Workgroup. | Xoserve's initial research began in July 2024, with a launch event taking place in September 2024. Xoserve work ongoing, further information on the Xoserve website: https://www.xoserve.com/products-services/data-products/uk-link-system/project-trident/ | Standard support for the current version of the SAP platform that supports UK Link ends in 2027, with extended support available until 2030. It is estimated that Project Trident will run until 2028. Xoserve's focus until July 2025 will be developing an FBC for procuring the most suitable solution against a set of critical success factors. | TBC | TBC | TBC | TBC | TBC
Xoserve | Service Line Review | Added by Workgroup - Review of the Xoserve service line areas, costs etc….. Detail to be confirmed by the Workgroup…. | TBC | TBC | TBC | TBC | TBC | TBC | Added by Workgroup - Detail to be confirmed | Added by Workgroup - Detail to be confirmed | Added by Workgroup - Detail to be confirmed | TBC | TBC | TBC | TBC | TBC
Digitalising the Energy System | Digital Spine Study | This feasibility study was funded by the Government’s NZIP, and examined the concept, opportunities and attributes of a data sharing infrastructure for the energy system; a ‘digital spine’. It was delivered by a consortium of Ove Arup, Energy Systems Catapult and the University of Bath. | - | - | - | - | - | - | None anticipated as part of the study itself. | DESNZ published its response to the digital spine study in August 2024. https://www.gov.uk/government/publications/digitalising-the-energy-system | Work expected to continue under Data Sharing Infrastructure work. | - | - | - | - | -
Digitalising the Energy System | Data Sharing Infrastructure | Introduction of a data sharing infrastructure, which is a minimum set of responsibilities, governance, functions and processes for secure, interoperable data sharing across the energy system. This activity covers the DSI Pilot, DSI MVP and Ofgem Guidance. | TBC | TBC | TBC | TBC | TBC | TBC | Risks and issues to be confirmed by Workgroup. | DESNZ published its response to the digital spine study in August 2024, which included commitments for the data sharing infrastructure https://www.gov.uk/government/publications/digitalising-the-energy-system Ofgem published its decision on the definition of ESD and DBP Guidance in October 2024. https://www.ofgem.gov.uk/decision/decision-definition-energy-system-data-data-best-practice-guidance | 2024: NESO will deliver a pilot data sharing infrastructure based on an outage planning use case. In Winter 2024, Ofgem will publish a further consultation on data sharing infrastructure governance, setting out their view of an enduring governance structure. The government will procure work in 2024 to assess the landscape of data standards 2025: NESO will begin its work in 2025, by delivering a minimum viable produce of a data sharing infrastructure focused on strategic planning. The government expects to publish a progress update against these commitments in 2025. | TBC | TBC | TBC | TBC | TBC | Related Ofgem programme’s name has changed from Energy Data and Digitalisation to Energy System Digitalisation. Ofgem's Energy System Digitalisation page is provided below: https://www.ofgem.gov.uk/energy-policy-and-regulation/policy-and-regulatory-programmes/energy-system-digitalisation
Hydrogen Blending | Added by Workgroup - Detail to be confirmed | Added by Workgroup - Detail and activities to be tracked to be confirmed by the Workgroup. | TBC | TBC | TBC | TBC | TBC | TBC | Added by Workgroup - Detail to be confirmed | Added by Workgroup - Detail to be confirmed | Added by Workgroup - Detail to be confirmed | TBC | TBC | TBC | TBC | TBC

## Cross Code Change
Cross Code Change
Code | Change Number | Related Changes | Title | Proposer | Current Status | Next Stage | Key Date | Other Comments / Useful Context
UNC | 843 | IGT165 | Establishing the Independent Shrinkage Charge and the Independent Shrinkage Expert | OVO Energy | Allocated to Working Group | Report to Panel | 2024-03-20 | Joint Office has reached out to the IGT UNC Code Administrator at the request of the UNC0843 Workgroup. They have asked that we attend future meetings. Xoserve have asked that add UNC0843 to the December IGT UNC Workgroup Agenda and invite the Proposer.
IGT UNC | 165 | UNC0843 | Establishing the Independent Shrinkage Charge and the Independent Shrinkage Expert | OVO Energy | Allocated to Working Group | Report to Panel | TBC - Waiting for UNC0843 to progress further before continuing at IGT UNC Workgroup | IGT UNC CA is currently reviewing the latest version of UNC0843 Legal Drafting to assess changes required to the IGT UNC.
UNC | 819 | IGT168 XRN5615 | Establishing/Amending a Gas Vacant Site Process | British Gas | Implemented | - | - | Implemented on 8th November 2024, to be removed after December Workgroup Meeting
IGT UNC | 168 | UNC0819 XRN5615 | Establishing/Amending a Gas Vacant Site Process | British Gas | Implemented | - | - | Implemented on 8th November 2024, to be removed after December Workgroup Meeting
UNC | 854 | IGT UNC Mod expected | Revision of Virtual Last Resort User and Contingent Procurement of Supplier Demand Event Triggers | National Grid Transmission | Implemented | - | - | Implemented on 22nd May 2024. IGT UNC Workgroup have agreed that a change to the IGT UNC is required. Waiting on an IGT UNC Modification to be raised.

## Milestone Timeline
IGT UNC Horizon Scanner Timeline
|  | 2024 |  |  |  |  | 2025 | [11 empty] | 2026
Category |  | Aug | Sep | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR
Code Reform | Code Consolidation (GNC) | 2024 Aug: Link
| SDS | 2024 Aug: Link; 2024 NOV: Ofgem consultation on draft SDS expected; 2025 MAR: First SDS expected
| Code Governance | 2024 Aug: Link; 2024 DEC: LINK, Respond by 30/01/25
| Pre-Consolidation Code Changes | 2024 Aug: Link
Xoserve | Project Trident | 2024 OCT: Launch Event; 2025 JUL: Completion of FBC and solution procurement expected
Service Line Review
Digitalising the Energy System | Digital Spine | 2024 Aug: Link; 2025 JAN: Gov. to procure work for landscape assessment in 2024
| DSI (NESO Pilot) | 2025 JAN: Pilot expected in 2024
| DSI (NESO MVP) | 2025 JAN: MVP Work expected in 2025
| DSI (Ofgem Guidance) | 2024 NOV: Ofgem consultation on DSI governance expected; 2026 JAN: DSI progress updated expected in 2025
Cross Code Change | UNC0845 (Shrinkage Expert) | 2025 APR: Consultation expected
| IGT165 (Shrinkage Expert) | 2025 MAY: Consultation expected
| UNC0819 (Vacant Site Process) | 2024 NOV: 08/11/2024
| IGT168 (Vacant Site Process) | 2024 NOV: 08/11/2024
D
D
D
D
P
C
E
D
C
P
R
R
R
W
W
W
W
W
W
W
W
W
W
W
P
P
C
C
C
W
IGT UNC WG Discussion
M
M
M
M
E
Activity TBC

## Timeline key
Icon | Description
Consultation Confirmed
Consultation Unconfirmed
Release Confirmed
Release Unconfirmed
Event/Workgroup/Steering Group Confirmed
Event/Workgroup/Steering Group Unconfirmed
Publication Confirmed
Publication Unconfirmed
Milestone Confirmed
Milestone Unconfirmed
Solid Yellow/Grey | Work Ongoing
P
P
R
R
C
C
E
E
M
M
W
S
W
S

## Acronyms
Acronym | Defined Term
BEIS | Department for Business, Energy, and Industrial Strategy
BSC | Balancing and Settlement Code
CDSP | Central Data Services Provider
CMA | Competition and Markets Authority
CSS | Central Switching Service
CUSC | Connection and Use of System Code
DBP | Data Best Practice
DCUSA | Distribution Connection and Use of System Agreement
ECC | Electricity Commercial Code
ESD | Energy System Data
ETC | Electricity Technical Code
FBC | Full Business Case
GEMA | Gas and Electricity Markets Authority
GNC | Gas Network Code
IGT UNC | Independent Gas Transporters Uniform Network Code
ISOP | Independent System Operator and Planner
MVP | Minimum Viable product
NESO | National Energy System Operator. Named in the Energy Act 2023 as ISOP
NZIP | Government’s Net Zero Innovation Portfolio
REC | Retail Energy Code
SAF | Stakeholder Advisory Forum
SDS | Strategic Direction Statement, which will set out Ofgems vision for how the codes should devolve on an annual basis
SEC | Smart Energy Code
SOS | Secretary of State
SQSS | Security and Quality of Supply Standard
STC | System Operator Transmission Owner Code
UNC | Uniform Network Code