## Introduction
IGT UNC Horizon Scanner
Date | 2025-02-06
Version | v1.2
Purpose | This document provides visibility of IGT UNC impacting industry activities, as well as the progression of Cross Code impacting Modifications. This document is owned by the IGT UNC Workgroup and is refreshed approximately monthly. Please refer to the IGT UNC Horizon Scanner page of the IGT UNC website for the most up to date version.
Contact | If you have any queries or comments about this Horizon Scanner, please contact the IGT UNC Code Administrator via email, IGTUNC@gemserv.com.
Uplift History | Reason for change | Date
v0.1 | Initial draft for Workgroup consideration | 2024-11-07
v1.0 | Uplift to approved working document | 2024-12-05

## Horizon Scanner
IGT UNC Horizon Scanner
|  |  | IMPACTS | [8 empty] | INDUSTRY CHANGE
Category | Activity | Description / Scope | IGT UNC | UNC | Other Codes | IGT | Shipper | Other Party | Risks / Issues | Current Status | Future Milestones / Key Dates | IGT Changes | UNC Changes | Other Code Changes | Central System Changes | Licences | Other Comments / Useful Context
Code Reform | Code Consolidation (GNC) | Introduction of GNC, which will involve the merging of IGT UNC and UNC. Designation of changes ahead of consolidation is expected. Further information on this will be noted when it is avaiable. | Yes | Yes | CUSC DCUSA SQSS STC | Yes | Yes | All parties to impacted Codes | Introduction of inaccuracies, short notice changes, lack of party engagement. | Ofgem Work Ongoing, last publication on the implementation of energy code reform was on 22nd August 2024: https://www.ofgem.gov.uk/decision/implementation-energy-code-reform-decision | We expect that a series of Ofgem-led industry working groups, beginning in 2025, will be the primary vehicle for engaging industry and developing the code changes necessary to deliver targeted rationalisation. Ofgem's next consultation will provide further detail on the sequencing and steps involved in code consolidation. The aim is for much of the detailed work to create the contractual framework and rationalise code provisions to take place in advance of a code manager being appointed. | Directed changes expected (timeline TBC) | Directed changes expected (timeline TBC) | Directed changes expected (timeline TBC) | TBC | Directed changes expected (timeline TBC) | Ofgem identified the following areas where they believed code provisions should be targeted for rationalisation and simplification as part of any Ofgem-led consolidation activity, using the transitional powers granted by the Energy Act: • Common contractual framework • Contract boilerplate and defined terms • Party accession and exit • Code objectives • Code modification process • Code compliance • Credit cover arrangements • Dispute processes • Derogation provisions
Code Reform | SDS | Introduction of the Ofgem SDS, which is intended to set the direction of travel for the development of codes, in line with Ofgem's overarching vision for the sector. The SDS is required by the Energy act to contain a strategic assessment of government policy and developments which require modifications to the designated codes, and in preparing the SDS Ofgem must have regard to advice given by the NESO. | Yes | Yes | Yes | Yes | Yes | Yes | Risks and issues to be confirmed by Workgroup when more detail is avaiable. | Ofgem Work Ongoing. Consultation on a preliminary SDS (as well as code governance arrangements) was published on 31st January 2025, which invites responses by 28th March 2025. Ofgem would like to hear views and feedback from anyone who has an interest in the preliminary SDS and governance arrangements, as well as people who work in the energy sector and the public. This includes: code administrators code parties central system delivery bodies consumer groups https://www.ofgem.gov.uk/consultation/consultation-preliminary-strategic-direction-statement-and-governance-arrangements-industry-codes | Publication of the first SDS expected in spring 2025. Ofgem have issued a consultation on a preliminary SDS, which is open for responses by 28th March 2025. Ofgem are hosting an event for industry on Monday, 17 February from 2:00 to 3:30pm. They will provide a high-level overview of the proposed content, structure and scope of the preliminary SDS. Find full details about the event on their registration page below: https://events.teams.microsoft.com/event/dd73cf35-f544-404a-9e8b-9810d3508780@185562ad-39bc-4840-8e40-be6216340c52 Also expecting a new licence condition related to SDS which Ofgem intend to consult on in due course. | Directed changes expected (timeline TBC) | Directed changes expected (timeline TBC) | Directed changes expected (timeline TBC) | TBC | Directed changes expected (timeline TBC) | Ofgem currently do not propose to introduce an obligation to implement the SDS before code managers are in place, however, they have proposed the introduction of a standard prioritisation process for code panels which will support the introduction of the SDS (see 22nd August 2024 decision publication and recently issued consultation on preliminary SDS dated 31st January 2025).
Code Reform | Code Governance | Changes to code governance (inc. matters relating to Code Managers, SAF, prioritisation, objectives, transition to new framework) will be done by Ofgem and with the permission of the SOS. | Yes | Yes | Yes | Yes | Yes | Yes | Risks and issues to be confirmed by Workgroup when more detail is avaiable. | Ofgem Work Ongoing. Consultation on code governance arrangements (as well as Ofgem's preliminary SDS) was published on 31st January 2025, which invites responses by 28th March 2025. Ofgem would like to hear views and feedback from anyone who has an interest in the preliminary SDS and governance arrangements, as well as people who work in the energy sector and the public. This includes: - code administrators - code parties - central system delivery bodies - consumer groups https://www.ofgem.gov.uk/consultation/consultation-preliminary-strategic-direction-statement-and-governance-arrangements-industry-codes | Code Managers: In future, Ofgem envisage that code managers may be subject to a licence obligation to prepare delivery plans setting out how they will facilitate delivery of the SDS through industry codes. Development of code manager licence conditions is ongoing and the intention is for these to be consulted on in spring 2025. Code Modifications: As part of stakeholder engagement planned for early 17th February 2025, Ofgem seek to understand to what extent existing modifications will enable the SDS. Ofgem are currently consulting on proposals to introduce a consistent set of prioritisation criteria. Proposed changes to all 15 codes. SDS: Stakeholder engagement even planned for 17th February 2025 regarding the preliminary SDS. | Directed changes expected (timeline TBC) | Directed changes expected (timeline TBC) | Directed changes expected (timeline TBC) | TBC | Directed changes expected (timeline TBC) | Recent publications on matters of Code Governance: Consultation on Code Manager Selection: https://www.ofgem.gov.uk/sites/default/files/2024-11/Consultation_on_code_manager_selection.pdf Decision on implementation of Energy Code Reform: https://www.ofgem.gov.uk/decision/implementation-energy-code-reform-decision Consultation on code governance arrangements and SDS: https://www.ofgem.gov.uk/consultation/consultation-preliminary-strategic-direction-statement-and-governance-arrangements-industry-codes
Code Reform | Pre-Consolidation Code Changes | Ofgem identified the following areas where we believed code provisions should be targeted for rationalisation and simplification as part of any Ofgem-led consolidation activity, using the transitional powers granted by the Act: • Common contractual framework • Contract boilerplate and defined terms • Party accession and exit • Code objectives • Code modification process • Code compliance • Credit cover arrangements • Dispute processes • Derogation provisions | Yes | Yes | Yes | Yes | Yes | Yes | Risks and issues to be confirmed by Workgroup. |  |  | Directed changes expected (timeline TBC) | Directed changes expected (timeline TBC) | Directed changes expected (timeline TBC) | TBC | Directed changes expected (timeline TBC) | Ofgem identified the following areas where they believed code provisions should be targeted for rationalisation and simplification as part of any Ofgem-led consolidation activity, using the transitional powers granted by the Energy Act: • Common contractual framework • Contract boilerplate and defined terms • Party accession and exit • Code objectives • Code modification process • Code compliance • Credit cover arrangements • Dispute processes • Derogation provisions
Xoserve | Project Trident | Project Trident is an Xoserve project, looking to modernise UK Link, the platform they use to connect information, technology and communications systems for the retail gas market. UK Link is used and managed by Xoserve in its role as CDSP. It ensures the industry operates smoothly, effectively and efficiently, in accordance with the Uniform Network Code and its IGT equivalent. | TBC | TBC | TBC | TBC | TBC | TBC | Risks and issues to be confirmed by Workgroup. | Xoserve's initial research began in July 2024, with a launch event taking place in September 2024. Xoserve work ongoing, further information on the Xoserve website: https://www.xoserve.com/products-services/data-products/uk-link-system/project-trident/ | Standard support for the current version of the SAP platform that supports UK Link ends in 2027, with extended support available until 2030. It is estimated that Project Trident will run until 2028. Xoserve's focus until July 2025 will be developing an FBC for procuring the most suitable solution against a set of critical success factors. | TBC | TBC | TBC | TBC | TBC
Xoserve | Service Line Review | Added by Workgroup - Review of the Xoserve service line areas, costs etc….. Detail to be confirmed when avaiable | TBC | TBC | TBC | TBC | TBC | TBC | Added by Workgroup - Detail to be confirmed | Added by Workgroup - Detail to be confirmed | Added by Workgroup - Detail to be confirmed | TBC | TBC | TBC | TBC | TBC
Digitalising the Energy System | Digital Spine Study | This feasibility study was funded by the Government’s NZIP, and examined the concept, opportunities and attributes of a data sharing infrastructure for the energy system; a ‘digital spine’. It was delivered by a consortium of Ove Arup, Energy Systems Catapult and the University of Bath. | - | - | - | - | - | - | None anticipated as part of the study itself. | DESNZ published its response to the digital spine study in August 2024: https://www.gov.uk/government/publications/digitalising-the-energy-system | Work expected to continue under Data Sharing Infrastructure work. | - | - | - | - | -
Digitalising the Energy System | Data Sharing Infrastructure | Introduction of a data sharing infrastructure, which is a minimum set of responsibilities, governance, functions and processes for secure, interoperable data sharing across the energy system. This activity covers the DSI Pilot, DSI MVP and Ofgem Guidance. | TBC | TBC | TBC | TBC | TBC | TBC | Risks and issues to be confirmed by Workgroup. | DESNZ published its response to the digital spine study in August 2024, which included commitments for the data sharing infrastructure: https://www.gov.uk/government/publications/digitalising-the-energy-system Ofgem published its decision on the definition of ESD and DBP Guidance in October 2024: https://www.ofgem.gov.uk/decision/decision-definition-energy-system-data-data-best-practice-guidance | Related Ofgem programme’s name has changed from Energy Data and Digitalisation to Energy System Digitalisation. Ofgem's Energy System Digitalisation page is provided below: https://www.ofgem.gov.uk/energy-policy-and-regulation/policy-and-regulatory-programmes/energy-system-digitalisation Project information for NESO DSI Pilot / MVP: https://smarter.energynetworks.org/projects/nia2_ngeso081/ Project information for NESO DSI / SSEN-T Component: https://smarter.energynetworks.org/projects/nia_shet_0053/ | TBC | TBC | TBC | TBC | TBC | Related Ofgem programme’s name has changed from Energy Data and Digitalisation to Energy System Digitalisation. Ofgem's Energy System Digitalisation page is provided below: https://www.ofgem.gov.uk/energy-policy-and-regulation/policy-and-regulatory-programmes/energy-system-digitalisation Project information for NESO DSI Pilot / MVP: https://smarter.energynetworks.org/projects/nia2_ngeso081/ Project information for NESO DSI / SSEN-T Component: https://smarter.energynetworks.org/projects/nia_shet_0053/
Hydrogen Blending | Hydrogen Blending | The Government sees Hydrogen as a key support for the decarbonisation of the UK economy. In 2021, the UK government published its first Hydrogen Strategy, which aimed for 5GW of low carbon hydrogen production capacity by 2030 for use across the economy. Building on these proposals, the British Energy Security Strategy committed to doubling this 2030 hydrogen production capacity ambition to up to 10GW, with at least half coming from electrolytic production. The Government set out its decision to support the blending of up to 20% hydrogen by volume into the GB gas distribution networks in 2023. | TBC | TBC | TBC | TBC | TBC | TBC | Added by Workgroup - Detail to be confirmed | Added by Workgroup - Detail to be confirmed | Added by Workgroup - Detail to be confirmed | TBC | TBC | TBC | TBC | TBC

## Cross Code Change
Cross Code Change
Code | Change Number | Related Changes | Title | Proposer | Current Status | Next Stage | Key Date | Other Comments / Useful Context
UNC | 843 | IGT165 | Establishing the Independent Shrinkage Charge and the Independent Shrinkage Expert | OVO Energy | Allocated to Working Group | Report to Panel | 2024-03-20 | Jan 2025 Update: Joint Office has reached out to the IGT UNC Code Administrator at the request of the UNC0843 Workgroup. They have asked that we attend future meetings. Xoserve have asked that add UNC0843 to the December IGT UNC Workgroup Agenda and invite the Proposer. Feb 2025 Update: The Code Administrator attended the UNC0843 Workgroup on 22nd January 2025 and will continue to attend meetings until the UNC Workgroup has concluded its work. The Code Adminstrator reccomends that IGTs review the latest UNC Workgroup meeting documents to remain up to date on the development of UNC0843.
IGT UNC | 165 | UNC0843 | Establishing the Independent Shrinkage Charge and the Independent Shrinkage Expert | OVO Energy | Allocated to Working Group | Report to Panel | TBC | Feb 2025 Update: The IGT UNC CA has produced the first draft of Legal Text changes for IGT165, which have been consdered and reviewed by the IGT165 Proposer. The IGT UNC Workgroup will consider the IGT165 Legal Text changes at its meeting on 13th February 2025.
UNC | 854 | IGT UNC Mod expected | Revision of Virtual Last Resort User and Contingent Procurement of Supplier Demand Event Triggers | National Grid Transmission | Implemented | - | - | Jan 2025 Update: Implemented on 22nd May 2024. IGT UNC Workgroup have agreed that a change to the IGT UNC is required. Waiting on an IGT UNC Modification to be raised. Feb 2025 Update: The IGT UNC Code Administrator has met with Energy Assets to discuss raised the required equivilat Modification. The Proposer will be brining the equivilant Modification to Workgroup on 13th March 2025 for pre-Modification discussion before looking to formally raise the Modification ahead of the February Panel meeting on 28th March 2025.

## Milestone Timeline
IGT UNC Horizon Scanner Timeline
|  | 2024 | 2025 | [11 empty] | 2026
Category |  | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR
Code Reform | Code Consolidation (GNC)
| SDS | 2025 FEB: LINK, Respond by 28/03/25; 2025 APR: First SDS expected
| Code Governance | 2024 DEC: LINK, Respond by 30/01/25
| Pre-Consolidation Code Changes | 2025 FEB: LINK, Respond by 28/03/25
Xoserve | Project Trident | 2025 JUL: Completion of FBC and solution procurement expected
Service Line Review
Digitalising the Energy System | Digital Spine | 2025 JAN: Gov. to procure work for landscape assessment in 2024
| DSI (NESO Pilot) | 2025 APR: Virtual Energy System DSI Pilot expected to end in March
| DSI (NESO MVP) | 2025 APR: MVP Work expected to commence; 2025 NOV: MVP launch expected
| DSI (Ofgem Guidance) | 2024 DEC: Ofgem cons. on DSI governance expected; 2026 JAN: DSI progress updated expected in 2025
Cross Code Change | UNC0845 (Shrinkage Expert) | 2025 APR: Consultation expected
| IGT165 (Shrinkage Expert) | 2025 MAY: Consultation expected
UNC0854 Equivalent IGT Modification (Number TBC) | bar: 2025 FEB; 2025 AUG
C
P
W
W
W
P
P
C
C
C
W
IGT UNC WG Discussion - LINK
M
M
Activity TBC
W
W
P
C
W
E
Feb 17th - Preliminary SDS and Code Governance Arrangements Event - LINK
P
C
E
P
W
Pre-Modification
M
M
M
M

## Timeline key
Icon | Description
Consultation Confirmed
Consultation Unconfirmed
Release Confirmed
Release Unconfirmed
Event/Workgroup/Steering Group Confirmed
Event/Workgroup/Steering Group Unconfirmed
Publication Confirmed
Publication Unconfirmed
Milestone Confirmed
Milestone Unconfirmed
Solid Yellow/Grey | Work Ongoing
P
P
R
R
C
C
E
E
M
M
W
S
W
S

## Acronyms
Acronym | Defined Term
BEIS | Department for Business, Energy, and Industrial Strategy
BSC | Balancing and Settlement Code
CDSP | Central Data Services Provider
CMA | Competition and Markets Authority
CSS | Central Switching Service
CUSC | Connection and Use of System Code
DBP | Data Best Practice
DCUSA | Distribution Connection and Use of System Agreement
ECC | Electricity Commercial Code
ESD | Energy System Data
ETC | Electricity Technical Code
FBC | Full Business Case
GEMA | Gas and Electricity Markets Authority
GNC | Gas Network Code
IGT UNC | Independent Gas Transporters Uniform Network Code
ISOP | Independent System Operator and Planner
MVP | Minimum Viable product
NESO | National Energy System Operator. Named in the Energy Act 2023 as ISOP
NZIP | Government’s Net Zero Innovation Portfolio
REC | Retail Energy Code
SAF | Stakeholder Advisory Forum
SDS | Strategic Direction Statement, which will set out Ofgems vision for how the codes should devolve on an annual basis
SEC | Smart Energy Code
SOS | Secretary of State
SQSS | Security and Quality of Supply Standard
STC | System Operator Transmission Owner Code
UNC | Uniform Network Code