## Watch List
Correct as of 03/04/2025
Mod Ref |  | Modification Title | Proposing Organisation | Date Raised | Live/Closed | Category | Workgroup | Current Status | Next Stage | Key date* | Legal Text Provider | IGT UNC Workgroup Update / Current Status
0908 |  | Removal of DNO meter reading obligations resulting from non-provision of a Valid Meter Reading | Wales & West Utilities | 2025-03-07 | Live | Authority Decision | Distribution | Allocated to Workgroup | Report to Panel | 2025-09-18 |  | This Modification will remove the DNO obligation, in Transportation Principal Document section M 5.10, to obtain a meter reading (commonly called the “must read” obligation) following non-provision of a Valid Meter Reading by a Shipper. The UNC Panel indicated that there might be an impact on the IGT UNC. The Code Administrator will monitor the Modification until impacts are known.
0907 | S | Extension to current maintenance period | National Gas Transmission | 2025-02-06 | Live | Self-Governance | Transmission | Allocated to Workgroup | Report to Panel | 2025-09-18 |  | This Modification proposes to amend the current maintenance period from 01 April to 31 October to 01 March to 30 November. April UNC Workgroup meeting slides state that this Modification primarily relates to outages impacting industrial and power customers connected to the NTS which is notified under TPD. Unlikely to impact IGTs and the IGT UNC at this stage.
0896 |  | Reducing the current Code Cut-Off Date (Line in the Sand) from 3 to 4 years to 2 to 3 years | SEFE Energy | 2024-10-04 | Live | Modification | Distribution | Allocated to Workgroup | Report to Panel | 2025-05-15 |  | This Modification proposes to reduce the existing Code Cut-Off Date (Line in the Sand) from 3 to 4 years to 2 to 3 years. Impacts on IGTs expected as line in the sand applies to IGTs. Impact on IGT UNC Code TBC. Potential impact on Must Reads process, this will need to be assessed as the Modification develops. This Modification was amended on 28th October. 12th December 2024: WG noted that this Modification has been extended by 3 months 6th March 2025: Legal text shared on 24th February 2025. No impact on IGT UNC Code based on the Legal Drafting at this time. However, the CA will continue to monitor this Modification as the change to the definition of "Code Cut Off Date" in the UNC will impact IGTs as parties to that Code.
0890 |  | Update to AQ Correction Processes - Request for Adjustments (RFA) AQ Change | Centrica | 2024-08-06 | Live | Modification | Distribution | Allocated to Workgroup | Report to Panel | 2025-07-17 | 2025-03-20 | This Modification proposes to add a further ‘eligible cause’ to the Annual Quantity (AQ) amendment process within TPD G2.3.21. Potential impact on IGT Parties as a result of changes to AQ process. Currently no Code impact anticipated. 12th December 2024: WG indicated that Xoserve are currently looking into the most appropriate solution, with the next update expected at the January Distribution Workgroup. 6th March 2025: In November, the UNC Workgroup discussed whether an AQ could be automatically updated as part of the current RFA process, based on the Consumption Adjustment value. An Impact assessment was conducted by the CDSP to confirm that an Automatic AQ recalculation was possible. DNs were consulted to determine if Code would permit an AQ recalculation or if a Mod would be required to ensure clarity in Code. The findings and approach were brought back to Workgroup in January 2025 and the proposer and Workgroup participants agreed to update UNC0890 to reflect the new approach. The Modification was amended. 3rd April 2025: Modification amended and published on 18th March. Amended Modification will be considered at UNC Workgroup on 27th March.
0886 |  | Amend the Code Cut-Off Date to a Rolling 3-Year Period | SSE Energy Supply Limited | 2024-06-28 | Live | Modification | Distribution | Allocated to Workgroup | Report to Panel | 2025-05-15 |  | The purpose of the modification is to shorten the code cut-off date (or line in the sand) from a 3 to 4-year period to a monthly rolling 3-year period. As line in the sand also applies to IGTs this will likely have an impact on IGTs. Code impacts are not yet known. 12th December 2024: WG noted that this Modification has been extended by 3 months 6th March 2025: Last meeting held on 27th February, expecting a new ROM for the March meeting.
0876 | S | Updates to the Annual Quantity (AQ) amendment process. | SEFE Energy Limited | 2024-04-29 | Live | Self-Governance | Distribution | Allocated to Workgroup | Report to Panel | 2025-06-19 |  | This Modification proposes to make updates to the AQ amendment process within TPD G 2.3. Specifically adding clarity around the use of “eligible cause” G2.3.21 (b) (change in Consumer Plant), as well as ensuring a process for managing instances of misuse across all “eligible causes” where identified. It is not believed that the IGT UNC requires updating as a result of this Modification as it points to the UNC for this part of the code, however, the updates made to the AQ amendments process will apply to IGT sites as well as DNO sites. This modification was amended on 25th November 6th February 2025: The UNC Workgroup discussed the potential for cross-code impacts on the IGT UNC at the 23 January 2025 Workgroup meeting and determined that Modification 0876S will not result in the need for a Modification to the IGT UNC. The Modification currently seeks to make changes to TPD G2.3.21(c). Currently, IGT UNC Part CI6 already cross references G2.3 of the UNC. The text allows for G2.3 provisions to apply under the IGT UNC for the purposes of determining AQ. Therefore, any changes implemented to G2.3 will automatically apply under the IGT UNC without any need for an equivalent IGT UNC Modification. The Chair of the Distribution Workgroup reached out to the CA and informed them that the Workgroup wanted it highlighted that there will be impacts to IGTs as parties, even though there is no change to Code. The CA recommends that IGTs review the documents for this Modification. 3rd March 2025: Panel determined that this Modification should go back to Workgroup for 3 months, with the Workgroup Report back to Panel in June 2025.

## Watchlist (Closed) (hidden)
CLOSED LIST
Mod Ref |  | Modification Title | Proposing Organisation | Date Raised | Live/Closed | Category | Workgroup | Current Status | Next Stage | Key date* | Legal Text Provider | IGT UNC Workgroup Update / Current Status
0867 |  | Gas Demand Side Response (DSR) Aggregation Arrangements | National Gas Transmission | 2024-01-08 | Closed | Modification | Transmission | Withdrawn | End of process | 2024-05-01 | National Gas Transmission | They may require a consequent IGT mod if implemented.
0865 | S | Permitting DNOs to charge Shippers negative Supplier of Last Resort (SoLR) unit rates | Wales & West Utilities | 2023-12-05 | Closed | Self-Governance | Distribution | Implemented | Effective Date | 2024-03-08 |  | UNC TPD (Transportation Principal Document) Section Y part B only permits Distribution Network Operators (DNOs) to charge positive unit rates to Shippers, this modification permits negative rates.
0863 | S | Erroneous Transfers Exception Process | SEFE Energy Limited | 2023-10-26 | Closed | Modification | Distribution | Withdrawn | End of process | 2024-05-21 | 2023-11-16 | To provide a remedy for Erroneous Transfers that have failed to be progressed (exceptions) within a reasonable period to be proactively managed by the Central Data Services Provider (CDSP). Question to Workgroup - Should this be a REC modification?
0861 |  | Clarification of Provisions Regarding Utilisation of the System Without Holding System Capacity | National Gas Transmission | 2023-10-24 | Closed | Self-Governance | None | Implemented | Effective Date | 2024-04-16 |  | The purpose of this Modification is to acknowledge the extent of Transporters’ obligations to accept gas tendered for delivery to (or make gas available for offtake from) the System in the provisions that set out the charges payable where a User utilises the System without holding system capacity.
0859 | S | Reintroduction of the enhanced pressure service and increased MNEPOR for BBLC (as introduced by UNC0814) | National Gas Transmission | 2023-10-09 | Closed | Modification | Transmission | Implemented | Effective Date | 2024-04-19
0858 |  | Amendment to Network Entry Provision at Shell St Fergus Terminal | Shell | 2023-09-13 | Closed | Modification | None | Implemented | Effective Date | 2023-12-08 |  | This Modification will enable the current Wobbe Index upper limit that applies between National Grid and Shell at St Fergus to be increased on an enduring basis from 51.2 MJ/m3 to 51.4 MJ/m3.
0856 |  | Introduction of Trials for Non-Daily Metered (NDM) Demand Side Response (DSR) | National Gas Transmission | 2023-09-13 | Closed | Modification | None | Implemented | Effective Date | 2024-04-22 |  | Issued for a shortened 12 day consulation
0854 |  | Revision of Virtual Last Resort User and Contingent Procurement of Supplier Demand Event Triggers | National Gas Transmission | 2023-08-04 | Closed | Modification | Transmission | Implemented | End of process | 2024-05-22 | National Gas Transmission | The UNC Modification Panel has considered this new Modification, at their meeting on Thursday 17 August 2023 and highlighted that there is a potential IGT-UNC impact.
0853 |  | CDSP permissions to facilitate implementation of UNC0701. | Northern Gas Networks | 2023-07-27 | Closed | Self-Governance | Distribution | Implemented | Effective Date | 04/11/2023 in line with UNC701 | Northern Gas Networks | Modification 0701 (Aligning Capacity booking under the UNC and arrangements set out in relevant NExAs), is being implemented in November 2023, should Shippers not reduce capacity in line with the NExA agreement they will be in breach of Uniform Network Code at this time. This Modification gives permission for the CDSP to reduce the capacity to align with the NExA should the Shipper not do so. Also includes administrative change re use of acronym NExA. At August Panel it was determined that this Modification should proceed to Consultation.
0852 | S | Shipper notification in relation to option exercise for Customer Demand Side Response | SEFE Energy Limited | 2023-07-25 | Closed | Modification | Transmission | Rejected | End of process | 2024-04-29 | National Gas Transmission | To require National Gas to notify the relevant Shipper in the event that a Customer Demand Side Response option is exercised. At August Panel it was determined that this Modification be issued to Workgroup with a Report to be presented to the January 2024 Panel.
0850 |  | Amendments to Allocation of Unidentified Gas Expert (AUGE) arrangements to introduce a new Residual Upstream Contributor | SEFE Energy Limited | 2023-07-07 | Closed | Modification | Distribution | Withdrawn | End of process | 2023-12-11 | Cadent | This Modification proposes to amend the existing Allocation of Unidentified Gas arrangements to introduce a new Residual Upstream Contributor that will be the new daily balancing factor for Unidentified Gas. | 2
0841 |  | Introduction of cost efficiency and transparency requirements for the CDSP Budget, and revisions to DSC change processes | British Gas | 2023-03-06 | Closed | Modification | Governance | Implemented | End of process | 2024-06-03 | Cadent | The purpose of this Modification is to improve the ability of UNC Parties to fulfill their obligation jointly to control and govern the CDSP on an economic and efficient basis (under UNC General Terms, Section D, 1.4.4), through the introduction of explicit requirements for efficiency, greater transparency of the Budget and revised governance processes. The Modification Panel has considered the Alternative Modification above, at their meeting on Thursday 19 October 2023 and highlighted that there is a potential IGT-UNC impact.
0836 | A | Resolution of Missing Messages following Central Switching Service implementation and integration with REC Change R0067. | Cadent | 2023-02-06 | Closed | Self-Governance | Distribution | Implemented | Effective Date | 18/12/2023 in line with RC0067 | Cadent | This Modification clarifies treatment and activities necessary when the CSS Registration Effective from Date does not align to that recorded in the UK Link system due to the issue whereby systems that interface with the Central Switching Service (CSS) have not received expected messages because they have not been generated, or because of issues in transmission or receipt of the messages. At August Panel it was determined that this Modification should proceed to Consultation.
0831 | S | Allocation of LDZ UIG to Shippers (Class 3 and 4) Based on a Straight Throughput Method | Brook Green Trading | 2023-03-06 | Closed | Alternate Modification | Distribution | Rejected | End of process | 2024-02-06 | Cadent | The purpose of this Modification is to remove the current AUGE process and create a permanent weighting table that encourages movement to Daily Metering, reduces levels of UIG and discourages risk premiums for customers.
0831 | A | Allocation of LDZ UIG to Shippers Based on a Straight Throughput Method | SSE | 2022-11-08 | Closed | Modification | Distribution | Rejected | End of process | 2024-02-06 | Cadent | The purpose of this Modification is to change the method by which unidentified gas (UIG) is allocated to Shippers from the current AUGE table of weighting factors to a throughput or universal allocation model. At August 2023 panel it was voted for the Modification to be deferred to September's panel rather than issue for Consultation.
0825 |  | Removal of the remaining Retrospective Asset, Address and Supply Point (RAASP) elements of the Retrospective Adjustment arrangements put in place under Modification 0434 | EDF Energy | 2022-10-10 | Closed | Modification | Distribution | Implemented | End of process | 2023-12-15 | Cadent | Removal of the remaining Retrospective Asset, Address and Supply Point (RAASP) elements of the Retrospective Adjustment arrangements put in place under Modification 0434 | 2023-06-15 | 2023-07-06 | 2022-05-19
0816 |  | Update to AQ Correction Processes | E.ON Next | 2022-08-08 | Closed | Self-Governance | Distribution | Implemented | Effective Date | 2024-02-24 | Scotia Gas Networks | This Modification was raised to add two further ‘eligible clauses’ to the Annual Quantity (AQ) amendment process within TPD G2.3.21 and to prevent AQ amendments being processed where there is no change in value to the AQ.Settlement Performance Obligations and Transportation Costs for Vacant sites. Report due to be taken to Panel in May 2023. Will be fully implemented into the IGT UNC by UNC modification. However one reference is now incorrect in the IGT UNC and this will need to be corrected. In Part C I Section 6 the reference to 2.3.22 should now read 2.3.23.
0811 | S | Shipper Agreed Read (SAR) exceptions process | SEFE Energy Limited | 2022-06-23 | Closed | Self-Governance | Distribution | Implemented | Effective Date | 2024-02-24 | Wales & West Utilities | Any solution identified in the UNC that processes at Supply Point level will likely require a modification in the IGT UNC to effect the solution within the IGT UNC similarly. The FMR was presented to Panel on 19th January 2023 and the Panel determined that this Modification should be implemented on a date to be confirmed. Will be implemented in the IGT UNC by UNC drafting

## IGT UNC Equivalent
Correct as of 03/04/2025
Mod Ref | Modification Title | Proposing Organisation | Date Raised | Current UNC Status | Next UNC Stage | Key date | IGT UNC Mod Ref | Current IGT UNC Status | Next IGT UNC Stage | Key date | IGT UNC Workgroup Summary
0899 | To ensure the suite of Network Exit Agreements (NExA) Modifications has been implemented, taking into account the changes introduced by 0804 (REC 3.0) |  |  |  | Awaiting implementation | 2025-02-20 | IGT175 | Allocated to Workgroup | Report to Panel | 2025-04-25 | This Self-Governance Modification seeks to make corrections needed to numbering, and other minor typographical errors, to allow the complete and accurate implementation of Modification 0701- Aligning Capacity booking under the UNC and arrangements set out in relevant NExAs, Modification 0770 - Amendments to legal text numbering for UNC Modification 0701 and Modification 0853 - CDSP permissions to facilitate implementation of UNC0701, taking into account changes introduced in the interim by Modification 0804 - Consequential UNC changes for Switching SCR (REC 3.0).y Capacity. Changes expected to the IGT UNC. 6th February 2025: Xoserve confirmed that UNC0899S will not lead to misalignment with IGT UNC. BUUK also added that the response to the action provided by Xoserve confirming the amendments to the IGT UNC are purely housekeeping and there are no changes to CDSP’s obligations. Xoserve clarified that the changes needed in IGT UNC as a result of this Modification add further clarity to the wording as opposed to changing it.Consultation for this Modification is open to responses until 5pm 06 February 2025. 6th March 2025: An IGT has submitted a draft proposal form. We are expecting the IGT Modification to be raised ahead of the March IGT UNC Panel meeting. 3rd April 2025: IGT175 was raised by BUUK on 10th March 2025 .This Modification will be presented to the IGT UNC Panel on 28th March and will be considered by the IGT UNC Workgroup at its April meeting.
0887 | Facilitating Bi-Directional Connections Between IGT Pipelines and the NTS | National Gas Transmission | 2024-07-18 |  | Report to Panel | 2025-04-17 | IGT176 | Allocated to Workgroup | Report to Panel | 2025-06-27 | This Modification was raised as an alternative to 0871. However, the UNC Panel determined that it was an extension of the 0871 solution and voted that the Modification should be separate and not an alternative. This Modification is likely to impact IGTs and the IGT UNC and seeks to clarify the treatment of energy entering the NTS after entering an IGT network. 6th February 2025: The CA recommends that IGTs review the legal text changes with regards to this Modification. Changes to TPD and the IGTAD were presented at the 9th January 2025 meeting for UNC0887, with the changes to the IGTAD being particularly extensive. There was also an amended ROM presented at the WG meeting, which contained more detail about the requirements for central systems. This Modification was amended on 30th January 2025. 6th March 2025: A Sponsor has come forward for this Modification and a draft Proposal Form has been submitted. We are expecting the Modification Proposal to be raised ahead of the March IGT UNC Panel meeting. 3rd April 2025: IGT176 was raised by CNG on 19th March 2025 .This Modification will be presented to the IGT UNC Panel on 28th March and will be considered by the IGT UNC Workgroup at its April meeting.
0884 | Extending the PC4 Read Submission Window |  |  |  | Report to Panel | 2025-04-17 | TBC | Awaiting IGT Party Sponson | Proposal Submitted | TBC | Under UNC TPD, M, 5.9.4, Shippers have 25 Supply Point Systems Business Days (SPSBD) after the read date to submit a read for settlement. Where there's an issue preventing the read from being validated, and that issue is not resolvable within the 25 SPSBD timeframe, the read becomes unusable. This is problematic for meter reads that are hard to retrieve. This Modification seeks to extend the window beyond 25 SPSBDs. This modification was amended on 22nd October Changes under UNC Mod to TPD, M, 5.9.4 will automatically apply under the IGT UNC, However no changes are made to the IGT UNC Code to enable the UNC Modification. 12th December 2024: WG discussions over how this Modification will impact the current IGT UNC Must Read and PC4 Read Submission Window processes. Xoserve and Centrica took an action to look into this Modification further. 6th February 2025: The CA met with the UNC Modification Proposer at the end of December. The Proposer is aware of the possible impacts to the IGT UNC and that a change to the submission window may impact Must Reads for IGTS, which have specific timescales within Code. 6th March 2025: The CA has written out to IGT UNC Parties to advise of the impacts identified by the IGT UNC Workgroup. This was also forwarded to the INA and brought up at their recent meeting. 3rd April 2025: A sponsor has come forward for the IGT UNC Modification. They have indicated that they plan to submit the Proposal form ahead of the April IGT UNC Panel meeting.
0881 | Review and consolidation of UNC Transition Document TDIIC - Transitional Rules | National Gas Transmission | 2024-06-07 | Implemented | Effective date | 2025-01-15 | IGT175 | Allocated to Workgroup | Report to Panel | 2025-04-25 | This Modification seeks to review and remove obsolete transitional rules within UNC TDIIC Transitional Rules and introduce additional steps within TDI – General to enable easier reviewing and removal of expired Transitional Rules in the future. 6th November 2024: One change to the IGT UNC will be required as a result of this Modification. a Reference to TDIIC 1.3.8 will need to be removed as it is being removed under 0881. 5th December 2024: Final Modification Report to be presented to UNC Panel at its December meeting. A Change is required to the IGT UNC to remove TDIIC 1.3.8 reference. 6th February 2025: This Modification was implemented with effect from 15th January 2025. A Change is still required to the IGT UNC to remove TDIIC 1.3.8 reference as this clause has been removed under this Modification. 3rd April 2025: BUUK raised IGT175 on 10th March 2025. This Modification will make the nessessary updates to the IGT UNC as a result of UNC0881.
0854 | Revision of Virtual Last Resort User and Contingent Procurement of Supplier Demand Event Triggers | National Gas Transmission | 2023-08-04 | Implemented | Effective date | 2024-05-22 | TBC | Sponsor found, awaiting Proposal Form submission | TBC | TBC | UNC legal text will impact on the IGT UNC. Mod mitigates DN risk. Similar risk may be identified for IGTs which would require an IGT UNC mod for the same purpose. It is not believed that the UNC legal text will impact the IGT UNC, however, the Code Administrator will review the UNC legal text to understand if there are any impacts. IGT's will need to decide if they want a similar mod to cover off their own risk if they believe that they have a risk to themselves. The CDSP confirmed that the solution for 0854 was going to apply to both GT and IGT sites, it will apply to any sites that are owned by the sanction shipper, slash user premises termination user. The CA reviewed the modification and, along with the WG, determined that a Modification to the IGT UNC is required. 6th November 2024: This Modification was implemented on 22nd May 2024. 5th December 2025: TL followed up with Energy Assets, who still plan to raise the Modification. TL and the Proposer will work together in the new year to get the Modification raised. Currently aiming for February 2025. 20th December 2025: IGT UNC Modification Proposal expected at February Workgroup for pre-Modification discussion. 6th February 2025: IGT UNC Modification Proposal was expected for pre-Modification discussion at February WG. Due to extenuating circumstance this Modification will now be discussed at the March Workgroup meeting. 6th March 2025: This Modification has been deferred to the next IGT UNC Workgroup meeting. 3rd April 2025: A sponsor has come forward for the IGT UNC Modification. They have indicated that they plan to submit the Proposal form ahead of the April IGT UNC Panel meeting.
0843 | Establishing the Independent Shrinkage Charge and the Independent Shrinkage Expert | OVO Energy | 2023-04-06 | Allocated to Workgroup | Report to Panel | 2025-05-15 | IGT165 | Allocated to Workgroup | Report to Panel | TBC | 5th December 2025: UNC0843 to be discuss at the December Workstream meeting. 20th December 2025: UNC0843 was discussed at December Workstream. The Proposer and the CA will be working on legal drafting for IGT165 in the new year with the aim of brining the drafting to the February Workstream meeting. The next UNC0843 meeting is scheduled for 22nd January 2025. 6th February 2025: Legal Drafting for IGT165 to be considered at February WG. 6th March 2025: The updated legal text and draft Workgroup Report for IGT165 will be considered by the IGT UNC Workgroup. Next steps include: - Final review of version the Modification - Final Review of the updated Legal Text with the Legal Text being provided at least 5 days ahead of the next meeting - Review of the ROM - Finalise Workgroup Report 3rd April 2025: The final version of the IGT165 Legal Text and Workgroup Report will be provided to parties ahead of the April 2025 Workgroup meeting. The Workgroup Report was due to be presented to the IGT UNC Panel at its April meeting. However, the UNC0843 Workgroup Report is now targeted at the May UNC meeting. Therefore, the Code Administrator recommends that the Workgroup Report for IGT165 be presented to the IGT UNC Panel in May as well.

## Live Review Groups
Correct as of 03/04/2025
Mod Ref |  | Modification Title | Proposing Organisation | Date Raised | Category | Workgroup | Current Status | Next Stage | Key date* | IGT UNC Workgroup Summary
0879 | R | Review of current Supply Meter Point Classes (Class 1,2,3 and 4). | Centrica | 2024-05-24 | Live | Distribution | Allocated to Workgroup | Report to Panel | 2025-07-17 | 6th November 2024: - The most recent UNC Workgroup Meeting was held on 24th October 2024. The Workgroup briefly discussed the scope of the solution, with the forward work plan deferred. The next meeting is planned for 15th November 2024. 5th December 2024: 4 week consultation completed for this Review. 9 responses were received, which were discussed at the 15th November 2024 meeting. Topic for discussion have been identified based on responses. A number of confidential responses were provided. The CA recommends parties review the documents from the 15th November 2024 meeting. Next meeting is scheduled for 30th January 2025. 6th March 2025: The UNC Workgroup considered classes 2 and 3 in the February meeting. CDSP to revisit Class 2/3 and introduce Class 4
0849 | R | Commercial Framework Review to Enable Hydrogen Blending | National Gas Transmission | 2023-05-09 | Live | Other | Allocated to Workgroup | Report to Panel | 2025-10-16 | To review the market principles and existing commercial framework in order to assess their compatibility with blending hydrogen into the networks and explore the required amendments where necessary. Ensuring the amended regime is simple and easy to implement whilst also remaining adaptable and consistent with relevant obligations. KPMG will be providing project management support for the project. 6th November 2024: The last 3 UNC Workgroup meetings have been cancelled. The next scheduled meeting for this Review is on 13th December 2024. 6th February 2025: The December UNC Workgroup meeting went ahead as scheduled, we recommend IGTs remain informed as the outputs of this Review will likely impact the IGT UNC. 6th March 2025: The UNC Workgroup considered the Design Stage process, Component Definitions, Locations, Capacity Terms, and a Request for Information. They considered the feedback provided by Workgroup and to update the presentation pack to include the detailed definitions requested in respect of ‘capacity’ for further consideration by the Workgroup. The next meeting will continue to cover the topic of Capacity and Connections.

## UNC Modification IAs
IGT UNC Impact Assessments (IAs)
Correct as of 03/04/2025
Mod Ref |  | Modification Title | Proposing Organisation | IA Date | Notes / Summary of IA Discussions | IA Outcome | Modification Required | Modification Agreement Date | IGT UNC Modification Proposer | Additional Comments / Updates
0899 | S | To ensure the suite of Network Exit Agreements (NExA) Modifications has been implemented, taking into account the changes introduced by 0804 | Northern Gas Networks | TBC | This Self-Governance Modification seeks to make corrections needed to numbering, and other minor typographical errors, to allow the complete and accurate implementation of Modification 0701- Aligning Capacity booking under the UNC and arrangements set out in relevant NExAs, Modification 0770 - Amendments to legal text numbering for UNC Modification 0701 and Modification 0853 - CDSP permissions to facilitate implementation of UNC0701, taking into account changes introduced in the interim by Modification 0804 - Consequential UNC changes for Switching SCR (REC 3.0).y Capacity. Discussion at November 2024 Workgroup indicated that changes are expected to the IGT UNC | TBC | TBC | TBC | TBC
0896 |  | Reducing the current Code Cut-Off Date (Line in the Sand) from 3 to 4 years to 2 to 3 years | SEFE Energy | 2024-12-12 | This Modification proposes to reduce the existing Code Cut-Off Date (Line in the Sand) from 3 to 4 years to 2 to 3 years. Impacts on IGTs expected as line in the sand applies to IGTs. Impact on IGT UNC Code TBC. Potential impact on Must Reads process, this will need to be assessed as the Modification develops. | TBC | TBC | TBC | TBC
0890 |  | Update to AQ Correction Processes - Request for Adjustments (RFA) AQ Change | Centrica | TBC | This Modification proposes to add a further ‘eligible cause’ to the Annual Quantity (AQ) amendment process within TPD G2.3.21. Potential impact on IGT UNC Parties as a result of changes to AQ process. Currently no Code impact anticipated. | TBC | TBC | TBC | TBC
0887 |  | Facilitating Bi-Directional Connections Between IGT Pipelines and the NTS | National Gas Transmission | TBC | This Modification was raised as an alternative to 0871. However, the UNC Panel determined that it was an extension of the 0871 solution and voted that the Modification should be separate and not an alternative. This Modification is likely to impact IGTs and the IGT UNC and seeks to clarify the treatment of energy entering the NTS after entering an IGT network. 6th February 2025: The CA recommends that IGTs review the legal text changes with regards to this Modification. Changes to TPD and the IGTAD were presented at the 9th January 2025 meeting for UNC0887, with the changes to the IGTAD being particularly extensive. There was also an amended ROM presented at the WG meeting, which contained more detail about the requirements for central systems. | TBC | TBC | TBC | TBC
0886 |  | Amend the Code Cut-Off Date to a Rolling 3-Year Period | SSE Energy Supply Limited | TBC | The purpose of the modification is to shorten the code cut-off date (or line in the sand) from a 3 to 4-year period to a monthly rolling 3-year period. As line in the sand also applies to IGTs this will likely have an impact on IGTs. Code impacts are not yet known. | TBC | TBC | TBC | TBC
0884 |  | Extending the PC4 Read Submission Window | OVO Energy | TBC | Under UNC TPD, in Profile Class (PC) 4, M, 5.9.4, Shippers have 25 Supply Point System Business Days after the read date to submit a meter read for Settlement. Where there is an issue preventing the read from being validated, and that issue is not resolvable within the 25 Day timeframe, the read becomes unusable. This is problematic for meter reads that are hard to retrieve from the meter. For example, it might take several months to obtain another reading from the meter. This Modification is seeking to extend the submission window for more complex reads. Changes under UNC Mod to TPD, M, 5.9.4 will automatically apply under the IGT UNC, However no changes are made to the IGT UNC Code to enable the UNC Modification. | TBC | TBC | TBC | TBC
0881 |  | Review and consolidation of UNC Transition Document TDIIC - Transitional Rules | National Gas Transmission | 2024-12-12 | This Modification seeks to review and remove obsolete transitional rules within UNC TDIIC Transitional Rules and introduce additional steps within TDI – General to enable easier reviewing and removal of expired Transitional Rules in the future. One change to the IGT UNC will be required as a result of this Modification. a Reference to TDIIC 1.3.8 will need to be removed as it is being removed under 0881. | Code changes required | Yes | TBC | TBC
0875 | S | Minor amendment to the Vacant Site exit process & 0819 Legal Text re-numbering | Centrica | 2024-12-12 | CDSP had viewed the initial legal text for 0875 and did not think there are any impacts to the IGT UNC because the relevant sections of the IGT UNC text, Sections 6 and 21, both already refer to the relevant sections of the UNC, so when these UNC sections are updated through this new modification, the updates will automatically apply to IGT sites. It was clarified that there is an impact from UNC 0875 on IGT sites, but not the IGT code. No IGT UNC Code changes required but there are changes to sections referenced in the IGT UNC which will automatically apply under the IGT UNC once implemented. (G2.3) | TBC | TBC | TBC | TBC
0874 | S | Amendments to UNC to align with Gas Demand Forecasting Methodology | National Gas Transmission | 2024-12-12 | Approved waiting implementation. No IGT UNC Code impact, though changes have been made to UNC Section C and H, which are referenced within the IGT UNC, in some instances in whole and so changes might automatically apply under the IGT UNC. | TBC | TBC | TBC | TBC

## Closed Impact Assessments
IGT UNC Impact Assessments (IAs)
Correct as of 03/04/2025
Mod Ref |  | Modification Title | Proposing Organisation | IA Date | Notes / Summary of IA Discussions | IA Outcome | Modification Required | Modification Agreement Date | IGT UNC Modification Proposer | Additional Comments / Updates
0904 | R | Review of the profiling arrangements with respect to LDZ Shrinkage Quantity | Cadent | 2025-02-06 | No IGT UNC impacts expected as the Review only applies to LDZ Shrinkage arrangements – NTS Shrinkage (dealt with under a different process under code and licence) and any exploration of IGT shrinkage (exists as a concept in IGTAD but is not currently calculated or purchased by IGTs) do not form part of this review. Recommend removing from the watch list. | No code change required | TBC | TBC | TBC
0902 | R | EU Capacity Allocation Mechanism Network Code Review | National Gas Transmission | 2025-02-06 | No IGT UNC impacts expected, recommend removing from the watch list. | No code change required | TBC | TBC | TBC
0901 | R | Review of the arrangements for reservation of NTS Capacity | National Gas Transmission | 2025-02-06 | No IGT UNC impacts expected, recommend removing from the watch list. | No code change required | TBC | TBC | TBC
0898 | S | Amendment to Gas Quality NTS Entry Specification at the St Fergus Shell System Entry Point | Shell Energy Europe Limited | 2024-12-12 | This enabling Modification will facilitate a change to the current contractual carbon dioxide entry limit at the St Fergus Shell entry Point, through the Modification of a network entry provision contained within the Network Entry Agreement (NEA) between National Gas and Shell UK in respect of the St Fergus Shell Terminal. No impact anticipated for IGT UNC. | No code change required | - | - | -
0897 | S | Removal of Non-Obligated Entry Capacity from Capacity Neutrality | SSE | 2025-02-06 | Implementation of the Proposal would remove the Non-Obligated Entry Capacity Revenues from Capacity Neutrality Revenues. This would reduce the revenues flowing into Capacity Neutrality Revenues which are redistributed to Users in proportion to their Firm Capacity holdings as well as reducing transportation charges paid by Users. No impacts on the IGT UNC expected as a result of this Modification. Recommend removing from watch list. | No code change required | - | - | -
0895 | S | Replacing ‘Energy Networks Association’ with another publishing method | Wales & West Utilities | 2024-12-12 | The purpose of this Modification is to update the Gas Distribution Networks (GDNs) UNC obligation to publish two engineering documents on the ENA website to another method. This is necessary following the GDNs collective decision to leave the ENA and to ensure compliance with the UNC. No impact anticipated for IGT UNC. | No code change required | - | - | -
0894 |  | Facilitating Biomethane entry into the GDN by exporting methane from the GDN into the NTS via Compression | Cadent | 2024-12-12 | This Modification seeks to introduce new criteria of Offtake where gas flows into the National Transmission System (NTS) from the Gas Distribution Network (GDN), and to clarify the treatment of the associated energy. This Modification was amended on 26th September. Amendments are due to be considered by Workgroup in October. No impact anticipated for IGT UNC. | No code change required | - | - | -
0893 |  | Reintroduce NTS Capacity Surrender text and update TPD B2.12 | National Gas Transmission | 2024-12-12 | The title of TPD B2.11 (Surrender of NTS Entry Capacity) was mistakenly changed and two clauses under 2.11 were removed in error due to what appears to be an issue with the implementation of a Modification. This Modification seeks to reintroduce the original text that was erroneously removed and implement the changes contained within Modification 0796 as intended. No impact anticipated for IGT UNC. | No code change required | - | - | -
0892 |  | Update incorrect NTS Entry Capacity paragraph references and reintroduce Daily Auctions to Entry Overrun Charges | National Gas Transmission | 2024-12-12 | The purpose of this Modification is to reintroduce reference to Daily NTS Entry Capacity within the entry Overrun Charges section of the UNC and update incorrect paragraph references within TPD B section 2 - NTS Entry Capacity. Consideration by Panel deferred to November 2024. No impact anticipated for IGT UNC. | No code change required | - | - | -
0891 |  | Reintroduction of the enhanced pressure service and increased MNEPOR for BBLC (reintroduced by UNC0589 and introduced by UNC0814) | National Gas Transmission | 2024-12-12 | Panel recommended approval to the Authority No impact anticipated for IGT UNC. | No code change required | - | - | -
0872 | S | Single-sided Nominations for clearing houses of gas exchanges | European Commodity Clearing AG | 2024-12-12 | No anticipated impact on IGT UNC, to be closed. | No code change required | - | - | -
0870 |  | Amendments to Wobbe Index and Calorific Value Lower Limits at NTS System National Transmission System (NTS) Entry Points. | National Gas Transmission | 2024-12-12 | No anticipated impact on IGT UNC, to be closed. | No code change required | - | - | -
0868 |  | Gas Demand Side Response (DSR) Aggregation Arrangements | SEFE Energy Limited | 2024-12-12 | No anticipated impact on IGT UNC, to be closed. | No code change required | - | - | -
0864 |  | Update of UNC Code Communication Methods | National Gas Transmission | 2024-12-12 | No anticipated impact on IGT UNC, to be closed. Should be noted that an independent IGT UNC Modification has been raised to make simular changes but this is stand alone. | No code change required | - | - | -
0880 |  | Amendment to Wobbe Index upper limit in the Network Entry Agreement at the York Entry Point | Centrica | 2024-12-12 | The Modification will enable the Wobbe Index upper limit set out in the York Network Entry Agreement between National Gas and Centrica Energy Storage to be increased from 51.2 MJ/m3 to 51.4 MJ/m3. Not expected to impact the IGT UNC. | No code change required | - | - | -
0876 | S | Updates to the Annual Quantity (AQ) amendment process. | SEFE Energy Limited | 2024-12-12 | It is not believed that the IGT UNC requires updating as a result of this Modification as it points to the UNC for this part of the code, however, the updates made to the AQ amendments process will apply to IGT sites as well as DNO sites. | No code change required | - | - | -
0883 |  | Update to the Annual Quantity (AQ) amendment process for- Erroneous Domestic AQs | Centrica | - | This Modification has been withdrawn. | - | - | - | -
0882 |  | Transparency of non-standard Gas Quality parameters at new entry connections to the NTS | National Gas Transmission | 2024-12-12 | This Modification seeks to enable greater transparency where a new entry connection to the National Transmission System (NTS) requests a “non-standard” gas quality specification, outside of the published NTS specification. This is to be more consistent with the rules for consultation at existing sites, whilst not impacting the connection process timelines adversely. No expected impact to IGT UNC. This Modification was amended on 18th October, with updated business rules and published legal text | No code change required | - | - | -
0885 |  | Amendment to Gas Quality NTS Entry Specification at the St Fergus SAGE System Entry Point | SAGE North Sea Limited | 2024-12-12 | This enabling Modification will facilitate a change to the current contractual oxygen limit at the St Fergus SAGE System Entry Point, through modification of a network entry provision contained within the Network Entry Agreement (NEA) between National Grid Gas plc and SAGE North Sea Limited (SNSL) in respect of the St Fergus SAGE Sub-Terminal. No impact anticipated for IGT UNC. | No code change required | - | - | -
0889 |  | Clarifying Inclusion of the Reserve Price in the System Entry Overrun Charge | National Gas Transmission | 2024-12-12 | This Modification will introduce an explicit reference to the Reserve Price within TPD B2.13.3 the System Entry Overrun Chare to clarify the process. This modification was amended on 30th October No expected impact on the IGT UNC. | No code change required | - | - | -
0888 |  | Correction to the Assessment Period for Demand Side Response (DSR) Option Offers | National Gas Transmission | 2024-12-12 | This Modification seeks to correct drafting errors in Modification 0866S ‘Amendments to Demand Side Response (DSR) Arrangements in respect of National Gas Transmission’s (NGT’s) assessment period for DSR Option Offers. No expected impact on the IGT UNC. | No code change required | - | - | -
0863 | S | Erroneous Transfers Exception Process | SEFE Energy Limited | 2024-03-14 | Indications from the Proposer that the mod will be raised in the REC. Mod not yet withdrawn. This Mod is still on hold in the UNC until further notice. | Withdrawn | - | - | - | -
0865 |  | Permitting DNOs to charge Shippers negative Supplier of Last Resort (SoLR) unit rates | Wales & West Utilities | 2024-03-14 | IGT sites included through UNC governance and not at supply point level. UNC0865 has now been implemented. The Workgroup doesn't believe that there is any impact. | No Impact | - | - | - | -
0856 |  | Introduction of Trials for Non-Daily Metered (NDM) Demand Side Response (DSR) | National Gas Transmission | - | IGT sites are expected to be included in the trials. Sent out for shortened consultation. Panel did not recommend implementation. Gone to Ofgem for decision. Proposer have decided to cease the trials so no IGT Mod required at this time. | No Impact | - | - | - | -
0855 |  | Settlement Adjustments for Supply Point Meter Points impacted by the Central Switching System P1 Incident. | SEFE Energy Limited | - | See UNC 0836. Modification IGT171 has now been raised. | Code & Party Impact | Yes | - | SEFE | Modification IGT171 has now been raised.
0853 |  | CDSP Permissions to facilitate implementation of UNC0701. | Northern Gas Networks | 2023-08-10 | The IGT Workgroup, at it's August meeting agreed that an IGT Modification would be required to cover the changes from UNC0701 and UNC0853 and to allow IGT's to manage the NExA implications. A proposer volunteered to sponsor this Modification and will work with the CA to raise and develop this. IGT169 has now been raised. | Code & Party Impact | Yes | - | MUA | Legal drafting in the IGT UNC needed in response to the implementation of UNC 0701 and the secondary intention of UNC0853 to allow the CDSP to validate using the relevant information
0852 |  | Shipper notification in relation to option exercise for Customer Demand Side Response | SEFE Energy Limited | 2023-08-10 | The section of the legal text added by the proposer in relation to the Shipper Notification would be encompassed in the IGT UNC by the legal text in IGT167. | Code & Party Impact | Yes | - | - | encompassed in the IGT UNC by the legal text in IGT167.
0850 |  | Amendments to Allocation of Unidentified Gas Expert (AUGE) arrangements to introduce a new Residual Upstream Contributor | SEFE Energy Limited | 2023-08-10 | Modification is at early stages, it has been to Panel and assigned to Workgroup. There were some questions raised on the IGT side which the proposer would take away and review. Proposer to attend September IGT Workgroup. This has now been withdrawn by the proposer. | No Impact | - | - | - | -
0845 |  | Enhancements to Demand Side Response (DSR) Arrangements including a D-5 Product | National Gas Transmission | 2023-07-13 | This modification is still under development and an equivalent mod IGT167 has been raised in the IGT UNC. | Code & Party Impact | Yes | - | BUUK
0844 |  | Enabling Direct Contractual Arrangements with Consumers for Demand Side Response | National Gas Transmission | 2023-07-13 | The IGTs have not been marked as an impacted group. The intention is for the modification to work on IGT Sites. This modification is still under development and an equivalent mod IGT167 has been raised in the IGT UNC. | Code & Party Impact | Yes |  | BUUK
0843 |  | Establishing the Independent Shrinkage Charge and the Independent Shrinkage Expert | OVO Energy | 2023-06-08 | WG initially considered the Modification during April 2023 meeting. The Proposer has indicated that they are happy to raise a Modification should there be an IGT/IGT UNC impact. The need for a Modification is dependant on how the UNC Mod Proposer sees Shrinkage Expert Role impacting IGTs/IGT UNC. This modification is still under development and an equivalent mod IGT165 has been raised in the IGT UNC. | Code & Party Impact | Yes | - | OVO | Proposer of UNC 0843 has indicated that they are keen to have the same obligations as the UNC with regards to Shrinkage. The UNC Modification Proposer has indicated that they are willing to raise a Modification to enable this. IGT UNC Modification IGT 165 raised
0842 |  | Gas Entry onto the Total system via an Independent Gas Transporter | SGN | 2023-07-13 | WG initially considered the Modification during May 2023 meeting. The UNC Modification Proposer and the Proposer of 0808 will discuss offline and engage with IGTs. Likely an impact but further information needed, which will be considered at the June 2023 meeting. CDSP advised that that they would look to consult IGT's on this Modification. IGT172 has now been raised. | Code & Party Impact | Yes | 2203-06-01 | Barrow Shipping | The Legal Draft provider for the UNC mod believes that title for the gas needs to be 'handed off' between the two codes. This will likely require an amendment to Section J of the IGT UNC IGT 172 has been raised
0841 | A | Introduction of cost efficiency and transparency requirements for the CDSP Budget, and revisions to DSC change processes | British Gas | 2023-11-10 | Cross-code implications anticipated as all parties of the IGT UNC are also parties in the DSC. 0841A has now been withdrawn. 0841 has just gone out for consultation - due back 7th March 2024. No IGT impacts identified. | No Impact | - | -
0836 | S | Resolution of Missing Messages following Central Switching Service implementation and integration with REC Change R0067. | Cadent | 2023-08-10 | The implications of this modification and related mod UNC0855 were discussed at the August Workgroup meeting. It was believed that the two UNC Modifications would require two equivalent IGT UNC Modifications. The implications of both UNC Mods would need to be fully understood by IGT UNC parties. The legal drafting for UNC0836 indicates that relatively small changes to the IGT UNC will be required. Specifically TPD Section G 5.9 and 5.18 will need to be referenced in the IGT UNC. UNC0836 was implemented 18/12/23. Modification IGT170 raised. | Code & Party Impact | Yes | 2023-08-10 | SEFE | Need to add Section G 5.9 and Section M5.18 of TPD into the IGT UNC so a modification will be required
0833 |  | Enabling Demand Side Response (DSR) Market Offers to be made by Non-Trading System Transactions | National Grid NTS | 2023-08-10 | The IGT UNC Panel, at its September meeting, agreed that a Modification is also needed to the IGT UNC as the Code Administrator has had confirmation from Xoserve that there are infact IGT sites on the system now that meet the eligibility criteria of the Modification. A sponsor for this Modification has approach the Code Administrator. We will continue to work with them in the new year to develop the nessessary changes to the IGT UNC. This modification will take into account 0822, 0833 and any other related DSR Modifications raised under the UNC. IGT167 Modification now been raised by BUUK and is out for consultation and due to go to an Extraordinary Panel on 17th August 2023. | Code & Party Impact | Yes | 2022-09-23 | Jenny Rawlinson, BUUK | Legal Drafting for the UNC modification removes / amends parts of TPD Section M 4. The IGT UNC points at the entirety of Section M 4, so the mod will be implemented into the IGT UNC.
0825 |  | Removal of remaining Retrospective Asset, Address and Supply Point (RAASP) elements of the Retrospective Adjustment Arrangements put in place under Modification 0434. | - | 2023-08-10 | At the May 2023 Workgroup it was established that an IGT Modification was not required. However, Legal text to be reviewed by Code Administrator. The Workgroup considered the impact of UNC0825 on the IGT UNC. Following discussion, it was widely agreed that no equivalent IGT UNC Modification would be required, as the relevant references to the UNC would still be accurate in the event that UNC0825 was implemented. Workgroup confirmed that this impacts the IGT sites but it doesn't need the IGT equivalent as there was never an original IGT Modification and this reverses out what the updated Retro was going to put in. Due to go to Panel and then consultation. Need to monitor. | No Impact | - | - | - | -
0808 |  | Reverse Compression | Barrow Shipping Limited | 2023-08-10 | WG considered the Modification following presentation from the Proposer. The WG agreed that based on the information provided there would not be an impact on the IGT UNC and therefore an IGT UNC Modification was not seen as being needed at this time. Still monitoring and seeking information as to whether there will be any impacts. | No Impact | - | - | -