## Introduction
IGT UNC Horizon Scanner
Date | 2025-07-03
Version | v1.7
Purpose | This document provides visibility of IGT UNC impacting industry activities, as well as the progression of Cross Code impacting Modifications. This document is owned by the IGT UNC Workgroup and is refreshed approximately monthly. Please refer to the IGT UNC Horizon Scanner page of the IGT UNC website for the most up to date version.
Contact | If you have any queries or comments about this Horizon Scanner, please contact the IGT UNC Code Administrator via email, IGTUNC@gemserv.com.
Uplift History | Reason for change | Date
v0.1 | Initial draft for Workgroup consideration | 2024-11-07
v1.0 | Uplift to approved working document | 2024-12-05

## Horizon Scanner
IGT UNC Horizon Scanner
|  |  | IMPACTS | [8 empty] | INDUSTRY CHANGE
Category | Activity | Description / Scope | IGT UNC | UNC | Other Codes | IGT | Shipper | Other Party | Risks / Issues | Current Status | Future Milestones / Key Dates | IGT Changes | UNC Changes | Other Code Changes | Central System Changes | Licences | Other Comments / Useful Context
Code Reform | Code Consolidation (GNC) | Introduction of GNC, which will involve the merging of IGT UNC and UNC. Designation of changes ahead of consolidation is expected. Further information on this will be noted when it is avaiable. | Yes | Yes | CUSC DCUSA SQSS STC | Yes | Yes | All parties to impacted Codes | Introduction of inaccuracies, short notice changes, lack of party engagement. | Ofgem work is ongoing. Ofgem issued its second consultation on the implementation of Energy Code Reform on 3rd April 2025, which closed on 29th May. This consultation set out Ofgems proposals on a range of policy areas on how code governance reform would be implemented in practice, including sections on: the code modification process Stakeholder Advisory forums (SAFs) cross-cutting consequential code changes cost recovery for the BSC and REC codes directing central system delivery bodies Ofgem's implementation and assurance approach Ofgem's transition plan https://www.ofgem.gov.uk/consultation/energy-code-reform-second-implementation-consultation | Ofgem expect to publish a joint consultation with DESNZ in Spring 2025, on both code manager standard licence conditions and updates to secondary legislation for code modification appeals to the Competition and Markets Authority (CMA). Expecting to publish another consultation later in 2025, where we expect to share areas of our approach which have not been covered in this consultation. That may include, but is not limited to, further proposals related to our implementation and transition process, such as transitioning live or inflight code processes, and drafts of proposed licence and code modifications. The interim milestones and timings of critical path activities for phase 1 codes are as follows: Spring / Summer 2025: Phase 1 bilateral and workgroups with the industry will be held for targeted policy topics. Later in 2025 / 1H-2026: We expect to consult on modification proposals for phase 1 codes. Implementation and assurance activities for phase 1 code manager candidates are expected to run during this period. Spring / Summer 2026: Phase 1 code manager appointments are expected. Commencing in 2026-27: We expect to publish our minded-to decisions with respect to the identity of the phase 2 code managers, followed by the start of the subsequent implementation and assurance period. | Directed changes expected (timeline TBC) | Directed changes expected (timeline TBC) | Directed changes expected (timeline TBC) | TBC | Directed changes expected (timeline TBC) | Ofgem identified the following areas where they believed code provisions should be targeted for rationalisation and simplification as part of any Ofgem-led consolidation activity, using the transitional powers granted by the Energy Act: • Common contractual framework • Contract boilerplate and defined terms • Party accession and exit • Code objectives • Code modification process • Code compliance • Credit cover arrangements • Dispute processes • Derogation provisions
Code Reform | SDS | Introduction of the Ofgem SDS, which is intended to set the direction of travel for the development of codes, in line with Ofgem's overarching vision for the sector. The SDS is required by the Energy act to contain a strategic assessment of government policy and developments which require modifications to the designated codes, and in preparing the SDS Ofgem must have regard to advice given by the NESO. | Yes | Yes | Yes | Yes | Yes | Yes | Risks and issues to be confirmed by Workgroup when more detail is avaiable. | Ofgem Work Ongoing. Latest consultation on a preliminary SDS (as well as code governance arrangements) closed on 28th March 2025. https://www.ofgem.gov.uk/consultation/consultation-preliminary-strategic-direction-statement-and-governance-arrangements-industry-codes | Ofgem Work Ongoing. Latest consultation on a preliminary SDS (as well as code governance arrangements) closed on 28th March 2025. https://www.ofgem.gov.uk/consultation/consultation-preliminary-strategic-direction-statement-and-governance-arrangements-industry-codes | Directed changes expected (timeline TBC) | Directed changes expected (timeline TBC) | Directed changes expected (timeline TBC) | TBC | Directed changes expected (timeline TBC) | Ofgem currently do not propose to introduce an obligation to implement the SDS before code managers are in place, however, they have proposed the introduction of a standard prioritisation process for code panels which will support the introduction of the SDS (see 22nd August 2024 decision publication and recently issued consultation on preliminary SDS dated 31st January 2025).
Code Reform | Code Governance | Changes to code governance (inc. matters relating to Code Managers, SAF, prioritisation, objectives, transition to new framework) will be done by Ofgem and with the permission of the SOS. | Yes | Yes | Yes | Yes | Yes | Yes | Risks and issues to be confirmed by Workgroup when more detail is avaiable. | Ofgem work is ongoing. Ofgem issued its second consultation on the implementation of Energy Code Reform on 3rd April 2025, which closed on 29th May. This consultation set out Ofgems proposals on a range of policy areas on how code governance reform would be implemented in practice, including sections on: the code modification process Stakeholder Advisory forums (SAFs) cross-cutting consequential code changes cost recovery for the BSC and REC codes directing central system delivery bodies Ofgem's implementation and assurance approach Ofgem's transition plan https://www.ofgem.gov.uk/consultation/energy-code-reform-second-implementation-consultation DESNZ and Ofgem are issued a joint consultation seeking views on proposals for energy code manager licence conditions and code modification appeals to the CMA. This consultation is now closed. https://www.gov.uk/government/consultations/energy-code-reform-code-manager-licence-conditions-and-code-modification-appeals-to-the-cma | Ofgem expect to publish a joint consultation with DESNZ in Spring 2025, on both code manager standard licence conditions and updates to secondary legislation for code modification appeals to the Competition and Markets Authority (CMA). Expecting to publish another consultation later in 2025, where we expect to share areas of our approach which have not been covered in this consultation. That may include, but is not limited to, further proposals related to our implementation and transition process, such as transitioning live or inflight code processes, and drafts of proposed licence and code modifications. The interim milestones and timings of critical path activities for phase 1 codes are as follows: Spring / Summer 2025: Phase 1 bilateral and workgroups with the industry will be held for targeted policy topics. Later in 2025 / 1H-2026: We expect to consult on modification proposals for phase 1 codes. Implementation and assurance activities for phase 1 code manager candidates are expected to run during this period. Spring / Summer 2026: Phase 1 code manager appointments are expected. | Directed changes expected (timeline TBC) | Directed changes expected (timeline TBC) | Directed changes expected (timeline TBC) | TBC | Directed changes expected (timeline TBC) | Recent publications on matters of Code Governance: Consultation on Code Manager Selection: https://www.ofgem.gov.uk/sites/default/files/2024-11/Consultation_on_code_manager_selection.pdf Decision on implementation of Energy Code Reform: https://www.ofgem.gov.uk/decision/implementation-energy-code-reform-decision Consultation on code governance arrangements and SDS: https://www.ofgem.gov.uk/consultation/consultation-preliminary-strategic-direction-statement-and-governance-arrangements-industry-codes Consultation on Code Manger Licenc Conditions and Appeals: https://www.gov.uk/government/consultations/energy-code-reform-code-manager-licence-conditions-and-code-modification-appeals-to-the-cma
Code Reform | Pre-Consolidation Code Changes | Ofgem identified the following areas where we believed code provisions should be targeted for rationalisation and simplification as part of any Ofgem-led consolidation activity, using the transitional powers granted by the Act: • Common contractual framework • Contract boilerplate and defined terms • Party accession and exit • Code objectives • Code modification process • Code compliance • Credit cover arrangements • Dispute processes • Derogation provisions | Yes | Yes | Yes | Yes | Yes | Yes | Risks and issues to be confirmed by Workgroup. | - | - | Directed changes expected (timeline TBC) | Directed changes expected (timeline TBC) | Directed changes expected (timeline TBC) | TBC | Directed changes expected (timeline TBC) | Ofgem identified the following areas where they believed code provisions should be targeted for rationalisation and simplification as part of any Ofgem-led consolidation activity, using the transitional powers granted by the Energy Act: • Common contractual framework • Contract boilerplate and defined terms • Party accession and exit • Code objectives • Code modification process • Code compliance • Credit cover arrangements • Dispute processes • Derogation provisions
Xoserve | Project Trident | Project Trident is an Xoserve project, looking to modernise UK Link, the platform they use to connect information, technology and communications systems for the retail gas market. UK Link is used and managed by Xoserve in its role as CDSP. It ensures the industry operates smoothly, effectively and efficiently, in accordance with the Uniform Network Code and its IGT equivalent. | TBC | TBC | TBC | TBC | TBC | TBC | Risks and issues to be confirmed by Workgroup. | Xoserve's initial research began in July 2024, with a launch event taking place in September 2024. To conclude its series of workshops, Xoserve is holding two in-person launch events of the final report, where we will share the key outputs and findings from the workshops. These sessions will provide an opportunity to reflect on the insights captured across the pain point areas explored in the workshop series. We will also discuss how these findings are feeding into our recommendations. The two playback sessions will be held: In Solihull, at Xoserve HQ on Monday 21 July from 15:30 to 17:00. In London, at Moorhouse HQ on Thursday 24 July from 17:00 to 18:30. Link to register: https://2dldbt.share-eu1.hsforms.com/2HOh9P8RATrCl-TiZ9sIolg?utm_source=hs_email&utm_medium=email&utm_content=111814190&_hsenc=p2ANqtz-9eN8hJH8gnZz8_NiPl80MOG5IfGhdwuA4Jl5htOotOy4TX5leS8RvMgskSTHj7aFYAyG1iTBeZygTQs4lSwEtbyEficrd3JGVAo_jgshAMrNYSXNE Xoserve work ongoing, further information on the Xoserve website: https://www.xoserve.com/products-services/data-products/uk-link-system/project-trident/ https://www.xoserve.com/media/ekhd0pqx/project-trident_pre-workshop-introductory-webinar-slides_v11.pdf | Standard support for the current version of the SAP platform that supports UK Link ends in 2027, with extended support available until 2030. It is estimated that Project Trident will run until 2028. Xoserve's focus until July 2025 will be developing an FBC for procuring the most suitable solution against a set of critical success factors. | TBC | TBC | TBC | TBC | TBC | https://www.xoserve.com/products-services/data-products/uk-link-system/project-trident/ https://www.xoserve.com/media/ekhd0pqx/project-trident_pre-workshop-introductory-webinar-slides_v11.pdf
Xoserve | Service Line Review | Xoserve looking at amendments to the service lines, introduction of a new service line which will include a new charge for IGTs and splitting an element related to AUGE, PAC and PAFA and making it a 50/50 split in respect of charging. | TBC | TBC | TBC | TBC | TBC | TBC | Added by Workgroup - Detail to be confirmed. | A Workgroup member has indicated that work has commenced on the Xoserve service line review. This work includes looking at amendments to the service lines, introduction of a new service line which will include a new charge for IGTs. The member added that work was also being done to look at splitting an element related to AUGE, PAC and PAFA and making it a 50/50 split in respect of charging. Specific timescales to be confirmed as work continues | Added by Workgroup - Detail to be confirmed | TBC | TBC | TBC | TBC | TBC
Digitalising the Energy System | Digital Spine Study | This feasibility study was funded by the Government’s NZIP, and examined the concept, opportunities and attributes of a data sharing infrastructure for the energy system; a ‘digital spine’. It was delivered by a consortium of Ove Arup, Energy Systems Catapult and the University of Bath. | - | - | - | - | - | - | None anticipated as part of the study itself. | DESNZ published its response to the digital spine study in August 2024: https://www.gov.uk/government/publications/digitalising-the-energy-system | Work expected to continue under Data Sharing Infrastructure work. | - | - | - | - | -
Digitalising the Energy System | Data Sharing Infrastructure | Introduction of a data sharing infrastructure, which is a minimum set of responsibilities, governance, functions and processes for secure, interoperable data sharing across the energy system. This activity covers the DSI Pilot, DSI MVP and Ofgem Guidance. | TBC | TBC | TBC | TBC | TBC | TBC | Risks and issues to be confirmed by Workgroup. | DESNZ published its response to the digital spine study in August 2024, which included commitments for the data sharing infrastructure: https://www.gov.uk/government/publications/digitalising-the-energy-system Ofgem published its decision on the definition of ESD and DBP Guidance in October 2024: https://www.ofgem.gov.uk/decision/decision-definition-energy-system-data-data-best-practice-guidance The Code Administrator is expecting a consultation to be issued by Ofgem ahead of the May Strategic Workgroup meeting. Ofgem issued its consultation on Data Best Practice as a Code Obligation on 30th June 2025, responses are invited by 11th August 2025: https://www.ofgem.gov.uk/publications/data-best-practice-code-obligation | Related Ofgem programme’s name has changed from Energy Data and Digitalisation to Energy System Digitalisation. Ofgem's Energy System Digitalisation page is provided below: https://www.ofgem.gov.uk/energy-policy-and-regulation/policy-and-regulatory-programmes/energy-system-digitalisation Project information for NESO DSI Pilot / MVP: https://smarter.energynetworks.org/projects/nia2_ngeso081/ https://www.neso.energy/document/353696/download Project information for NESO DSI / SSEN-T Component: https://smarter.energynetworks.org/projects/nia_shet_0053/ | TBC | TBC | TBC | TBC | TBC | Related Ofgem programme’s name has changed from Energy Data and Digitalisation to Energy System Digitalisation. Ofgem's Energy System Digitalisation page is provided below: https://www.ofgem.gov.uk/energy-policy-and-regulation/policy-and-regulatory-programmes/energy-system-digitalisation Project information for NESO DSI Pilot / MVP: https://smarter.energynetworks.org/projects/nia2_ngeso081/ Project information for NESO DSI / SSEN-T Component: https://smarter.energynetworks.org/projects/nia_shet_0053/
Hydrogen Blending | Hydrogen Strategy | The Government sees Hydrogen as a key support for the decarbonisation of the UK economy. In 2021, the UK government published its first Hydrogen Strategy, which aimed for 5GW of low carbon hydrogen production capacity by 2030 for use across the economy. Building on these proposals, the British Energy Security Strategy committed to doubling this 2030 hydrogen production capacity ambition to up to 10GW, with at least half coming from electrolytic production. The Government set out its decision to support the blending of up to 20% hydrogen by volume into the GB gas distribution networks in 2023. | TBC | TBC | TBC | TBC | TBC | TBC | Added by Workgroup - Detail to be confirmed | Added by Workgroup - Detail to be confirmed | Added by Workgroup - Detail to be confirmed | TBC | TBC | TBC | TBC | TBC
Hydrogen Blending | RTSM Programme | In February 2024, a programme was established, to develop a modelling solution that will facilitate the introduction of a fair and equitable billing and settlement framework able to operate in a multi-gas system with varying CVs. The RTSM programme aims to develop an integrated solution for the processes of characterising, settling, and billing gas in a multi-gas energy system. The current challenges highlight the need for a flexible solution that can respond to changes in gas mix and subsequent CVs. The findings of this programme will be applicable and relevant to all gas networks across GB amongst wider energy industry stakeholders. Stakeholder engagement with key industry stakeholder is vital to ensure that all eligibility criteria are thoroughly reviewed and endorsed by all relevant parties. | TBC | TBC | TBC | TBC | TBC | TBC | Added by Workgroup - Detail to be confirmed | Documentation published indicates that the programme is currently in the Phase 1 (10 months, started in September 2024). Phase 1 has been split into 5 work packages: • WP1: Market research to identify existing solutions. • WP2: Develop the Basis of Design of a fit-for-purpose modelling solution. • WP3a: Feasibility study: economic, technical, regulatory, operational, etc. • WP3b: Roadmap for a seamless integration across the UK. • WP4: Rollout strategy to assess the requirements for a potential demonstration. • WP5: Dissemination. | Further information on timescales can be found in the document linked below, which indicates the following: Phase 0: Engagement, 4 months (2024) Phase 1: Methodology Development, 10 months (2024/2025) Phase 2: Front-End Engineering Design, 7 months (2025/2026) Phase 3: Demonstration, 12 months (2026/2027) Implementation: 2030 https://www.gasgovernance.co.uk/sites/default/files/related-files/2025-02/RTSM%20Stakeholder%20Engagement%20v1.0_0.pdf | TBC | TBC | TBC | TBC | TBC | Phase 1 Methodology Development Presentation: https://www.gasgovernance.co.uk/sites/default/files/related-files/2025-02/RTSM%20Stakeholder%20Engagement%20v1.0_0.pdf Xoserve RTSM webpage: https://www.xoserve.com/decarbonisation/decarbonising-gas/decarbonisation-knowledge-centre/real-time-settlement-methodology-rtsm/

## Cross Code Change
Cross Code Change
Code | Change Number | Related Changes | Title | Proposer | Current Status | Next Stage | Key Date | Other Comments / Useful Context
IGT UNC | 165 | UNC0843 | Establishing the Independent Shrinkage Charge and the Independent Shrinkage Expert | OVO Energy | Industry Consultation | Report to Panel | 2025-08-29 | Apr / May 2025 Update: At its March meeting the Workgroup agreed to do a final review of the Workgroup Report and make their final conclusions on the Modification at the April meeting. The Workgroup revisited the Workgroup Report and made significant progress but chose to leave views on objectives for the May 2025 Workgroup. The Workgroup Report will still be presented to the IGT UNC Panelling May 2025. June 2025 Update: The IGT UNC Panel determined that IGT165 should be issued for industry consultation in June for 15 working days, ending on 18th July 2025.The FMR will be presented to IGT UNC Panel in August. July 25 Update: IGT165 is currently out of industry consultation, with responses due back by 11th July 2025. The FMR will be presented to Panel in August.
IGT UNC | 175 | UNC0889 | Alignment of the IGT UNC with the UNC following Modification UNC0899 and additional housekeeping changes | BUUK | Awaiting Implementation | Implementation | 2025-06-27 | Apr/May 2025 Update: BUUK raised this Modification on 10th March 2025. The Panel considered the Modification at its meeting on 28th March. The Modification was taken to Workgroup on 10th April, where the Workgroup completed work on the Modification and agreed the Workgroup Report. The Workgroup Report was taken to Panel on 25th April 2025 where they unanimously agreed to issue the Draft Modification Report for Consultation. The Consultation will close at 5pm on 20th May 2025 and the Pre-Panel Final Modification Report will go back to Panel on 30th May 2025 as a late paper. June 2025 Update: The IGT UNC Panel unanimously decided that iGT175 should be approved, at its meeting on 30th June. The Modification will be implemented in June 2025 as part of the June 2025 Release subject to the 15 working day appeal window. July 2025 Update: Modification implemented on 27th June 2025.
IGT UNC | 176 | UNC0887 | Changes to IGT UNC to enable UNC0887 ‘Facilitating Bi-Directional Connections Between IGT Pipelines and the NTS’ | CNG Services | Allocated to Working Group | Report to Panel | 2025-06-27 | Apr/May 2025 Update: CNG raised this Modification on 19th March 2025. The Panel considered the Modification at its meeting on 28th March. The Modification was briefly discussed at Workgroup on 10th April. The Workgroup will do further work on the Modification at its 8th May meeting. July 2025 Update: The Workgroup had continued its work on this Modification. We are aiming to agreed the Workgroup Report in July.
IGT UNC | 177 | 908 | Aligning IGT “must read” obligations within the IGT UNC | BUUK | Allocated to Working Group | Report to Panel | 2025-06-27 | June 2025 Update: BUUK have rasied IGT177 to maintain existing obligation on IGTs to obtain a meter reading (commonly called the “must read” obligation) following non-provision of a Valid Meter Reading by a Shipper, by removing reference to UNC TPD M 5.10 from IGT UNC Part E – Meter Reading, 11 (Failure to obtain readings), and aligning the total relevant text within the IGT UNC. July 2025 Update: The Workgroup considered the Modification at its July meeting and completed the Workgroup Report. This was considered by the Panel in July and issued for industry consutlation shortly after. Responses are due by 21st July 2025. The FMR will be presented to Panel in August.
UNC | 843 | IGT165 | Establishing the Independent Shrinkage Charge and the Independent Shrinkage Expert | OVO Energy | Industry Consultation | Report to Panel | 2025-08-21 | Mar 2025 Update: the UNC Workgroup considered and Amended Modification and the changes that had been agreed and made. No changes had been made to the Solution and the Charging Objectives had been removed. Based on the discussions that had taken place, some further amendments were required to the ROM. To avoid causing confusion, it was agreed to defer the review of the ROM. The Workgroup also reviewed some updates to the legal drafting. Next steps include: - Final review of version the Modification - Final Review of the updated Legal Text with the Legal Text being provided at least 5 days ahead of the next meeting - Review of the ROM - Finalise Workgroup Report Apr/May 2025 Update: UNC0843 Workgroup Report now due in May 2025. June 2025 Update: The UNC Panel have issued UNC0843 for industry consutaltion, closing on 18th July. The FMR will be presented to UNC Panel in August.
UNC | 854 | IGT UNC Mod expected | Revision of Virtual Last Resort User and Contingent Procurement of Supplier Demand Event Triggers | National Gas Transmission | Implemented | - | - | Jan 2025 Update: Implemented on 22nd May 2024. IGT UNC Workgroup have agreed that a change to the IGT UNC is required. Waiting on an IGT UNC Modification to be raised. Feb 2025 Update: The IGT UNC Code Administrator has met with Energy Assets to discuss raised the required equivalate Modification. The Proposer will be brining the equivalent Modification to Workgroup on 13th March 2025 for pre-Modification discussion before looking to formally raise the Modification ahead of the February Panel meeting on 28th March 2025. Mar 2025 Update: The Code Administrator is still expecting this Modification to be discussed at an upcoming IGT UNC Workgroup meeting.
UNC | 884 | TBC | Extending the PC4 Read Submission Window | OVO Energy | Allocated to Working Group | Report to Panel | 2025-06-19 | Apr/ May 2025 Update: UNC Workgroup Report is due to be presented to the UNC Panel on 17th April. IGT currently drafting a related IGT UNC Modification to address impacts to the IGT Must Read submission window for PC4.
UNC | 887 | IGT176 | Facilitating Bi-Directional Connections Between IGT Pipelines and the NTS | National Gas Transmission | Allocated to Working Group | Report to Panel | 2025-06-27 | Mar 2025 Update: An IGT has submitted a draft Modification Proposal form. The Code Administrator expect this Modification to be raised ahead of the March 2025 Panel meeting. Apr/ May 2025 Update: UNC Workgroup Report was presented to the UNC Panel on 17th April. This Modification is currently out for industry Consultation, which will close on 13th May 2025. The Modification will go back to Panel on 16th May 2025. June 2025 Update: FMR for UNC0887 is due to be presented to the UNC Panel in June. July 2025 Update: This Modification was recommened for approval by the UNC Panel in June and was submitted to the Authority for consideration on 20th June 2025.
UNC | 908 | IGT177 | Removal of DNO meter reading obligations resulting from non-provision of a Valid Meter Reading | Wales & West Utilities | Allocated to Working Group | Report to Panel | 2025-09-18 | June 2025 Update: BUUK have rasied IGT177 to maintain existing obligation on IGTs to obtain a meter reading (commonly called the “must read” obligation) following non-provision of a Valid Meter Reading by a Shipper, by removing reference to UNC TPD M 5.10 from IGT UNC Part E – Meter Reading, 11 (Failure to obtain readings), and aligning the total relevant text within the IGT UNC. July 2025 Update: a ROM has been requested and will be considered at the July Workgroup meeting.

## Milestone Timeline
IGT UNC Horizon Scanner Timeline
2026
Category |  | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Code Reform | Code Consolidation (GNC) | bar: MAY to 2026 APR
| SDS | JUN: First SDS expected
| Code Governance | JUN: LINK - Closes 27/06/25
Pre-Consolidation Code Changes | bar: MAY to 2026 APR
Xoserve | Project Trident | JUN: Sourcing and Procurement (25/26) - Build, Design and Test (25-29) - Target Implemenation Window (27/30)
Digitalising the Energy System | DSI (NESO Pilot) | 2026 JAN: MVP launch expected
| DSI (NESO MVP) | 2026 JAN: MVP launch expected; 2026 APR: RIIO T3/GD3 start
| DSI (Ofgem) | JUN: LINK - Closes 11/08/25; 2026 JAN: DSI progress updated expected in 2025
Cross Code Change | UNC0843 (Shrinkage Expert) | JUN: LINK - Closes 11/07/25
| IGT165 (Shrinkage Expert) | JUN: LINK - Closes 11/07/25
IGT176 (Bidirectional Gas to NTS via IGT) | bar: AUG to OCT
UNC0887 (Bidirectional Gas to NTS via IGT) | bar: MAY; AUG
IGT175 (UNC0899 & Housekeeping Changes) | bar: MAY to JUN; AUG
Hydrogen Blending | RTSM Programme | AUG: Phase 1 expected to end
P
M
P
P
M
Phase 2 expected to end
Phase 2 expected to start
P
W
W
W
P
P
P
P
P
Issued to Authority on 20/06/24
M
Issue to Authority
M
C
C
I
Implemented: 27/06/25
C
C
M
P
C
W
M
M
M
M
Issue to Authority
M

## Timeline key
Icon | Description
Consultation Confirmed
Consultation Unconfirmed
Release/Implementation Confirmed
Release/Implementation Unconfirmed
Event/Workgroup/Steering Group/Panel Confirmed
Event/Workgroup/Steering Group/Panel Unconfirmed
Publication Confirmed
Publication Unconfirmed
Milestone Confirmed
Milestone Unconfirmed
Solid Yellow/Solid Grey | Work Ongoing
P
P
R
R
C
E
E
M
M
W
S
W
S
P
P
C
I
I

## Acronyms
Acronym | Defined Term
AUGE | Allocation of Unidentified Gas Expert
BEIS | Department for Business, Energy, and Industrial Strategy
BSC | Balancing and Settlement Code
CDSP | Central Data Services Provider
CMA | Competition and Markets Authority
CSS | Central Switching Service
CUSC | Connection and Use of System Code
CV | Calorific Value
DBP | Data Best Practice
DCUSA | Distribution Connection and Use of System Agreement
ECC | Electricity Commercial Code
ESD | Energy System Data
ETC | Electricity Technical Code
FBC | Full Business Case
GEMA | Gas and Electricity Markets Authority
GNC | Gas Network Code
IGT UNC | Independent Gas Transporters Uniform Network Code
ISOP | Independent System Operator and Planner
MVP | Minimum Viable product
NESO | National Energy System Operator. Named in the Energy Act 2023 as ISOP
NZIP | Government’s Net Zero Innovation Portfolio
PAC | Performance Assurance Committee
PAFA | Performance Assurance Framework Administrator
REC | Retail Energy Code
RTSM | Real Time Settlement Methodology
SAF | Stakeholder Advisory Forum
SDS | Strategic Direction Statement, which will set out Ofgems vision for how the codes should devolve on an annual basis
SEC | Smart Energy Code
SOS | Secretary of State
SQSS | Security and Quality of Supply Standard
STC | System Operator Transmission Owner Code
UNC | Uniform Network Code