## Introduction
IGT UNC Horizon Scanner
Date | 2025-09-03
Version | v1.8
Purpose | This document provides visibility of IGT UNC impacting industry activities, as well as the progression of Cross Code impacting Modifications. This document is owned by the IGT UNC Workgroup and is refreshed approximately monthly. Please refer to the IGT UNC Horizon Scanner page of the IGT UNC website for the most up to date version.
Contact | If you have any queries or comments about this Horizon Scanner, please contact the IGT UNC Code Administrator via email, IGTUNC@gemserv.com.
Uplift History | Reason for change | Date
v0.1 | Initial draft for Workgroup consideration | 2024-11-07
v1.0 | Uplift to approved working document | 2024-12-05

## Horizon Scanner
IGT UNC Horizon Scanner
|  |  | IMPACTS | [8 empty] | INDUSTRY CHANGE
Category | Activity | Description / Scope | IGT UNC | UNC | Other Codes | IGT | Shipper | Other Party | Risks / Issues | Current Status | Future Milestones / Key Dates | IGT Changes | UNC Changes | Other Code Changes | Central System Changes | Licences | Other Comments / Useful Context
Code Reform | Code Consolidation (GNC) | Introduction of GNC, which will involve the merging of IGT UNC and UNC. Designation of changes ahead of consolidation is expected. Further information on this will be noted when it is available. | Yes | Yes | CUSC DCUSA SQSS STC | Yes | Yes | All parties to impacted Codes | Introduction of inaccuracies, short notice changes, lack of party engagement. | Ofgem work is ongoing. Ofgem issued its second consultation on the implementation of Energy Code Reform on 3rd April 2025, which closed on 29th May. This consultation set out Ofgem's proposals on a range of policy areas on how code governance reform would be implemented in practice, including sections on: the code modification process Stakeholder Advisory forums (SAFs) cross-cutting consequential code changes cost recovery for the BSC and REC codes directing central system delivery bodies Ofgem's implementation and assurance approach Ofgem's transition plan https://www.ofgem.gov.uk/consultation/energy-code-reform-second-implementation-consultation | The interim milestones and timings of critical path activities for phase 1 codes are as follows: Spring / Summer 2025: Phase 1 bilateral and workgroups with the industry will be held for targeted policy topics. Later in 2025 / 1H-2026: We expect to consult on modification proposals for phase 1 codes. Implementation and assurance activities for phase 1 code manager candidates are expected to run during this period. Spring / Summer 2026: Phase 1 code manager appointments are expected. Commencing in 2026-27: Ofgem expected to publish minded-to decisions with respect to the identity of the phase 2 code managers, followed by the start of the subsequent implementation and assurance period. Below summarises the upcoming code reform publications, planned for 2025/26: • Autumn 2025: Decision on second implementation consultation • Winter 2025/26: Modification proposals consultation • Winter 2025/26: Decision on code manager licence conditions and code modification appeals to the CMA – in collaboration with DESNZ | Directed changes expected (timeline TBC) | Directed changes expected (timeline TBC) | Directed changes expected (timeline TBC) | TBC | Directed changes expected (timeline TBC) | Ofgem identified the following areas where they believed code provisions should be targeted for rationalisation and simplification as part of any Ofgem-led consolidation activity, using the transitional powers granted by the Energy Act: • Common contractual framework • Contract boilerplate and defined terms • Party accession and exit • Code objectives • Code modification process • Code compliance • Credit cover arrangements • Dispute processes • Derogation provisions
Code Reform | SDS | Introduction of the Ofgem SDS, which is intended to set the direction of travel for the development of codes, in line with Ofgem's overarching vision for the sector. The SDS is required by the Energy act to contain a strategic assessment of government policy and developments which require modifications to the designated codes, and in preparing the SDS Ofgem must have regard to advice given by the NESO. | Yes | Yes | Yes | Yes | Yes | Yes | Risks and issues to be confirmed by Workgroup when more detail is available. | Ofgem Work Ongoing. on 1st August 2025, Ofgem published its decision on the preliminary SDS and governance arrangements for industry Codes. https://www.ofgem.gov.uk/decision/decision-preliminary-strategic-direction-statement-and-governance-arrangements-industry-codes | The next formal SDS is expected to follow the appointment of code managers in 2026. | Directed changes expected (timeline TBC) | Directed changes expected (timeline TBC) | Directed changes expected (timeline TBC) | TBC | Directed changes expected (timeline TBC) | Ofgem currently do not propose to introduce an obligation to implement the SDS before code managers are in place, however, they have proposed the introduction of a standard prioritisation process for code panels which will support the introduction of the SDS (see 22nd August 2024 decision publication and recently issued consultation on preliminary SDS dated 31st January 2025). Decision on code governance arrangements and SDS: https://www.ofgem.gov.uk/decision/decision-preliminary-strategic-direction-statement-and-governance-arrangements-industry-codes
Code Reform | Code Governance | Changes to code governance (inc. matters relating to Code Managers, SAF, prioritisation, objectives, transition to new framework) will be done by Ofgem and with the permission of the SOS. | Yes | Yes | Yes | Yes | Yes | Yes | Risks and issues to be confirmed by Workgroup when more detail is available. | Ofgem Work Ongoing. on 1st August 2025, Ofgem published its decision on the preliminary SDS and governance arrangements for industry Codes. https://www.ofgem.gov.uk/decision/decision-preliminary-strategic-direction-statement-and-governance-arrangements-industry-codes | The interim milestones and timings of critical path activities for phase 1 codes are as follows: Spring / Summer 2025: Phase 1 bilateral and workgroups with the industry will be held for targeted policy topics. Later in 2025 / 1H-2026: We expect to consult on modification proposals for phase 1 codes. Implementation and assurance activities for phase 1 code manager candidates are expected to run during this period. Spring / Summer 2026: Phase 1 code manager appointments are expected. Below summarises the upcoming code reform publications, planned for 2025/26: • Autumn 2025: Decision on second implementation consultation • Winter 2025/26: Modification proposals consultation • Winter 2025/26: Decision on code manager licence conditions and code modification appeals to the CMA – in collaboration with DESNZ | Directed changes expected (timeline TBC) | Directed changes expected (timeline TBC) | Directed changes expected (timeline TBC) | TBC | Directed changes expected (timeline TBC) | Recent publications on matters of Code Governance: Consultation on Code Manager Selection: https://www.ofgem.gov.uk/sites/default/files/2024-11/Consultation_on_code_manager_selection.pdf Decision on implementation of Energy Code Reform: https://www.ofgem.gov.uk/decision/implementation-energy-code-reform-decision Decision on code governance arrangements and SDS: https://www.ofgem.gov.uk/decision/decision-preliminary-strategic-direction-statement-and-governance-arrangements-industry-codes Consultation on Code Manger Licence Conditions and Appeals: https://www.gov.uk/government/consultations/energy-code-reform-code-manager-licence-conditions-and-code-modification-appeals-to-the-cma
Code Reform | Pre-Consolidation Code Changes | Ofgem identified the following areas where we believed code provisions should be targeted for rationalisation and simplification as part of any Ofgem-led consolidation activity, using the transitional powers granted by the Act: • Common contractual framework • Contract boilerplate and defined terms • Party accession and exit • Code objectives • Code modification process • Code compliance • Credit cover arrangements • Dispute processes • Derogation provisions | Yes | Yes | Yes | Yes | Yes | Yes | Risks and issues to be confirmed by Workgroup. |  | The interim milestones and timings of critical path activities for phase 1 codes are as follows: Spring / Summer 2025: Phase 1 bilateral and workgroups with the industry will be held for targeted policy topics. Later in 2025 / 1H-2026: We expect to consult on modification proposals for phase 1 codes. Implementation and assurance activities for phase 1 code manager candidates are expected to run during this period. Spring / Summer 2026: Phase 1 code manager appointments are expected. Below summarises the upcoming code reform publications, planned for 2025/26: • Autumn 2025: Decision on second implementation consultation • Winter 2025/26: Modification proposals consultation • Winter 2025/26: Decision on code manager licence conditions and code modification appeals to the CMA – in collaboration with DESNZ | Directed changes expected (timeline TBC) | Directed changes expected (timeline TBC) | Directed changes expected (timeline TBC) | TBC | Directed changes expected (timeline TBC) | Ofgem identified the following areas where they believed code provisions should be targeted for rationalisation and simplification as part of any Ofgem-led consolidation activity, using the transitional powers granted by the Energy Act: • Common contractual framework • Contract boilerplate and defined terms • Party accession and exit • Code objectives • Code modification process • Code compliance • Credit cover arrangements • Dispute processes • Derogation provisions
Xoserve | Project Trident | Project Trident is an Xoserve project, looking to modernise UK Link, the platform they use to connect information, technology and communications systems for the retail gas market. UK Link is used and managed by Xoserve in its role as CDSP. It ensures the industry operates smoothly, effectively and efficiently, in accordance with the Uniform Network Code and its IGT equivalent. | TBC | TBC | TBC | TBC | TBC | TBC | Risks and issues to be confirmed by Workgroup. | Project Trident has launched a customer consultation on its preferred hypothesis. The preferred hypothesis is the option that is currently favoured over others based on research and evidence indicating that this best meets the needs of Project Trident, and no decision has yet been made. This consultation closes on Tuesday 12 September. Information on how to respond to the consultation can be found on the project trident webpage as well as the August 2025 issue of the Tide: https://www.xoserve.com/products-services/data-products/uk-link-system/project-trident/ https://www.xoserve.com/media/tmphcj2i/the-tide-xoserves-project-trident-newsletter-10.pdf | Standard support for the current version of the SAP platform that supports UK Link ends in 2027, with extended support available until 2030. It is estimated that Project Trident will run until 2028. Xoserve's focus until July 2025 will be developing an FBC for procuring the most suitable solution against a set of critical success factors. | TBC | TBC | TBC | TBC | TBC | https://www.xoserve.com/products-services/data-products/uk-link-system/project-trident/ https://www.xoserve.com/media/ekhd0pqx/project-trident_pre-workshop-introductory-webinar-slides_v11.pdf
Xoserve | Service Line Review | Xoserve looking at amendments to the service lines, introduction of a new service line which will include a new charge for IGTs and splitting an element related to AUGE, PAC and PAFA and making it a 50/50 split in respect of charging. | TBC | TBC | TBC | TBC | TBC | TBC | Added by Workgroup - Detail to be confirmed. |  | Added by Workgroup - Detail to be confirmed | TBC | TBC | TBC | TBC | TBC
Digitalising the Energy System | Digital Spine Study | This feasibility study was funded by the Government’s NZIP, and examined the concept, opportunities and attributes of a data sharing infrastructure for the energy system; a ‘digital spine’. It was delivered by a consortium of Ove Arup, Energy Systems Catapult and the University of Bath. | - | - | - | - | - | - | None anticipated as part of the study itself. |  | Work expected to continue under Data Sharing Infrastructure work. | - | - | - | - | -
Digitalising the Energy System | Data Sharing Infrastructure | Introduction of a data sharing infrastructure, which is a minimum set of responsibilities, governance, functions and processes for secure, interoperable data sharing across the energy system. This activity covers the DSI Pilot, DSI MVP and Ofgem Guidance. | TBC | TBC | TBC | TBC | TBC | TBC | Risks and issues to be confirmed by Workgroup. | DESNZ published its response to the digital spine study in August 2024, which included commitments for the data sharing infrastructure: https://www.gov.uk/government/publications/digitalising-the-energy-system Ofgem published its decision on the definition of ESD and DBP Guidance in October 2024: https://www.ofgem.gov.uk/decision/decision-definition-energy-system-data-data-best-practice-guidance The Code Administrator is expecting a consultation to be issued by Ofgem ahead of the May Strategic Workgroup meeting. Ofgem issued its consultation on Data Best Practice as a Code Obligation on 30th June 2025, responses are invited by 11th August 2025: https://www.ofgem.gov.uk/publications/data-best-practice-code-obligation | Related Ofgem programme’s name has changed from Energy Data and Digitalisation to Energy System Digitalisation. Ofgem's Energy System Digitalisation page is provided below: https://www.ofgem.gov.uk/energy-policy-and-regulation/policy-and-regulatory-programmes/energy-system-digitalisation Project information for NESO DSI Pilot / MVP: https://smarter.energynetworks.org/projects/nia2_ngeso081/ https://www.neso.energy/document/353696/download Project information for NESO DSI / SSEN-T Component: https://smarter.energynetworks.org/projects/nia_shet_0053/ | TBC | TBC | TBC | TBC | TBC | Related Ofgem programme’s name has changed from Energy Data and Digitalisation to Energy System Digitalisation. Ofgem's Energy System Digitalisation page is provided below: https://www.ofgem.gov.uk/energy-policy-and-regulation/policy-and-regulatory-programmes/energy-system-digitalisation Project information for NESO DSI Pilot / MVP: https://smarter.energynetworks.org/projects/nia2_ngeso081/ Project information for NESO DSI / SSEN-T Component: https://smarter.energynetworks.org/projects/nia_shet_0053/
Hydrogen Blending | Hydrogen Strategy | The Government sees Hydrogen as a key support for the decarbonisation of the UK economy. In 2021, the UK government published its first Hydrogen Strategy, which aimed for 5GW of low carbon hydrogen production capacity by 2030 for use across the economy. Building on these proposals, the British Energy Security Strategy committed to doubling this 2030 hydrogen production capacity ambition to up to 10GW, with at least half coming from electrolytic production. The Government set out its decision to support the blending of up to 20% hydrogen by volume into the GB gas distribution networks in 2023. | TBC | TBC | TBC | TBC | TBC | TBC | Added by Workgroup - Detail to be confirmed | Added by Workgroup - Detail to be confirmed | Added by Workgroup - Detail to be confirmed | TBC | TBC | TBC | TBC | TBC
Hydrogen Blending | RTSM Programme | In February 2024, a programme was established, to develop a modelling solution that will facilitate the introduction of a fair and equitable billing and settlement framework able to operate in a multi-gas system with varying CVs. The RTSM programme aims to develop an integrated solution for the processes of characterising, settling, and billing gas in a multi-gas energy system. The current challenges highlight the need for a flexible solution that can respond to changes in gas mix and subsequent CVs. The findings of this programme will be applicable and relevant to all gas networks across GB amongst wider energy industry stakeholders. Stakeholder engagement with key industry stakeholder is vital to ensure that all eligibility criteria are thoroughly reviewed and endorsed by all relevant parties. | TBC | TBC | TBC | TBC | TBC | TBC | Added by Workgroup - Detail to be confirmed | Documentation published indicates that the programme is currently in the Phase 1 (10 months, started in September 2024). Phase 1 has been split into 5 work packages: • WP1: Market research to identify existing solutions. • WP2: Develop the Basis of Design of a fit-for-purpose modelling solution. • WP3a: Feasibility study: economic, technical, regulatory, operational, etc. • WP3b: Roadmap for a seamless integration across the UK. • WP4: Rollout strategy to assess the requirements for a potential demonstration. • WP5: Dissemination. | Further information on timescales can be found in the document linked below, which indicates the following: Phase 0: Engagement, 4 months (2024) Phase 1: Methodology Development, 10 months (2024/2025) Phase 2: Front-End Engineering Design, 7 months (2025/2026) Phase 3: Demonstration, 12 months (2026/2027) Implementation: 2030 https://www.gasgovernance.co.uk/sites/default/files/related-files/2025-02/RTSM%20Stakeholder%20Engagement%20v1.0_0.pdf | TBC | TBC | TBC | TBC | TBC | Phase 1 Methodology Development Presentation: https://www.gasgovernance.co.uk/sites/default/files/related-files/2025-02/RTSM%20Stakeholder%20Engagement%20v1.0_0.pdf Xoserve RTSM webpage: https://www.xoserve.com/decarbonisation/decarbonising-gas/decarbonisation-knowledge-centre/real-time-settlement-methodology-rtsm/

## Cross Code Change
Cross Code Change
Code | Change Number | Related Changes | Title | Proposer | Current Status | Next Stage | Key Date | Other Comments / Useful Context
IGT UNC | 165 | UNC0843 | Establishing the Independent Shrinkage Charge and the Independent Shrinkage Expert | OVO Energy | Authority Determination | TBC | TBC | Apr / May 2025 Update: At its March meeting the Workgroup agreed to do a final review of the Workgroup Report and make their final conclusions on the Modification at the April meeting. The Workgroup revisited the Workgroup Report and made significant progress but chose to leave views on objectives for the May 2025 Workgroup. The Workgroup Report will still be presented to the IGT UNC Panelling May 2025. June 2025 Update: The IGT UNC Panel determined that IGT165 should be issued for industry consultation in June for 15 working days, ending on 18th July 2025.The FMR will be presented to IGT UNC Panel in August. July 2025 Update: IGT165 is currently out of industry consultation, with responses due back by 11th July 2025. The FMR will be presented to Panel in August. September 2025 Update: IGT165 was send to the Authority for decision on 3rd September 2025.
IGT UNC | 176 | UNC0887 | Changes to IGT UNC to enable UNC0887 ‘Facilitating Bi-Directional Connections Between IGT Pipelines and the NTS’ | CNG Services | Authority Determination | TBC | TBC | Apr/May 2025 Update: CNG raised this Modification on 19th March 2025. The Panel considered the Modification at its meeting on 28th March. The Modification was briefly discussed at Workgroup on 10th April. The Workgroup will do further work on the Modification at its 8th May meeting. July 2025 Update: The Workgroup had continued its work on this Modification. We are aiming to agreed the Workgroup Report in July. September 2025 Update: IGT176 was send to the Authority for decision on 2nd September 2025.
IGT UNC | 177 | 908 | Aligning IGT “must read” obligations within the IGT UNC | BUUK | Appeal Window | Implementation | 2025-09-26 | June 2025 Update: BUUK have raised IGT177 to maintain existing obligation on IGTs to obtain a meter reading (commonly called the “must read” obligation) following non-provision of a Valid Meter Reading by a Shipper, by removing reference to UNC TPD M 5.10 from IGT UNC Part E – Meter Reading, 11 (Failure to obtain readings), and aligning the total relevant text within the IGT UNC. July 2025 Update: The Workgroup considered the Modification at its July meeting and completed the Workgroup Report. This was considered by the Panel in July and issued for industry consultation shortly after. Responses are due by 21st July 2025. The FMR will be presented to Panel in August. September 2025 Update: IGT177 was approved by the IGT UNC Panel under Self-Governance procedures on 19th August 2025. The Appeal window will close on 19th September 2025. If no appeals are received the Modification will be implemented on 26th September 2025. .
UNC | 843 | IGT165 | Establishing the Independent Shrinkage Charge and the Independent Shrinkage Expert | OVO Energy | Authority Determination | TBC | TBC | Mar 2025 Update: the UNC Workgroup considered and Amended Modification and the changes that had been agreed and made. No changes had been made to the Solution and the Charging Objectives had been removed. Based on the discussions that had taken place, some further amendments were required to the ROM. To avoid causing confusion, it was agreed to defer the review of the ROM. The Workgroup also reviewed some updates to the legal drafting. Next steps include: - Final review of version the Modification - Final Review of the updated Legal Text with the Legal Text being provided at least 5 days ahead of the next meeting - Review of the ROM - Finalise Workgroup Report Apr/May 2025 Update: UNC0843 Workgroup Report now due in May 2025. June 2025 Update: The UNC Panel have issued UNC0843 for industry consultation, closing on 18th July. The FMR will be presented to UNC Panel in August. September 2025 Update: UNC0843 was issued to the Authority for decision on 3rd September 2025.
UNC | 854 | IGT UNC Mod expected | Revision of Virtual Last Resort User and Contingent Procurement of Supplier Demand Event Triggers | National Gas Transmission | Implemented | - | - | Jan 2025 Update: Implemented on 22nd May 2024. IGT UNC Workgroup have agreed that a change to the IGT UNC is required. Waiting on an IGT UNC Modification to be raised. Feb 2025 Update: The IGT UNC Code Administrator has met with Energy Assets to discuss raised the required equivalate Modification. The Proposer will be brining the equivalent Modification to Workgroup on 13th March 2025 for pre-Modification discussion before looking to formally raise the Modification ahead of the February Panel meeting on 28th March 2025. Mar 2025 Update: The Code Administrator is still expecting this Modification to be discussed at an upcoming IGT UNC Workgroup meeting.
UNC | 884 | IGT178 | Extending the PC4 Read Submission Window | OVO Energy | Allocated to Working Group | Report to Panel | 2025-06-19 | Apr/ May 2025 Update: UNC Workgroup Report is due to be presented to the UNC Panel on 17th April. IGT currently drafting a related IGT UNC Modification to address impacts to the IGT Must Read submission window for PC4. September 2025 Update: IGT178 was raised by BUUK on 24th July 2025. This Modification seeks to extend the PC4 Read Submission Window following the approval of UNC0884. IGT178 will go to the September IGT UNC Workgroup meeting.
UNC | 887 | IGT176 | Facilitating Bi-Directional Connections Between IGT Pipelines and the NTS | National Gas Transmission | Implementation | - | TBC | Mar 2025 Update: An IGT has submitted a draft Modification Proposal form. The Code Administrator expect this Modification to be raised ahead of the March 2025 Panel meeting. Apr/ May 2025 Update: UNC Workgroup Report was presented to the UNC Panel on 17th April. This Modification is currently out for industry Consultation, which will close on 13th May 2025. The Modification will go back to Panel on 16th May 2025. June 2025 Update: FMR for UNC0887 is due to be presented to the UNC Panel in June. July 2025 Update: This Modification was recommended for approval by the UNC Panel in June and was submitted to the Authority for consideration on 20th June 2025.
UNC | 908 | IGT177 | Removal of DNO meter reading obligations resulting from non-provision of a Valid Meter Reading | Wales & West Utilities | Allocated to Working Group | Report to Panel | 2025-09-18 | June 2025 Update: BUUK have raised IGT177 to maintain existing obligation on IGTs to obtain a meter reading (commonly called the “must read” obligation) following non-provision of a Valid Meter Reading by a Shipper, by removing reference to UNC TPD M 5.10 from IGT UNC Part E – Meter Reading, 11 (Failure to obtain readings), and aligning the total relevant text within the IGT UNC. July 2025 Update: a ROM has been requested and will be considered at the July Workgroup meeting.

## Milestone Timeline
IGT UNC Horizon Scanner Timeline
[7 empty] | 2026 | [11 empty] | 2027
Category |  | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb
Code Reform | Code Consolidation (GNC) | bar: AUG to 2026 APR
SDS | bar: AUG to 2026 APR
Code Governance | bar: AUG to 2026 APR
Pre-Consolidation Code Changes | bar: AUG to 2026 APR
Xoserve | Project Trident | bar: 2026 APR
Digitalising the Energy System | DSI (NESO Pilot) | 2026 JAN: MVP launch expected
| DSI (NESO MVP) | 2026 JAN: MVP launch expected; 2026 APR: RIIO T3/GD3 start
| DSI (Ofgem), DBP (Ofgem) | 2026 JAN: DSI progress updated expected in 2025
Cross Code Change | UNC0843 (Shrinkage Expert) | bar: NOV
IGT165 (Shrinkage Expert) | bar: NOV
IGT176 (Bidirectional Gas to NTS via IGT) | bar: NOV
UNC0887 (Bidirectional Gas to NTS via IGT) | bar: AUG
IGT178 (Extending PC4 Read Submission Window) | bar: OCT to NOV
UNC0884 (Extending PC4 Read Submission Window) | bar: AUG
Hydrogen Blending | RTSM Programme | bar: AUG to 2026 APR
P
Phase 2 expected to end
P
P
Approved by Authority on 19/08/2025
Issued to Authority on 03/09/2025
M
M
M
M
Issued to Authority on 02/09/2035
LINK: Decision published 01/08/2025
C
Closed 11/08/2025
P
M
M
M
M
P
LINK: Decision published 01/08/2025
P
Issued to Authority on 21/08/2025
M
W
P
P
C
P
Issue to Authority
M

## Timeline key
Icon | Description
Consultation Confirmed
Consultation Unconfirmed
Release/Implementation Confirmed
Release/Implementation Unconfirmed
Event/Workgroup/Steering Group/Panel Confirmed
Event/Workgroup/Steering Group/Panel Unconfirmed
Publication Confirmed
Publication Unconfirmed
Milestone Unconfirmed
Milestone Confirmed
Solid Yellow/Solid Grey | Work Ongoing
P
P
R
R
C
E
E
M
M
W
S
W
S
P
P
C
I
I

## Acronyms
Acronym | Defined Term
AUGE | Allocation of Unidentified Gas Expert
BEIS | Department for Business, Energy, and Industrial Strategy
BSC | Balancing and Settlement Code
CDSP | Central Data Services Provider
CMA | Competition and Markets Authority
CSS | Central Switching Service
CUSC | Connection and Use of System Code
CV | Calorific Value
DBP | Data Best Practice
DCUSA | Distribution Connection and Use of System Agreement
ECC | Electricity Commercial Code
ESD | Energy System Data
ETC | Electricity Technical Code
FBC | Full Business Case
GEMA | Gas and Electricity Markets Authority
GNC | Gas Network Code
IGT UNC | Independent Gas Transporters Uniform Network Code
ISOP | Independent System Operator and Planner
MVP | Minimum Viable product
NESO | National Energy System Operator. Named in the Energy Act 2023 as ISOP
NZIP | Government’s Net Zero Innovation Portfolio
PAC | Performance Assurance Committee
PAFA | Performance Assurance Framework Administrator
REC | Retail Energy Code
RTSM | Real Time Settlement Methodology
SAF | Stakeholder Advisory Forum
SDS | Strategic Direction Statement, which will set out Ofgem's vision for how the codes should devolve on an annual basis
SEC | Smart Energy Code
SOS | Secretary of State
SQSS | Security and Quality of Supply Standard
STC | System Operator Transmission Owner Code
UNC | Uniform Network Code