## Watch List
Correct as of 05/02/2026
Mod Ref |  | Modification Title | Proposing Organisation | Date Raised | Live/Closed | Category | Workgroup | Current Status | Next Stage | Key date* | Legal Text Provider | IGT UNC Workgroup Update / Current Status
0922 |  | CDSP Obligations required for the introduction of the Gas Shipper Obligation | National Gas Transmission | 2026-01-07 | Live | Authority Direction | Distribution | Allocated to Workgroup | Report to Panel | 2026-07-16 |  | The Gas Shipper Obligation (GSO) is intended to be the long-term funding mechanism for initial hydrogen production projects funded through the Hydrogen Production Business Model (HPBM). The GSO charge will be placed on Shippers based on the quantity of gas they ship to customers. The GSO scheme will be administered by the GSO Administrator (who is expected to be the Low Carbon Contracts Company (LCCC), subject to formal appointment through regulations) and will be outside of the UNC. This Modification will create obligations on the Central Data Service Provider CDSP to provide services to the GSO Administrator to support the implementation of the GSO, including a period of live data testing. It is proposed that a subsequent Modification is developed and will be implemented to ensure the CDSP Obligations endure following implementation of the GSO legislation. February 2026: This Modification was considered by UNC Panel in January and has been allocated to a joint IGT UNC / UNC Workgroup to be developed alongside IGT180. The First meeting for this joint Workgroup will be on 12th March 2026,
0921 |  | Broadening the definition of the Data Permissions Matrix to align with disclosure of UK Link Gemini data | National Gas Transmission | 2025-09-12 | Live | Self-Governance | Transmission | Allocated to Workgroup | Report to Panel | 2026-05-21 |  | At its August 2025 meeting, the DSC Contract Management Committee approved the Disclosure Request Report (DRR) ‘Green Gas Certification Scheme (GGCS) Biomethane Data’. This DRR permits the CDSP to provide Renewable Energy Assurance Limited (REA) with data from UK Link Gemini; specifically, allocated volumes of biomethane gas injected. The UNC definition of the Data Permissions Matrix (within General Terms section D) refers exclusively to categories of data maintained in the Supply Point Register. The Proposer is seeking to broaden this definition, to align with the release of UK Link Gemini data through this DRR. February 2026: This Modification will impact the IGT UNC. A change is required to Part N2.5.1(b) to align the IGT UNC definition of Data Permissions Matrix to align with the changes under 0921.
0919 | S | Housekeeping amendments to TPD Sections B, G and M | Cadent | 2025-10-09 | Live | Self-Governance | Distribution | Allocated to Workgroup | Report to Panel | 2026-05-21 |  | The Proposer has identified cross-referencing errors in TPD sections B and G, introduced through the implementation of Modification 0804, which this Modification proposal seeks to rectify. Additionally, the Proposer has identified Modification 0804 amendments to TPD section M which were subsequently undone in error, through the delayed implementation of UNC 0710S. This Modification proposal seeks to reinstate those changes. Separately, the Proposer has identified further amendments to section M, introduced through Modification 0692S, which were erroneously undone by an earlier version of the Code. This Modification proposal seeks to reinstate those changes and, in addition, correct a newly identified formatting error. January 2026: The Code Administrator has reviewed the legal drafting and has not identified any impacts to IGT UNC as a result of the legal text changes under this Modification. February 2026: No IGT UNC Code changes required, but changes to Section M5.9 will automatically apply under the IGT UNC via cross referencing. Changes to Section B 4.7 will not result in a change to the IGT UNC as they are reference number changes only.
0914 | S | Refining the Class 3 EUC1 read submission rules introduced through Modification 0700 | Centrica | 2025-09-09 | Live | Self-Governance | Distribution | Allocated to Workgroup | Report to Panel | 2026-03-19 |  | This Modification proposes the removal of the batch read validation rules introduced under Modification 0700 for Class 3 EUC1 reads. This would allow daily reads for Class 3 EUC1 to be submitted and validated without the current restrictions. October 2025 - IGT UNC Code impact to be determined based on legal text drafting. It is expected that this functionality will apply to all Supply Points, including those on IGT Networks. February 2026: This Modification will impact the IGT UNC. A change is required to Part E 9.1 to change a reference to "Section M 5.8.6" to "Section M5.8.4" as a result of re-numbering.
0909 | S | Refining the Class 2 Individual Valid Meter Reading Requirement Performance Measures | SEFE Energy Limited | 2025-06-06 | Live | Self-Governance | Distribution | Industry Consultation | Final Modification Report | 2026-02-19 |  | The purpose of this Modification is to clarify the obligations on Shipper Users regarding Class 2 Meter Reading Performance. Changes to 5.17 of Section M, which the IGT UNC currently points to under with regards to Performance Assurance or Class 2 and 3, will automatically apply under the IGT UNC. The Code Administrator will continue to monitor and assess the impact of any changes once legal text is available. September 2025 - The Workgroup Report for this Modification is now due to be presented to UNC Panel in September 2025. There is currently no legal text for this Modification. Therefore, the IGT UNC Code Administrator cannot confirm how this Modification may impact IGTs or the IGT UNC. However, based on the proposal form, there will likely be automatic application of changes to 5.17 of Section M. The Code Administrator will re-assess the impacts once Legal Text is available. January 2026 - The Code Administrator has reviewed the legal drafting and any changes to 5.17 of Section M will automatically apply under the IGT UNC. However, there are no changes to the IGT UNC required. Consultation open for responses until 6th February.
0908 |  | Removal of DNO meter reading obligations resulting from non-provision of a Valid Meter Reading | Wales & West Utilities | 2025-03-07 | Live | Authority Direction | Distribution | Allocated to Workgroup | Report to Panel | 2026-02-19 |  | This Modification will remove the DNO obligation, in Transportation Principal Document section M 5.10, to obtain a meter reading (commonly called the “must read” obligation) following non-provision of a Valid Meter Reading by a Shipper. Impact on the IGT UNC should the provisions be removed from UNC completely as the IGTs still use the Must Reads process. Note that IGT177, once implemented, will mean that there is no impact on the IGT UNC. April 2025: At the April UNC Workgroup meeting, the Proposer advised that Transporters have an obligation to obtain a must-read if a Shipper fails to obtain a read for Class 2, 3, and 4 sites. It was noted that the obligation dates back to when Transporters were considered “guardians of the settlement system”. This is no longer the case. Transporters no longer provide meter read services and, in some instances, never have. Wales and West Utilities initiated a review group (0812R) to assess alternatives to the must-read arrangements. The Workgroup were advised that the Modification may have an impact on IGT UNC as the IGTs have their own “must read” arrangements under IGT UNC and noted that IGTs may raise a Modification to address this. The Code Administrator will monitor the Modification until impacts are known. June 2025 - BUUK have raised IGT177 to maintain existing obligation on IGTs to obtain a meter reading (commonly called the “must read” obligation) following non-provision of a Valid Meter Reading by a Shipper, by removing reference to UNC TPD M 5.10 from IGT UNC Part E – Meter Reading, 11 (Failure to obtain readings), and aligning the total relevant text within the IGT UNC. July 2025 - The IGT UNC Workgroup have concluded their work on IGT177. They have confirmed that whilst IGT177 will have no impact on the UNC, it should be noted under UNC0908 would have an impact on the IGT UNC regardless of IGT177 and therefore impacts should be noted under that Modification. September 2025 - The IGT UNC Panel approved IGT177 under Self Governance. The Appeal Window for IGT177 will close on 19th September. If no appeals are received the Modification will be implemented on 26th September 2025. Once implemented, UNC0908 will not pose a direct impact to IGT UNC Code as the must read provisions will sit within the IGT UNC. October 2025 - IGT177 was implemented on 26th September 2025.
0907 | S | Extension to current maintenance period | National Gas Transmission | 2025-02-06 | Live | Self-Governance | Transmission | Industry Consultation | Report to Panel | 2026-02-11 |  | This Modification proposes to amend the current maintenance period from 01 April to 31 October to 01 March to 30 November. No direct Code impact but IGT UNC Part H, 2.2 says, “The Pipeline Operator will use reasonable endeavours to co-ordinate its Maintenance Programme with the maintenance of the Large Transporter System in accordance with Section L4 of the UNC.”. L4 is System Maintenance.
0896 |  | Reducing the current Code Cut-Off Date (Line in the Sand) from 3 to 4 years to 2 to 3 years | SEFE Energy | 2024-10-04 | Live | Authority Direction | Distribution | Awaiting Implementation | Implementation | 2026-04-01 |  | This Modification proposes to reduce the existing Code Cut-Off Date (Line in the Sand) from 3 to 4 years to 2 to 3 years. Impact on IGT Parties as a result of changes to AQ process. No IGT UNC Code impact. April 2025: This Modification was amended on 24th April 2025. June 2025 - This Modification was extended by 2 months at the May UNC Panel. The UGT UNC Code Administrator has found a reference to the amended term in IGT UNC Section E, 21 (Updated Meter Readings). This paragraph makes a direct reference to TPD Section M, 5.16 which applies the use of Code Cut-Off Date. So any changes to the definition will directly pass through and apply under the IGT UNC. July 2025 - This Modification is currently out for industry consultation, closing on 10th July 2025 . September 2025 - Modification approved by the Authority in August 2025. Implementation TBC. January 2026 - Expected implementation date of 1st April 2026
0890 |  | Update to AQ Correction Processes - Request for Adjustments (RFA) AQ Change | Centrica | 2024-08-06 | Live | Authority Direction | Distribution | Awaiting Implementation | Implementation | TBC | 2025-03-20 | This Modification proposes to add a further ‘eligible cause’ to the Annual Quantity (AQ) amendment process within TPD G2.3.21. Impact on IGT Parties as a result of changes to AQ process. No Code impact anticipated. April 2025: Modification amended and published on 18th March. Amended Modification will be considered at UNC Workgroup on 27th March. Modification was amended again on 25th April. July 2025 - Xoserve contacted the IGT UNC Code Administrator advising of changes to the Modification that might alter the impacts of this Modification. The Code Administrator is currently assessing the legal drafting and will update the Workgroup at its July meeting. September 2025 - Modification approved by the Authority in August 2025. Implementation TBC.
0886 |  | Amend the Code Cut-Off Date to a Rolling 3-Year Period | SSE Energy Supply Limited | 2024-06-28 | Live | Authority Direction | Distribution | Awaiting Implementation | Implementation | 2026-04-01 |  | The purpose of the modification is to shorten the code cut-off date (or line in the sand) from a 3 to 4-year period to a monthly rolling 3-year period. Impact on IGT Parties as a result of changes to AQ process. No IGT UNC Code impact. April 2025:Modification was amended on 25th April 2025 June 2025 - This Modification was extended by X months at the May UNC Panel. The UGT UNC Code Administrator has found a reference to the amended term in IGT UNC Section E, 21 (Updated Meter Readings). This paragraph makes a direct reference to TPD Section M, 5.16 which applies the use of Code Cut-Off Date. So any changes to the definition will directly pass through and apply under the IGT UNC. July 2025 - This Modification is currently out for industry consultation, closing on 10th July 2025 . September 2025 - Modification approved by the Authority in August 2025. Implementation TBC. January 2026 - Expected implementation date of 1st April 2026
0876 | S | Updates to the Annual Quantity (AQ) amendment process. | SEFE Energy Limited | 2024-04-29 | Live | Self-Governance | Distribution | Awaiting Implementation | Implementation | TBC |  | This Modification proposes to make updates to the AQ amendment process within TPD G 2.3. Specifically adding clarity around the use of “eligible cause” G2.3.21 (b) (change in Consumer Plant), as well as ensuring a process for managing instances of misuse across all “eligible causes” where identified. March 2025: Panel determined that this Modification should go back to Workgroup for 3 months, with the Workgroup Report back to Panel in June 2025. July 2025 - The Code Administrator has reviewed the UNC Changes and there is no IGT UNC Code impact. However, the updates made to the AQ amendments process will apply to IGT sites as well as DNO sites as a result of a general reference to TPD G 2.3. The UNC Modification is current out for industry consultation closing on 10th July 2025. September 2025 - Approved by the UNC Panel in August. Implementation Date TBC.

## Watchlist (Closed) (hidden)
CLOSED LIST
Mod Ref |  | Modification Title | Proposing Organisation | Date Raised | Live/Closed | Category | Workgroup | Current Status | Next Stage | Key date* | Legal Text Provider | IGT UNC Workgroup Update / Current Status
0867 |  | Gas Demand Side Response (DSR) Aggregation Arrangements | National Gas Transmission | 2024-01-08 | Closed | Modification | Transmission | Withdrawn | End of process | 2024-05-01 | National Gas Transmission | They may require a consequent IGT mod if implemented.
0865 | S | Permitting DNOs to charge Shippers negative Supplier of Last Resort (SoLR) unit rates | Wales & West Utilities | 2023-12-05 | Closed | Self-Governance | Distribution | Implemented | Effective Date | 2024-03-08 |  | UNC TPD (Transportation Principal Document) Section Y part B only permits Distribution Network Operators (DNOs) to charge positive unit rates to Shippers, this modification permits negative rates.
0863 | S | Erroneous Transfers Exception Process | SEFE Energy Limited | 2023-10-26 | Closed | Modification | Distribution | Withdrawn | End of process | 2024-05-21 | 2023-11-16 | To provide a remedy for Erroneous Transfers that have failed to be progressed (exceptions) within a reasonable period to be proactively managed by the Central Data Services Provider (CDSP). Question to Workgroup - Should this be a REC modification?
0861 |  | Clarification of Provisions Regarding Utilisation of the System Without Holding System Capacity | National Gas Transmission | 2023-10-24 | Closed | Self-Governance | None | Implemented | Effective Date | 2024-04-16 |  | The purpose of this Modification is to acknowledge the extent of Transporters’ obligations to accept gas tendered for delivery to (or make gas available for offtake from) the System in the provisions that set out the charges payable where a User utilises the System without holding system capacity.
0859 | S | Reintroduction of the enhanced pressure service and increased MNEPOR for BBLC (as introduced by UNC0814) | National Gas Transmission | 2023-10-09 | Closed | Modification | Transmission | Implemented | Effective Date | 2024-04-19
0858 |  | Amendment to Network Entry Provision at Shell St Fergus Terminal | Shell | 2023-09-13 | Closed | Modification | None | Implemented | Effective Date | 2023-12-08 |  | This Modification will enable the current Wobbe Index upper limit that applies between National Grid and Shell at St Fergus to be increased on an enduring basis from 51.2 MJ/m3 to 51.4 MJ/m3.
0856 |  | Introduction of Trials for Non-Daily Metered (NDM) Demand Side Response (DSR) | National Gas Transmission | 2023-09-13 | Closed | Modification | None | Implemented | Effective Date | 2024-04-22 |  | Issued for a shortened 12 day consulation
0854 |  | Revision of Virtual Last Resort User and Contingent Procurement of Supplier Demand Event Triggers | National Gas Transmission | 2023-08-04 | Closed | Modification | Transmission | Implemented | End of process | 2024-05-22 | National Gas Transmission | The UNC Modification Panel has considered this new Modification, at their meeting on Thursday 17 August 2023 and highlighted that there is a potential IGT-UNC impact.
0853 |  | CDSP permissions to facilitate implementation of UNC0701. | Northern Gas Networks | 2023-07-27 | Closed | Self-Governance | Distribution | Implemented | Effective Date | 04/11/2023 in line with UNC701 | Northern Gas Networks | Modification 0701 (Aligning Capacity booking under the UNC and arrangements set out in relevant NExAs), is being implemented in November 2023, should Shippers not reduce capacity in line with the NExA agreement they will be in breach of Uniform Network Code at this time. This Modification gives permission for the CDSP to reduce the capacity to align with the NExA should the Shipper not do so. Also includes administrative change re use of acronym NExA. At August Panel it was determined that this Modification should proceed to Consultation.
0852 | S | Shipper notification in relation to option exercise for Customer Demand Side Response | SEFE Energy Limited | 2023-07-25 | Closed | Modification | Transmission | Rejected | End of process | 2024-04-29 | National Gas Transmission | To require National Gas to notify the relevant Shipper in the event that a Customer Demand Side Response option is exercised. At August Panel it was determined that this Modification be issued to Workgroup with a Report to be presented to the January 2024 Panel.
0850 |  | Amendments to Allocation of Unidentified Gas Expert (AUGE) arrangements to introduce a new Residual Upstream Contributor | SEFE Energy Limited | 2023-07-07 | Closed | Modification | Distribution | Withdrawn | End of process | 2023-12-11 | Cadent | This Modification proposes to amend the existing Allocation of Unidentified Gas arrangements to introduce a new Residual Upstream Contributor that will be the new daily balancing factor for Unidentified Gas. | 2
0841 |  | Introduction of cost efficiency and transparency requirements for the CDSP Budget, and revisions to DSC change processes | British Gas | 2023-03-06 | Closed | Modification | Governance | Implemented | End of process | 2024-06-03 | Cadent | The purpose of this Modification is to improve the ability of UNC Parties to fulfill their obligation jointly to control and govern the CDSP on an economic and efficient basis (under UNC General Terms, Section D, 1.4.4), through the introduction of explicit requirements for efficiency, greater transparency of the Budget and revised governance processes. The Modification Panel has considered the Alternative Modification above, at their meeting on Thursday 19 October 2023 and highlighted that there is a potential IGT-UNC impact.
0836 | A | Resolution of Missing Messages following Central Switching Service implementation and integration with REC Change R0067. | Cadent | 2023-02-06 | Closed | Self-Governance | Distribution | Implemented | Effective Date | 18/12/2023 in line with RC0067 | Cadent | This Modification clarifies treatment and activities necessary when the CSS Registration Effective from Date does not align to that recorded in the UK Link system due to the issue whereby systems that interface with the Central Switching Service (CSS) have not received expected messages because they have not been generated, or because of issues in transmission or receipt of the messages. At August Panel it was determined that this Modification should proceed to Consultation.
0831 | S | Allocation of LDZ UIG to Shippers (Class 3 and 4) Based on a Straight Throughput Method | Brook Green Trading | 2023-03-06 | Closed | Alternate Modification | Distribution | Rejected | End of process | 2024-02-06 | Cadent | The purpose of this Modification is to remove the current AUGE process and create a permanent weighting table that encourages movement to Daily Metering, reduces levels of UIG and discourages risk premiums for customers.
0831 | A | Allocation of LDZ UIG to Shippers Based on a Straight Throughput Method | SSE | 2022-11-08 | Closed | Modification | Distribution | Rejected | End of process | 2024-02-06 | Cadent | The purpose of this Modification is to change the method by which unidentified gas (UIG) is allocated to Shippers from the current AUGE table of weighting factors to a throughput or universal allocation model. At August 2023 panel it was voted for the Modification to be deferred to September's panel rather than issue for Consultation.
0825 |  | Removal of the remaining Retrospective Asset, Address and Supply Point (RAASP) elements of the Retrospective Adjustment arrangements put in place under Modification 0434 | EDF Energy | 2022-10-10 | Closed | Modification | Distribution | Implemented | End of process | 2023-12-15 | Cadent | Removal of the remaining Retrospective Asset, Address and Supply Point (RAASP) elements of the Retrospective Adjustment arrangements put in place under Modification 0434 | 2023-06-15 | 2023-07-06 | 2022-05-19
0816 |  | Update to AQ Correction Processes | E.ON Next | 2022-08-08 | Closed | Self-Governance | Distribution | Implemented | Effective Date | 2024-02-24 | Scotia Gas Networks | This Modification was raised to add two further ‘eligible clauses’ to the Annual Quantity (AQ) amendment process within TPD G2.3.21 and to prevent AQ amendments being processed where there is no change in value to the AQ.Settlement Performance Obligations and Transportation Costs for Vacant sites. Report due to be taken to Panel in May 2023. Will be fully implemented into the IGT UNC by UNC modification. However one reference is now incorrect in the IGT UNC and this will need to be corrected. In Part C I Section 6 the reference to 2.3.22 should now read 2.3.23.
0811 | S | Shipper Agreed Read (SAR) exceptions process | SEFE Energy Limited | 2022-06-23 | Closed | Self-Governance | Distribution | Implemented | Effective Date | 2024-02-24 | Wales & West Utilities | Any solution identified in the UNC that processes at Supply Point level will likely require a modification in the IGT UNC to effect the solution within the IGT UNC similarly. The FMR was presented to Panel on 19th January 2023 and the Panel determined that this Modification should be implemented on a date to be confirmed. Will be implemented in the IGT UNC by UNC drafting

## IGT UNC Equivalent
Correct as of 05/02/2026
UNC Mod Ref | Modification Title | Proposing Organisation | Date Raised | Current UNC Status | Next UNC Stage | Key date | IGT UNC Mod Ref | Current IGT UNC Status | Next IGT UNC Stage | Key date | IGT UNC Workgroup Summary
0922 | CDSP Obligations required for the introduction of the Gas Shipper Obligation |  |  |  | Report to Panel | 2026-07-16 | IGT180 | Allocated to Workgroup | Report to Panel | 2026-07-16 | February 2026: IGT180 was raised by BUUK on 15th January 2026. This Modification will be progressed in line with UNC0922 and will be considered via Joint Workgroup.
0921 | Broadening the definition of the Data Permissions Matrix to align with disclosure of UK Link Gemini data |  |  |  | Report to Panel | 2026-05-21 | - | Seeking Proposer | - | - | This Modification will impact the IGT UNC. A change is required to Part N2.5.1(b) to align the IGT UNC definition of Data Permissions Matrix to align with the changes under 0921.
0914 | Refining the Class 3 EUC1 read submission rules introduced through Modification 0700 |  |  |  | Report to Panel | 2026-03-19 | - | Seeking Proposer | - | - | February 2026: This Modification will impact the IGT UNC.A change is required to Part E 9.1 to change a referece to "Section M 5.8.6" to "Section M5.8.4" as a result of re-numbering.
0887 | Facilitating Bi-Directional Connections Between IGT Pipelines and the NTS | National Gas Transmission | 2024-07-18 |  | Implementation | TBC | IGT176 | Implementation | - | TBC | This Modification was raised as an alternative to 0871. However, the UNC Panel determined that it was an extension of the 0871 solution and voted that the Modification should be separate and not an alternative. This Modification is likely to impact IGTs and the IGT UNC and seeks to clarify the treatment of energy entering the NTS after entering an IGT network. April 2025: The IGT UNC Workgroup briefly discussed the Modification at a high level. The initial draft legal text changes are expected ahead of the May Workgroup meeting, where the Workgroup are expected to consider the detail of the Moidifcaiton. June 2025: FMR for UNC0887 is due to be presented to the UNC Panel in June. July 2025: The IGT176 Workgroup Report will be brought to Workgroup in July so that work can begin on finalising the document. UNC0887 was recommended for approval by the UNC Panel and submitted to Ofgem on 20th June 2025. September 2025 - UNC0887 was approved by the Authority in August 2025. IGT176 was issued to the Authority on 2nd September 2025. January 2026: Ofgem approved IGT176 on 2nd December 2025. February 2026: Implementation TBC
0884 | Extending the PC4 Read Submission Window |  |  |  | Implementation | TBC | IGT178 | Awaiting Implementation | Implementation | TBC | Under UNC TPD, M, 5.9.4, Shippers have 25 Supply Point Systems Business Days (SPSBD) after the read date to submit a read for settlement. Where there's an issue preventing the read from being validated, and that issue is not resolvable within the 25 SPSBD timeframe, the read becomes unusable. This is problematic for meter reads that are hard to retrieve. This Modification seeks to extend the window beyond 25 SPSBDs. This modification was amended on 22nd October. Changes under UNC Mod to TPD, M, 5.9.4 will automatically apply under the IGT UNC, However no changes are made to the IGT UNC Code to enable the UNC Modification. December 2024: WG discussions over how this Modification will impact the current IGT UNC Must Read and PC4 Read Submission Window processes. Xoserve and Centrica took an action to look into this Modification further. February 2025: The CA met with the UNC Modification Proposer at the end of December. The Proposer is aware of the possible impacts to the IGT UNC and that a change to the submission window may impact Must Reads for IGTS, which have specific timescales within Code. March 2025: The CA has written out to IGT UNC Parties to advise of the impacts identified by the IGT UNC Workgroup. This was also forwarded to the INA and brought up at their recent meeting. April 2025: A sponsor has come forward for the IGT UNC Modification. They have indicated that they plan to submit the Proposal form ahead of the April IGT UNC Panel meeting. UNC 0884 was amended on 24th April September 2025 - BUUK have raised IGT178 to align the must read submission window with the revised PC4 Submission Window. November 2025: UNC0884 has been approved by the Authority and IGT178 was approved by the Panel under Self-Governance. February 2026: UNC0884 and IGT178 will be implemented on 27th February 2026.
0854 | Revision of Virtual Last Resort User and Contingent Procurement of Supplier Demand Event Triggers | National Gas Transmission | 2023-08-04 | Implemented | Effective date | 2024-05-22 | TBC | Sponsor found, awaiting Proposal Form submission | TBC | TBC | UNC legal text will impact on the IGT UNC. Mod mitigates DN risk. Similar risk may be identified for IGTs which would require an IGT UNC mod for the same purpose. It is not believed that the UNC legal text will impact the IGT UNC, however, the Code Administrator will review the UNC legal text to understand if there are any impacts. IGT's will need to decide if they want a similar mod to cover off their own risk if they believe that they have a risk to themselves. The CDSP confirmed that the solution for 0854 was going to apply to both GT and IGT sites, it will apply to any sites that are owned by the sanction shipper, slash user premises termination user. The CA reviewed the modification and, along with the WG, determined that a Modification to the IGT UNC is required. February 2025: IGT UNC Modification Proposal was expected for pre-Modification discussion at February WG. Due to extenuating circumstance this Modification will now be discussed at the March Workgroup meeting. March 2025: This Modification has been deferred to the next IGT UNC Workgroup meeting. April 2025: A sponsor has come forward for the IGT UNC Modification. They have indicated that they plan to submit the Proposal form ahead of the April IGT UNC Panel meeting. January 2026: The Code Administrator is currently in talks with a new sponsor and are hoping to update the Workgroup on progress made at the January 2026 meeting.
0843 | Establishing the Independent Shrinkage Charge and the Independent Shrinkage Expert | OVO Energy | 2023-04-06 | Allocated to Workgroup | Authority Decision | TBC | IGT165 | Authority Decision | TBC | TBC | February 2025: Legal Drafting for IGT165 to be considered at February WG. March 2025: The updated legal text and draft Workgroup Report for IGT165 will be considered by the IGT UNC Workgroup. Next steps include: - Final review of version the Modification - Final Review of the updated Legal Text with the Legal Text being provided at least 5 days ahead of the next meeting - Review of the ROM - Finalise Workgroup Report April 2025: The updated version of the IGT165 Legal Text and Workgroup Report was be provided to parties ahead of the April 2025 Workgroup meeting. The Workgroup Report was due to be presented to the IGT UNC Panel at its April meeting. However, the UNC0843 Workgroup Report is now targeted at the May UNC meeting. Therefore, the Code Administrator recommends that the Workgroup Report for IGT165 be presented to the IGT UNC Panel in May as well. April 2025: The final version of the IGT165 Workgroup Report will be considred at the May meeting. June 2025: IGT165 Workgroup Report was presented to UNC Panel in May. The Modification is currently out for industry consultation until 18th July 2025. The IGT UNC Panel considered the IGT165 Workgroup Report in May. This Modification will soon be issued for consultation, also closing on 18th July 2025. Both Modificaions will be brought back to Panel in August. July 2025: Both Modifications are currently out for industry consultaiton. Both consultations close on 11th July 2025. Both Modifications are scheduled to return to their respective Panels in August 2025 . September 2025 - Both Modifications have been issued to the Authority. November 2025: Ofgem have indicated that they are looking to make a decision on these Modifications by the end of this year. February 2026: Ofgem have advised the Code Administrator that their decisions on IGT165 and UNC0843 have been delayed but were unable to provide an updated expected decision date.

## Live Review Groups
Correct as of 05/02/2026
Mod Ref |  | Modification Title | Proposing Organisation | Date Raised | Category | Workgroup | Current Status | Next Stage | Key date* | IGT UNC Workgroup Summary
0879 | R | Review of current Supply Meter Point Classes (Class 1,2,3 and 4). | Centrica | 2024-05-24 | Closed | Distribution | - | - | 2025-10-16 | November 2024: - The most recent UNC Workgroup Meeting was held on 24th October 2024. The Workgroup briefly discussed the scope of the solution, with the forward work plan deferred. The next meeting is planned for 15th November 2024. December 2024: 4 week consultation completed for this Review. 9 responses were received, which were discussed at the 15th November 2024 meeting. Topic for discussion have been identified based on responses. A number of confidential responses were provided. The CA recommends parties review the documents from the 15th November 2024 meeting. Next meeting is scheduled for 30th January 2025. March 2025: The UNC Workgroup considered classes 2 and 3 in the February meeting. CDSP to revisit Class 2/3 and introduce Class 4. June 2025: Work on this review picked up again in May, the Workgroup considered classes 2 and 3 further as well as introdudec Class 4. The Workgroup also discussed the butterfly effect and cascading dependencies, assuptions and review scope. July 2025: Work on this review continues, with the Workgroup discussing classes 2, 3 and 4. There was also some discussion on Daily Read Equipment (DRE) Faults (DM Drift). The Code Administrator continues to recommend that IGTs get involved in this group and/or follow the outputs to stay up to date. October 2025 - Draft Workgroup Report presented to Workgroup in September. There are a number of potential Modifications that have been proposed by the Workgroup. The Code Administrator recommends parties review the report. The Code Administrator will review and engage on the Modifications raised. January 2026: The Panel has closed this review.
0849 | R | Commercial Framework Review to Enable Hydrogen Blending | National Gas Transmission | 2023-05-09 | Closed | Other | - | - | 2025-11-20 | To review the market principles and existing commercial framework in order to assess their compatibility with blending hydrogen into the networks and explore the required amendments where necessary. Ensuring the amended regime is simple and easy to implement whilst also remaining adaptable and consistent with relevant obligations. KPMG will be providing project management support for the project. November 2024: The last 3 UNC Workgroup meetings have been cancelled. The next scheduled meeting for this Review is on 13th December 2024. February 2025: The December UNC Workgroup meeting went ahead as scheduled, we recommend IGTs remain informed as the outputs of this Review will likely impact the IGT UNC. March 2025: The UNC Workgroup considered the Design Stage process, Component Definitions, Locations, Capacity Terms, and a Request for Information. They considered the feedback provided by Workgroup and to update the presentation pack to include the detailed definitions requested in respect of ‘capacity’ for further consideration by the Workgroup. The next meeting will continue to cover the topic of Capacity and Connections. July 2025: The next Workgroup meeting will be on 29th July and will cover LDZ level blending, NTS level blending and all remaining issues. January 2026: The Panel has closed this review.

## UNC Modification IAs
IGT UNC Impact Assessments (IAs)
Correct as of 05/02/2026
Mod Ref |  | Modification Title | Proposing Organisation | Latest IA Date | Notes / Summary of IA Discussions | IA Outcome | Modification Required | Modification Agreement Date | IGT UNC Modification Proposer | Additional Comments / Updates
0922 |  | CDSP Obligations required for the introduction of the Gas Shipper Obligation |  | 2025-02-05 | The Gas Shipper Obligation (GSO) is intended to be the long-term funding mechanism for initial hydrogen production projects funded through the Hydrogen Production Business Model (HPBM). The GSO charge will be placed on Shippers based on the quantity of gas they ship to customers. The GSO scheme will be administered by the GSO Administrator (who is expected to be the Low Carbon Contracts Company (LCCC), subject to formal appointment through regulations) and will be outside of the UNC. This Modification will create obligations on the Central Data Service Provider CDSP to provide services to the GSO Administrator to support the implementation of the GSO, including a period of live data testing. It is proposed that a subsequent Modification is developed and will be implemented to ensure the CDSP Obligations endure following implementation of the GSO legislation. This Modification will impact the IGT UNC. IGT180 has been raised by BUUK and will be progressed in line with UNC0922. | Code Impact | Yes | 2025-02-05 | BUUK | -
0921 |  | Broadening the definition of the Data Permissions Matrix to align with disclosure of UK Link Gemini data |  | 2025-02-05 | At its August 2025 meeting, the DSC Contract Management Committee approved the Disclosure Request Report (DRR) ‘Green Gas Certification Scheme (GGCS) Biomethane Data’. This DRR permits the CDSP to provide Renewable Energy Assurance Limited (REA) with data from UK Link Gemini; specifically, allocated volumes of biomethane gas injected. The UNC definition of the Data Permissions Matrix (within General Terms section D) refers exclusively to categories of data maintained in the Supply Point Register. The Proposer is seeking to broaden this definition, to align with the release of UK Link Gemini data through this DRR. This Modification will impact the IGT UNC. A change is required to Part N2.5.1(b) to align the IGT UNC definition of Data Permissions Matrix to align with the changes under 0921. | Code Impact | Yes | TBC | TBC | -
0919 | S | Housekeeping amendments to TPD Sections B, G and M |  | 2025-02-05 | The Proposer has identified cross-referencing errors in TPD sections B and G, introduced through the implementation of Modification 0804, which this Modification proposal seeks to rectify. Additionally, the Proposer has identified Modification 0804 amendments to TPD section M which were subsequently undone in error, through the delayed implementation of UNC 0710S. This Modification proposal seeks to reinstate those changes. Separately, the Proposer has identified further amendments to section M, introduced through Modification 0692S, which were erroneously undone by an earlier version of the Code. This Modification proposal seeks to reinstate those changes and, in addition, correct a newly identified formatting error. No IGT UNC Code changes required, but changes to Section M5.9 will automatically apply under the IGT UNC via cross referencing. Changes to Section B 4.7 will not result in a change to the IGT UNC as they are reference number changes only. | No Code Impact | No | - | - | -
0914 | S | Refining the Class 3 EUC1 read submission rules introduced through Modification 0700 |  | 2025-02-05 | This Modification proposes the removal of the batch read validation rules introduced under Modification 0700 for Class 3 EUC1 reads. This would allow daily reads for Class 3 EUC1 to be submitted and validated without the current restrictions. This Modification will impact the IGT UNC. A change is required to Part E 9.1 to change a referece to "Section M 5.8.6" to "Section M5.8.4" as a result of re-numbering. | Code Impact | Yes | TBC | TBC | -
0909 | S | Refining the Class 2 Individual Valid Meter Reading Requirement Performance Measures |  | 2025-02-05 | The purpose of this Modification is to clarify the obligations on Shipper Users regarding Class 2 Meter Reading Performance. Changes to 5.17 of Section M will automatically apply under the IGT UNC. However, there are no changes to the IGT UNC required. Consultation open for responses until 6th February. | No Code Impact | No | - | - | -
0909 | S | Refining the Class 2 Individual Valid Meter Reading Requirement Performance Measures |  | 2025-02-05 | The purpose of this Modification is to clarify the obligations on Shipper Users regarding Class 2 Meter Reading Performance. Changes to 5.17 of Section M will automatically apply under the IGT UNC. However, there are no changes to the IGT UNC required. Consultation open for responses until 6th February. | No Code Impact | No | - | - | -
0907 | S | Extension to current maintenance period |  | 2026-02-05 | This Modification proposes to amend the current maintenance period from 01 April to 31 October to 01 March to 30 November. No direct Code impact but IGT UNC Part H, 2.2 says, “The Pipeline Operator will use reasonable endeavours to co-ordinate its Maintenance Programme with the maintenance of the Large Transporter System in accordance with Section L4 of the UNC.”. L4 is System Maintenance. | No Code Impact | No | - | - | -

## Closed Impact Assessments
IGT UNC Impact Assessments (IAs)
Correct as of 05/02/2026
Mod Ref | Column1 | Modification Title | Proposing Organisation | IA Date | Notes / Summary of IA Discussions | IA Outcome | Modification Required | Modification Agreement Date | IGT UNC Modification Proposer | Additional Comments / Updates
0911 | S | Amendment to DSC to introduce Shipper Assurance Audit (ISAE) |  | 2025-06-30 | This Modification proposes an amendment to the DSC to introduce a periodic Shipper Assurance Audit (International Standard on Assurance Engagements (ISAE) No IGT UNC Impact | No Code Impact | None | - | -
0910 | S | Amendment to DSC T&Cs to include a requirement to provide data incident contact details |  | 2025-06-30 | This modification proposes an amendment to the DSC Terms and Conditions to include an obligation on Parties to provide and maintain contact details to be used in the event of a data incident or breach. IGT Party impact, no code impact, we do reference the DSC but not at a level that would result in an impact. | No Code Impact | None | - | -
0908 |  | Removal of DNO meter reading obligations resulting from non-provision of a Valid Meter Reading |  | 2025-06-30 | This Modification will remove the DNO obligation, in Transportation Principal Document section M 5.10, to obtain a meter reading (commonly called the “must read” obligation) following non-provision of a Valid Meter Reading by a Shipper. IGT177 implemented on 26th September 2025. UNC0908 will no longer impact the IGT UNC as the provisions for Must Reads is now sat within the IGT UNC for IGTs. | Code Impact | Yes | 2025-06-30 | BUUK
0884 |  | Extending the PC4 Read Submission Window | OVO Energy | 2025-06-30 | Under UNC TPD, M, 5.9.4, Shippers have 25 Supply Point Systems Business Days (SPSBD) after the read date to submit a read for settlement. Where there's an issue preventing the read from being validated, and that issue is not resolvable within the 25 SPSBD timeframe, the read becomes unusable. This is problematic for meter reads that are hard to retrieve. This Modification seeks to extend the window beyond 25 SPSBDs. IGT178 was raised by BUUK to align the IGT UNC with the UNC following the implementation of UNC0884: Extending the PC4 Read Submission Window. The reference within the IGT UNC to the number of Supply Point Systems Business Days (SPSBD) after the read date to submit a read for settlement needs to be updated to remain aligned. | Code Impact - | Yes | 2025-06-30 | BUUK | -
0887 |  | Facilitating Bi-Directional Connections Between IGT Pipelines and the NTS | National Gas Transmission | 2026-02-05 | This Modification was raised as an alternative to 0871. However, the UNC Panel determined that it was an extension of the 0871 solution and voted that the Modification should be separate and not an alternative. Both code modifications approved (UNC0887 and IGT176). | Code Impact - | Yes | 2025-02-13 | CNG
0896 |  | Reducing the current Code Cut-Off Date (Line in the Sand) from 3 to 4 years to 2 to 3 years | SEFE Energy | 2024-12-12 | This Modification proposes to reduce the existing Code Cut-Off Date (Line in the Sand) from 3 to 4 years to 2 to 3 years. No direct code impact but IGT UNC Section E, 21 (Updated Meter Readings) makes a direct reference to TPD Section M, 5.16 which applies the use of Code Cut-Off Date. So any changes to the definition will directly pass through and apply under the IGT UNC. | Automatic Appliacation - No Code Changes Nessary unless IGT Parties wish to deviate from what is proposed under the Mod | None | - | - | Code Administrator will monitor Modificaiton until Legal Drafting is finalised to ensure there has been no scope creep that might result in a Code impact.
0890 |  | Update to AQ Correction Processes - Request for Adjustments (RFA) AQ Change | Centrica | 2025-06-30 | This Modification proposes to add a further ‘eligible cause’ to the Annual Quantity (AQ) amendment process within TPD G2.3.21. Potential impact on IGT UNC Parties as a result of changes to AQ process. Potental impact to Code identified. The Code Administrator is currently investigating this and will continue to engage with Xoserve who highlighted the most recent updates to the drafting. | Automatic Appliacation - Possible Code Changes need, Current in discussions with Xoserve | TBC | TBC | TBC
0886 |  | Amend the Code Cut-Off Date to a Rolling 3-Year Period | SSE Energy Supply Limited | 2025-06-16 | The purpose of the modification is to shorten the code cut-off date (or line in the sand) from a 3 to 4-year period to a monthly rolling 3-year period. No direct code impact but IGT UNC Section E, 21 (Updated Meter Readings) makes a direct reference to TPD Section M, 5.16 which applies the use of Code Cut-Off Date. So any changes to the definition will directly pass through and apply under the IGT UNC. | Automatic Appliacation - No Code Changes Nessary unless IGT Parties wish to deviate from what is proposed under the Mod | None | - | - | Code Administrator will monitor Modificaiton until Legal Drafting is finalised to ensure there has been no scope creep that might result in a Code impact.
0876 | S | Updates to the Annual Quantity (AQ) amendment process. |  | 2025-06-30 | This Modification proposes to make updates to the AQ amendment process within TPD G 2.3. Specifically adding clarity around the use of “eligible cause” G2.3.21 (b) (change in Consumer Plant), as well as ensuring a process for managing instances of misuse across all “eligible causes” where identified. No direct code impact but the changes to Section G will automatically apply under IGT UNC governance if this Mod is implemented as we make a direct reference to TPD G2.3. | Automatic Appliacation - No Code Changes Nessary unless IGT Parties wish to deviate from what is proposed under the Mod | - | - | - | Code Administrator will monitor Modificaiton until Legal Drafting is finalised to ensure there has been no scope creep that might result in a Code impact.
0904 | R | Review of the profiling arrangements with respect to LDZ Shrinkage Quantity | Cadent | 2025-02-06 | No IGT UNC impacts expected as the Review only applies to LDZ Shrinkage arrangements – NTS Shrinkage (dealt with under a different process under code and licence) and any exploration of IGT shrinkage (exists as a concept in IGTAD but is not currently calculated or purchased by IGTs) do not form part of this review. Recommend removing from the watch list. | No code change required | - | - | -
0902 | R | EU Capacity Allocation Mechanism Network Code Review | National Gas Transmission | 2025-02-06 | No IGT UNC impacts expected, recommend removing from the watch list. | No code change required | - | - | -
0901 | R | Review of the arrangements for reservation of NTS Capacity | National Gas Transmission | 2025-02-06 | No IGT UNC impacts expected, recommend removing from the watch list. | No code change required | - | - | -
0899 | S | To ensure the suite of Network Exit Agreements (NExA) Modifications has been implemented, taking into account the changes introduced by 0804 | Northern Gas Networks | TBC | This Self-Governance Modification seeks to make corrections needed to numbering, and other minor typographical errors, to allow the complete and accurate implementation of Modification 0701- Aligning Capacity booking under the UNC and arrangements set out in relevant NExAs, Modification 0770 - Amendments to legal text numbering for UNC Modification 0701 and Modification 0853 - CDSP permissions to facilitate implementation of UNC0701, taking into account changes introduced in the interim by Modification 0804 - Consequential UNC changes for Switching SCR (REC 3.0).y Capacity. Discussion at November 2024 Workgroup indicated that changes are expected to the IGT UNC | Code changes required | Yes | 2024-12-12 | BUUK | Nessessary changes implemented under IGT175 in June 2025.
0898 | S | Amendment to Gas Quality NTS Entry Specification at the St Fergus Shell System Entry Point | Shell Energy Europe Limited | 2024-12-12 | This enabling Modification will facilitate a change to the current contractual carbon dioxide entry limit at the St Fergus Shell entry Point, through the Modification of a network entry provision contained within the Network Entry Agreement (NEA) between National Gas and Shell UK in respect of the St Fergus Shell Terminal. No impact anticipated for IGT UNC. | No code change required | - | - | -
0897 | S | Removal of Non-Obligated Entry Capacity from Capacity Neutrality | SSE | 2025-02-06 | Implementation of the Proposal would remove the Non-Obligated Entry Capacity Revenues from Capacity Neutrality Revenues. This would reduce the revenues flowing into Capacity Neutrality Revenues which are redistributed to Users in proportion to their Firm Capacity holdings as well as reducing transportation charges paid by Users. No impacts on the IGT UNC expected as a result of this Modification. Recommend removing from watch list. | No code change required | - | - | -
0895 | S | Replacing ‘Energy Networks Association’ with another publishing method | Wales & West Utilities | 2024-12-12 | The purpose of this Modification is to update the Gas Distribution Networks (GDNs) UNC obligation to publish two engineering documents on the ENA website to another method. This is necessary following the GDNs collective decision to leave the ENA and to ensure compliance with the UNC. No impact anticipated for IGT UNC. | No code change required | - | - | -
0894 |  | Facilitating Biomethane entry into the GDN by exporting methane from the GDN into the NTS via Compression | Cadent | 2024-12-12 | This Modification seeks to introduce new criteria of Offtake where gas flows into the National Transmission System (NTS) from the Gas Distribution Network (GDN), and to clarify the treatment of the associated energy. This Modification was amended on 26th September. Amendments are due to be considered by Workgroup in October. No impact anticipated for IGT UNC. | No code change required | - | - | -
0893 |  | Reintroduce NTS Capacity Surrender text and update TPD B2.12 | National Gas Transmission | 2024-12-12 | The title of TPD B2.11 (Surrender of NTS Entry Capacity) was mistakenly changed and two clauses under 2.11 were removed in error due to what appears to be an issue with the implementation of a Modification. This Modification seeks to reintroduce the original text that was erroneously removed and implement the changes contained within Modification 0796 as intended. No impact anticipated for IGT UNC. | No code change required | - | - | -
0892 |  | Update incorrect NTS Entry Capacity paragraph references and reintroduce Daily Auctions to Entry Overrun Charges | National Gas Transmission | 2024-12-12 | The purpose of this Modification is to reintroduce reference to Daily NTS Entry Capacity within the entry Overrun Charges section of the UNC and update incorrect paragraph references within TPD B section 2 - NTS Entry Capacity. Consideration by Panel deferred to November 2024. No impact anticipated for IGT UNC. | No code change required | - | - | -
0891 |  | Reintroduction of the enhanced pressure service and increased MNEPOR for BBLC (reintroduced by UNC0589 and introduced by UNC0814) | National Gas Transmission | 2024-12-12 | Panel recommended approval to the Authority No impact anticipated for IGT UNC. | No code change required | - | - | -
0889 |  | Clarifying Inclusion of the Reserve Price in the System Entry Overrun Charge | National Gas Transmission | 2024-12-12 | This Modification will introduce an explicit reference to the Reserve Price within TPD B2.13.3 the System Entry Overrun Chare to clarify the process. This modification was amended on 30th October No expected impact on the IGT UNC. | No code change required | - | - | -
0888 |  | Correction to the Assessment Period for Demand Side Response (DSR) Option Offers | National Gas Transmission | 2024-12-12 | This Modification seeks to correct drafting errors in Modification 0866S ‘Amendments to Demand Side Response (DSR) Arrangements in respect of National Gas Transmission’s (NGT’s) assessment period for DSR Option Offers. No expected impact on the IGT UNC. | No code change required | - | - | -
0885 |  | Amendment to Gas Quality NTS Entry Specification at the St Fergus SAGE System Entry Point | SAGE North Sea Limited | 2024-12-12 | This enabling Modification will facilitate a change to the current contractual oxygen limit at the St Fergus SAGE System Entry Point, through modification of a network entry provision contained within the Network Entry Agreement (NEA) between National Grid Gas plc and SAGE North Sea Limited (SNSL) in respect of the St Fergus SAGE Sub-Terminal. No impact anticipated for IGT UNC. | No code change required | - | - | -
0883 |  | Update to the Annual Quantity (AQ) amendment process for- Erroneous Domestic AQs | Centrica | - | This Modification has been withdrawn. | - | - | - | -
0882 |  | Transparency of non-standard Gas Quality parameters at new entry connections to the NTS | National Gas Transmission | 2024-12-12 | This Modification seeks to enable greater transparency where a new entry connection to the National Transmission System (NTS) requests a “non-standard” gas quality specification, outside of the published NTS specification. This is to be more consistent with the rules for consultation at existing sites, whilst not impacting the connection process timelines adversely. No expected impact to IGT UNC. This Modification was amended on 18th October, with updated business rules and published legal text | No code change required | - | - | -
0881 |  | Review and consolidation of UNC Transition Document TDIIC - Transitional Rules | National Gas Transmission | 2024-12-12 | This Modification seeks to review and remove obsolete transitional rules within UNC TDIIC Transitional Rules and introduce additional steps within TDI – General to enable easier reviewing and removal of expired Transitional Rules in the future. One change to the IGT UNC will be required as a result of this Modification. a Reference to TDIIC 1.3.8 will need to be removed as it is being removed under 0881. | Code changes required | Yes | 2024-12-12 | BUUK | Nessessary changes implemented under IGT175 in June 2025.
0880 |  | Amendment to Wobbe Index upper limit in the Network Entry Agreement at the York Entry Point | Centrica | 2024-12-12 | The Modification will enable the Wobbe Index upper limit set out in the York Network Entry Agreement between National Gas and Centrica Energy Storage to be increased from 51.2 MJ/m3 to 51.4 MJ/m3. Not expected to impact the IGT UNC. | No code change required | - | - | -
0876 | S | Updates to the Annual Quantity (AQ) amendment process. | SEFE Energy Limited | 2024-12-12 | It is not believed that the IGT UNC requires updating as a result of this Modification as it points to the UNC for this part of the code, however, the updates made to the AQ amendments process will apply to IGT sites as well as DNO sites. | No code change required | - | - | -
0875 | S | Minor amendment to the Vacant Site exit process & 0819 Legal Text re-numbering | Centrica | 2024-12-12 | CDSP had viewed the initial legal text for 0875 and did not think there are any impacts to the IGT UNC because the relevant sections of the IGT UNC text, Sections 6 and 21, both already refer to the relevant sections of the UNC, so when these UNC sections are updated through this new modification, the updates will automatically apply to IGT sites. It was clarified that there is an impact from UNC 0875 on IGT sites, but not the IGT code. No IGT UNC Code changes required but there are changes to sections referenced in the IGT UNC which will automatically apply under the IGT UNC once implemented. (G2.3) | Automatic Application - No Code Impact | - | - | -
0874 | S | Amendments to UNC to align with Gas Demand Forecasting Methodology | National Gas Transmission | 2024-12-12 | Approved waiting implementation. No IGT UNC Code impact, though changes have been made to UNC Section C and H, which are referenced within the IGT UNC, in some instances in whole and so changes might automatically apply under the IGT UNC. | No Impact | - | - | -
0872 | S | Single-sided Nominations for clearing houses of gas exchanges | European Commodity Clearing AG | 2024-12-12 | No anticipated impact on IGT UNC, to be closed. | No code change required | - | - | -
0870 |  | Amendments to Wobbe Index and Calorific Value Lower Limits at NTS System National Transmission System (NTS) Entry Points. | National Gas Transmission | 2024-12-12 | No anticipated impact on IGT UNC, to be closed. | No code change required | - | - | -
0868 |  | Gas Demand Side Response (DSR) Aggregation Arrangements | SEFE Energy Limited | 2024-12-12 | No anticipated impact on IGT UNC, to be closed. | No code change required | - | - | -
0865 |  | Permitting DNOs to charge Shippers negative Supplier of Last Resort (SoLR) unit rates | Wales & West Utilities | 2024-03-14 | IGT sites included through UNC governance and not at supply point level. UNC0865 has now been implemented. The Workgroup doesn't believe that there is any impact. | No Impact | - | - | - | -
0864 |  | Update of UNC Code Communication Methods | National Gas Transmission | 2024-12-12 | No anticipated impact on IGT UNC, to be closed. Should be noted that an independent IGT UNC Modification has been raised to make simular changes but this is stand alone. | No code change required | - | - | -
0863 | S | Erroneous Transfers Exception Process | SEFE Energy Limited | 2024-03-14 | Indications from the Proposer that the mod will be raised in the REC. Mod not yet withdrawn. This Mod is still on hold in the UNC until further notice. | Withdrawn | - | - | - | -
0856 |  | Introduction of Trials for Non-Daily Metered (NDM) Demand Side Response (DSR) | National Gas Transmission | - | IGT sites are expected to be included in the trials. Sent out for shortened consultation. Panel did not recommend implementation. Gone to Ofgem for decision. Proposer have decided to cease the trials so no IGT Mod required at this time. | No Impact | - | - | - | -
0855 |  | Settlement Adjustments for Supply Point Meter Points impacted by the Central Switching System P1 Incident. | SEFE Energy Limited | - | See UNC 0836. Modification IGT171 has now been raised. | Code & Party Impact | Yes | - | SEFE | Modification IGT171 has now been raised.
0853 |  | CDSP Permissions to facilitate implementation of UNC0701. | Northern Gas Networks | 2023-08-10 | The IGT Workgroup, at it's August meeting agreed that an IGT Modification would be required to cover the changes from UNC0701 and UNC0853 and to allow IGT's to manage the NExA implications. A proposer volunteered to sponsor this Modification and will work with the CA to raise and develop this. IGT169 has now been raised. | Code & Party Impact | Yes | - | MUA | Legal drafting in the IGT UNC needed in response to the implementation of UNC 0701 and the secondary intention of UNC0853 to allow the CDSP to validate using the relevant information
0852 |  | Shipper notification in relation to option exercise for Customer Demand Side Response | SEFE Energy Limited | 2023-08-10 | The section of the legal text added by the proposer in relation to the Shipper Notification would be encompassed in the IGT UNC by the legal text in IGT167. | Code & Party Impact | Yes | - | - | encompassed in the IGT UNC by the legal text in IGT167.
0850 |  | Amendments to Allocation of Unidentified Gas Expert (AUGE) arrangements to introduce a new Residual Upstream Contributor | SEFE Energy Limited | 2023-08-10 | Modification is at early stages, it has been to Panel and assigned to Workgroup. There were some questions raised on the IGT side which the proposer would take away and review. Proposer to attend September IGT Workgroup. This has now been withdrawn by the proposer. | No Impact | - | - | - | -
0845 |  | Enhancements to Demand Side Response (DSR) Arrangements including a D-5 Product | National Gas Transmission | 2023-07-13 | This modification is still under development and an equivalent mod IGT167 has been raised in the IGT UNC. | Code & Party Impact | Yes | - | BUUK
0844 |  | Enabling Direct Contractual Arrangements with Consumers for Demand Side Response | National Gas Transmission | 2023-07-13 | The IGTs have not been marked as an impacted group. The intention is for the modification to work on IGT Sites. This modification is still under development and an equivalent mod IGT167 has been raised in the IGT UNC. | Code & Party Impact | Yes |  | BUUK
0843 |  | Establishing the Independent Shrinkage Charge and the Independent Shrinkage Expert | OVO Energy | 2023-06-08 | WG initially considered the Modification during April 2023 meeting. The Proposer has indicated that they are happy to raise a Modification should there be an IGT/IGT UNC impact. The need for a Modification is dependant on how the UNC Mod Proposer sees Shrinkage Expert Role impacting IGTs/IGT UNC. This modification is still under development and an equivalent mod IGT165 has been raised in the IGT UNC. | Code & Party Impact | Yes | - | OVO | Proposer of UNC 0843 has indicated that they are keen to have the same obligations as the UNC with regards to Shrinkage. The UNC Modification Proposer has indicated that they are willing to raise a Modification to enable this. IGT UNC Modification IGT 165 raised
0842 |  | Gas Entry onto the Total system via an Independent Gas Transporter | SGN | 2023-07-13 | WG initially considered the Modification during May 2023 meeting. The UNC Modification Proposer and the Proposer of 0808 will discuss offline and engage with IGTs. Likely an impact but further information needed, which will be considered at the June 2023 meeting. CDSP advised that that they would look to consult IGT's on this Modification. IGT172 has now been raised. | Code & Party Impact | Yes | 2203-06-01 | Barrow Shipping | The Legal Draft provider for the UNC mod believes that title for the gas needs to be 'handed off' between the two codes. This will likely require an amendment to Section J of the IGT UNC IGT 172 has been raised
0841 | A | Introduction of cost efficiency and transparency requirements for the CDSP Budget, and revisions to DSC change processes | British Gas | 2023-11-10 | Cross-code implications anticipated as all parties of the IGT UNC are also parties in the DSC. 0841A has now been withdrawn. 0841 has just gone out for consultation - due back 7th March 2024. No IGT impacts identified. | No Impact | - | -
0836 | S | Resolution of Missing Messages following Central Switching Service implementation and integration with REC Change R0067. | Cadent | 2023-08-10 | The implications of this modification and related mod UNC0855 were discussed at the August Workgroup meeting. It was believed that the two UNC Modifications would require two equivalent IGT UNC Modifications. The implications of both UNC Mods would need to be fully understood by IGT UNC parties. The legal drafting for UNC0836 indicates that relatively small changes to the IGT UNC will be required. Specifically TPD Section G 5.9 and 5.18 will need to be referenced in the IGT UNC. UNC0836 was implemented 18/12/23. Modification IGT170 raised. | Code & Party Impact | Yes | 2023-08-10 | SEFE | Need to add Section G 5.9 and Section M5.18 of TPD into the IGT UNC so a modification will be required
0833 |  | Enabling Demand Side Response (DSR) Market Offers to be made by Non-Trading System Transactions | National Grid NTS | 2023-08-10 | The IGT UNC Panel, at its September meeting, agreed that a Modification is also needed to the IGT UNC as the Code Administrator has had confirmation from Xoserve that there are infact IGT sites on the system now that meet the eligibility criteria of the Modification. A sponsor for this Modification has approach the Code Administrator. We will continue to work with them in the new year to develop the nessessary changes to the IGT UNC. This modification will take into account 0822, 0833 and any other related DSR Modifications raised under the UNC. IGT167 Modification now been raised by BUUK and is out for consultation and due to go to an Extraordinary Panel on 17th August 2023. | Code & Party Impact | Yes | 2022-09-23 | Jenny Rawlinson, BUUK | Legal Drafting for the UNC modification removes / amends parts of TPD Section M 4. The IGT UNC points at the entirety of Section M 4, so the mod will be implemented into the IGT UNC.
0825 |  | Removal of remaining Retrospective Asset, Address and Supply Point (RAASP) elements of the Retrospective Adjustment Arrangements put in place under Modification 0434. | - | 2023-08-10 | At the May 2023 Workgroup it was established that an IGT Modification was not required. However, Legal text to be reviewed by Code Administrator. The Workgroup considered the impact of UNC0825 on the IGT UNC. Following discussion, it was widely agreed that no equivalent IGT UNC Modification would be required, as the relevant references to the UNC would still be accurate in the event that UNC0825 was implemented. Workgroup confirmed that this impacts the IGT sites but it doesn't need the IGT equivalent as there was never an original IGT Modification and this reverses out what the updated Retro was going to put in. Due to go to Panel and then consultation. Need to monitor. | No Impact | - | - | - | -
0808 |  | Reverse Compression | Barrow Shipping Limited | 2023-08-10 | WG considered the Modification following presentation from the Proposer. The WG agreed that based on the information provided there would not be an impact on the IGT UNC and therefore an IGT UNC Modification was not seen as being needed at this time. Still monitoring and seeking information as to whether there will be any impacts. | No Impact | - | - | -