## Introduction
IGT UNC Horizon Scanner
Date | 31st March 2026
Version | v1.14
Purpose | This document provides visibility of IGT UNC impacting industry activities, as well as the progression of Cross Code impacting Modifications. This document is owned by the IGT UNC Workgroup and is refreshed approximately monthly. Please refer to the IGT UNC Horizon Scanner page of the IGT UNC website for the most up to date version.
Contact | If you have any queries or comments about this Horizon Scanner, please contact the IGT UNC Code Administrator via email, IGTUNC@gemserv.com.
Uplift History | Reason for change | Date
v0.1 | Initial draft for Workgroup consideration | 2024-11-07
v1.0 | Uplift to approved working document | 2024-12-05

## Horizon Scanner
IGT UNC Horizon Scanner
|  |  | IMPACTS | [8 empty] | INDUSTRY CHANGE
Category | Activity | Description / Scope | IGT UNC | UNC | Other Codes | IGT | Shipper | Other Party | Risks / Issues | Current Status | Future Milestones / Key Dates | IGT Changes | UNC Changes | Other Code Changes | Central System Changes | Licences | Other Comments / Useful Context
Code Reform | Code Consolidation (GNC) | Introduction of GNC, which will involve the merging of IGT UNC and UNC. Designation of changes ahead of consolidation is expected. Further information on this will be noted when it is available. | Yes | Yes | CUSC DCUSA SQSS STC | Yes | Yes | All parties to impacted Codes | Introduction of inaccuracies, short notice changes, lack of party engagement. | Ofgem work is ongoing. Ofgem are looking to publish the Government and Ofgem response to the consultation on code manager licence conditions and code modification appeals to the CMA – a joint-DESNZ-Ofgem publication that sets the regulatory foundations of the reform, including the new code manager licence conditions. Planned date: By the end of March 2026 Ofgem are looking to publish transitional measures and consequential changes for Energy Code Reform phase 1 – establishing the transitional measures required to ensure a smooth move to the new model and day-one readiness, seeking stakeholder views on the required code changes. Planned date: By the end of March 2026 Ofgem are looking to publish a consultation on the second preliminary SDS. In April they will consult on their second SDS setting a clear and ambitious direction for industry on how codes must evolve to deliver strategic priorities for consumers and support the transition to net zero in the years ahead. Planned date: By end of April 2026 On 16 March, Ofgem published our decision on competitive code manager selection and updated our guidance on code manager selection. The decisions set out in this document are intended to enable us to run competitive code manager selection exercises in the second and third phase of energy code reform, if Ofgem determine that a competition would be in the best interests of the industry and consumers. Energy code reform: https://www.ofgem.gov.uk/consultation/energy-code-reform-competitive-code-manager-selection On 6 March 2026, Ofgem issued a call for expressions of interest to join the code consolidation workgroups (CCW) for phase 2, which are planned to begin later this summer. Ofgem are seeking participation from any person who is interested in helping us develop the modifications required to create a consolidated electricity commercial code or a consolidated gas network code. If you would like to express interest in participating in the CCW, please review the draft terms of reference and then let us know by emailing industrycodes@ofgem.gov.uk by 17 April 2026: https://www.ofgem.gov.uk/consultation/implementation-energy-code-reform-template-code-text On 6 March 2026, Ofgem published the Implementation of energy code reform: second decision. This decision sets out our approach to implementing the industry code governance reforms as set out in the Energy Act 2023. This document summarises respondents’ views on the Implementation of energy code reform: Second consultation and sets out our decisions. It also consults on the proposed code text for the future code modification process and the Stakeholder Advisory Forum (SAF), which reflects the policy positions in this document. Response deadline: 17 April 2026: https://www.ofgem.gov.uk/consultation/energy-code-reform-second-implementation-consultation | The interim milestones and timings of critical path activities for phase 1 codes are as follows: Spring / Summer 2025: Phase 1 bilateral and workgroups with the industry will be held for targeted policy topics. Later in 2025 / 1H-2026: Ofgem expect to consult on modification proposals for phase 1 codes. Implementation and assurance activities for phase 1 code manager candidates are expected to run during this period. Spring / Summer 2026: Phase 1 code manager appointments are expected. Commencing in 2026-27: Ofgem expected to publish minded-to decisions with respect to the identity of the phase 2 code managers, by the start of the subsequent implementation and assurance period. Below summarises the upcoming code reform publications, planned for 2025/26: • Autumn 2025: Decision on second implementation consultation • Winter 2025/26: Modification proposals consultation • Winter 2025/26: Decision on code manager licence conditions and code modification appeals to the CMA – in collaboration with DESNZ | Directed changes expected (timeline TBC) | Directed changes expected (timeline TBC) | Directed changes expected (timeline TBC) | TBC | Directed changes expected (timeline TBC) | Ofgem identified the following areas where they believed code provisions should be targeted for rationalisation and simplification as part of any Ofgem-led consolidation activity, using the transitional Ofgem powers granted by the Energy Act: • Common contractual framework • Contract boilerplate and defined terms • Party accession and exit • Code objectives • Code modification process • Code compliance • Credit cover arrangements • Dispute processes • Derogation provisions
Code Reform | SDS | Introduction of the Ofgem SDS, which is intended to set the direction of travel for the development of codes, in line with Ofgem's overarching vision for the sector. The SDS is required by the Energy act to contain a strategic assessment of government policy and developments which require modifications to the designated codes, and in preparing the SDS Ofgem must have regard to advice given by the NESO. | Yes | Yes | Yes | Yes | Yes | Yes | Risks and issues to be confirmed by Workgroup when more detail is available. | Ofgem work is ongoing. Ofgem are looking to publish a consultation on the second preliminary SDS. In April they will consult on their second SDS setting a clear and ambitious direction for industry on how codes must evolve to deliver strategic priorities for consumers and support the transition to net zero in the years ahead. Planned date: By end of April 2026 | The next formal SDS is expected to follow the appointment of code managers in 2026. | Directed changes expected (timeline TBC) | Directed changes expected (timeline TBC) | Directed changes expected (timeline TBC) | TBC | Directed changes expected (timeline TBC) | Ofgem currently do not propose to introduce an obligation to implement the SDS before code managers are in place, however, they have proposed the introduction of a standard prioritisation process for code panels which will support the introduction of the SDS (see 22nd August 2024 decision publication and recently issued consultation on preliminary SDS dated 31st January 2025). Decision on code governance arrangements and SDS: https://www.ofgem.gov.uk/decision/decision-preliminary-strategic-direction-statement-and-governance-arrangements-industry-codes
Code Reform | Code Governance | Changes to code governance (inc. matters relating to Code Managers, SAF, prioritisation, objectives, transition to new framework) will be done by Ofgem and with the permission of the SOS. | Yes | Yes | Yes | Yes | Yes | Yes | Risks and issues to be confirmed by Workgroup when more detail is available. | Ofgem Work Ongoing. Ofgem are looking to publish the Government and Ofgem response to the consultation on code manager licence conditions and code modification appeals to the CMA – a joint-DESNZ-Ofgem publication that sets the regulatory foundations of the reform, including the new code manager licence conditions. Planned date: By the end of March 2026 Ofgem are looking to publish transitional measures and consequential changes for Energy Code Reform phase 1 – establishing the transitional measures required to ensure a smooth move to the new model and day-one readiness, seeking stakeholder views on the required code changes. Planned date: By the end of March 2026 Ofgem are looking to publish a consultation on the second preliminary SDS. In April they will consult on their second SDS setting a clear and ambitious direction for industry on how codes must evolve to deliver strategic priorities for consumers and support the transition to net zero in the years ahead. Planned date: By end of April 2026 On 6 March 2026, Ofgem issued a call for expressions of interest to join the code consolidation workgroups (CCW) for phase 2, which are planned to begin later this summer. Ofgem are seeking participation from any person who is interested in helping us develop the modifications required to create a consolidated electricity commercial code or a consolidated gas network code. If you would like to express interest in participating in the CCW, please review the draft terms of reference and then let us know by emailing industrycodes@ofgem.gov.uk by 17 April 2026: https://www.ofgem.gov.uk/consultation/implementation-energy-code-reform-template-code-text | The interim milestones and timings of critical path activities for phase 1 codes are as follows: Spring / Summer 2025: Phase 1 bilateral and workgroups with the industry will be held for targeted policy topics. Later in 2025 / 1H-2026: Ofgem expect to consult on modification proposals for phase 1 codes. Implementation and assurance activities for phase 1 code manager candidates are expected to run during this period. Spring / Summer 2026: Phase 1 code manager appointments are expected. Below summarises the upcoming code reform publications, planned for 2025/26: • Winter 2025/26: Modification proposals consultation • Winter 2025/26: Decision on code manager licence conditions and code modification appeals to the CMA – in collaboration with DESNZ | Directed changes expected (timeline TBC) | Directed changes expected (timeline TBC) | Directed changes expected (timeline TBC) | TBC | Directed changes expected (timeline TBC) | Recent publications on matters of Code Governance: Consultation on Code Manager Selection: https://www.ofgem.gov.uk/sites/default/files/2024-11/Consultation_on_code_manager_selection.pdf Decision on implementation of Energy Code Reform: https://www.ofgem.gov.uk/decision/implementation-energy-code-reform-decision Decision on code governance arrangements and SDS: https://www.ofgem.gov.uk/decision/decision-preliminary-strategic-direction-statement-and-governance-arrangements-industry-codes Consultation on Code Manger Licence Conditions and Appeals: https://www.gov.uk/government/consultations/energy-code-reform-code-manager-licence-conditions-and-code-modification-appeals-to-the-cma Expressions of interest in Code Manager candidates: https://www.ofgem.gov.uk/call-for-input/expression-interest-invitation-code-manager-candidates
Code Reform | Pre-Consolidation Code Changes | Ofgem identified the following areas where Ofgem believed code provisions should be targeted for rationalisation and simplification as part of any Ofgem-led consolidation activity, using the transitional powers granted by the Act: • Common contractual framework • Contract boilerplate and defined terms • Party accession and exit • Code objectives • Code modification process • Code compliance • Credit cover arrangements • Dispute processes • Derogation provisions | Yes | Yes | Yes | Yes | Yes | Yes | Risks and issues to be confirmed by Workgroup. | On 6 March 2026, Ofgem issued a call for expressions of interest to join the code consolidation workgroups (CCW) for phase 2, which are planned to begin later this summer. Ofgem are seeking participation from any person who is interested in helping us develop the modifications required to create a consolidated electricity commercial code or a consolidated gas network code. If you would like to express interest in participating in the CCW, please review the draft terms of reference and then let Ofgem know by emailing industrycodes@ofgem.gov.uk by 17 April 2026: https://www.ofgem.gov.uk/consultation/implementation-energy-code-reform-template-code-text | The interim milestones and timings of critical path activities for phase 1 codes are as follows: Spring / Summer 2025: Phase 1 bilateral and workgroups with the industry will be held for targeted policy topics. Later in 2025 / 1H-2026: Ofgem expect to consult on modification proposals for phase 1 codes. Implementation and assurance activities for phase 1 code manager candidates are expected to run during this period. Spring / Summer 2026: Phase 1 code manager appointments are expected. Below summarises the upcoming code reform publications, planned for 2025/26: • Winter 2025/26: Modification proposals consultation • Winter 2025/26: Decision on code manager licence conditions and code modification appeals to the CMA – in collaboration with DESNZ | Directed changes expected (timeline TBC) | Directed changes expected (timeline TBC) | Directed changes expected (timeline TBC) | TBC | Directed changes expected (timeline TBC) | Ofgem identified the following areas where they believed code provisions should be targeted for rationalisation and simplification as part of any Ofgem-led consolidation activity, using the transitional powers granted by the Energy Act: • Common contractual framework • Contract boilerplate and defined terms • Party accession and exit • Code objectives • Code modification process • Code compliance • Credit cover arrangements • Dispute processes • Derogation provisions
Xoserve | Project Trident | Project Trident is an Xoserve project, looking to modernise UK Link, the platform they use to connect information, technology and communications systems for the retail gas market. UK Link is used and managed by Xoserve in its role as CDSP. It ensures the industry operates smoothly, effectively and efficiently, in accordance with the Uniform Network Code and its IGT equivalent. | TBC | TBC | TBC | TBC | TBC | TBC | Risks and issues to be confirmed by Workgroup. | Project Trident has launched a customer consultation on its preferred hypothesis. The preferred hypothesis is the option that is currently favoured over others based on research and evidence indicating that this best meets the needs of Project Trident, and no decision has yet been made. This consultation closed on Tuesday 12 September. https://www.xoserve.com/products-services/data-products/uk-link-system/project-trident/ https://www.xoserve.com/media/tmphcj2i/the-tide-xoserves-project-trident-newsletter-10.pdf | Standard support for the current version of the SAP platform that supports UK Link ends in 2027, with extended support available until 2030. It is estimated that Project Trident will run until 2028. | TBC | TBC | TBC | TBC | TBC | https://www.xoserve.com/products-services/data-products/uk-link-system/project-trident/ https://www.xoserve.com/media/ekhd0pqx/project-trident_pre-workshop-introductory-webinar-slides_v11.pdf
Xoserve | Service Line Review | Xoserve looking at amendments to the service lines, introduction of a new service line which will include a new charge for IGTs and splitting an element related to AUGE, PAC and PAFA and making it a 50/50 split in respect of charging. | TBC | TBC | TBC | TBC | TBC | TBC | Added by Workgroup - Detail to be confirmed. |  | Added by Workgroup - Detail to be confirmed | TBC | TBC | TBC | TBC | TBC
Digitalising the Energy System | Data Sharing Infrastructure | Introduction of a data sharing infrastructure, which is a minimum set of responsibilities, governance, functions and processes for secure, interoperable data sharing across the energy system. This activity covers the DSI Pilot, DSI MVP and Ofgem Guidance. | TBC | TBC | TBC | TBC | TBC | TBC | Risks and issues to be confirmed by Workgroup. | Ofgem and DESNZ vision for digitalisation of the energy sector, including policy and technical coordination, expected in Q1 2026. | Related Ofgem programme’s name has changed from Energy Data and Digitalisation to Energy System Digitalisation. Ofgem's Energy System Digitalisation page is provided below: https://www.ofgem.gov.uk/energy-policy-and-regulation/policy-and-regulatory-programmes/energy-system-digitalisation Project information for NESO DSI Pilot / MVP: https://smarter.energynetworks.org/projects/nia2_ngeso081/ https://www.neso.energy/document/353696/download Project information for NESO DSI / SSEN-T Component: https://smarter.energynetworks.org/projects/nia_shet_0053/ | TBC | TBC | TBC | TBC | TBC | Related Ofgem programme’s name has changed from Energy Data and Digitalisation to Energy System Digitalisation. Ofgem's Energy System Digitalisation page is provided below: https://www.ofgem.gov.uk/energy-policy-and-regulation/policy-and-regulatory-programmes/energy-system-digitalisation Project information for NESO DSI Pilot / MVP: https://smarter.energynetworks.org/projects/nia2_ngeso081/ Project information for NESO DSI / SSEN-T Component: https://smarter.energynetworks.org/projects/nia_shet_0053/ Digitalising the Energy System: https://www.gov.uk/government/publications/digitalising-the-energy-system Ofgem decision on the definition of ESD and DBP Guidance: https://www.ofgem.gov.uk/decision/decision-definition-energy-system-data-data-best-practice-guidance
Hydrogen | Hydrogen Strategy | The Government sees Hydrogen as a key support for the decarbonisation of the UK economy. In 2021, the UK government published its first Hydrogen Strategy, which aimed for 5GW of low carbon hydrogen production capacity by 2030 for use across the economy. Building on these proposals, the British Energy Security Strategy committed to doubling this 2030 hydrogen production capacity ambition to up to 10GW, with at least half coming from electrolytic production. The Government set out its decision to support the blending of up to 20% hydrogen by volume into the GB gas distribution networks in 2023. | TBC | TBC | TBC | TBC | TBC | TBC | Added by Workgroup - Detail to be confirmed | Added by Workgroup - Detail to be confirmed | Added by Workgroup - Detail to be confirmed | TBC | TBC | TBC | TBC | TBC
Hydrogen | RTSM Programme | In February 2024, a programme was established, to develop a modelling solution that will facilitate the introduction of a fair and equitable billing and settlement framework able to operate in a multi-gas system with varying CVs. The RTSM programme aims to develop an integrated solution for the processes of characterising, settling, and billing gas in a multi-gas energy system. The current challenges highlight the need for a flexible solution that can respond to changes in gas mix and subsequent CVs. The findings of this programme will be applicable and relevant to all gas networks across GB amongst wider energy industry stakeholders. Stakeholder engagement with key industry stakeholder is vital to ensure that all eligibility criteria are thoroughly reviewed and endorsed by all relevant parties. | TBC | TBC | TBC | TBC | TBC | TBC | Added by Workgroup - Detail to be confirmed | Documentation published indicates that the programme is currently in the Phase 1 (10 months, started in September 2024). Phase 1 has been split into 5 work packages: • WP1: Market research to identify existing solutions. • WP2: Develop the Basis of Design of a fit-for-purpose modelling solution. • WP3a: Feasibility study: economic, technical, regulatory, operational, etc. • WP3b: Roadmap for a seamless integration across the UK. • WP4: Rollout strategy to assess the requirements for a potential demonstration. • WP5: Dissemination. | Further information on timescales can be found in the document linked below, which indicates the following: Phase 0: Engagement, 4 months (2024) Phase 1: Methodology Development, 10 months (2024/2025) Phase 2: Front-End Engineering Design, 7 months (2025/2026) Phase 3: Demonstration, 12 months (2026/2027) Implementation: 2030 https://www.gasgovernance.co.uk/sites/default/files/related-files/2025-02/RTSM%20Stakeholder%20Engagement%20v1.0_0.pdf | TBC | TBC | TBC | TBC | TBC | Phase 1 Methodology Development Presentation: https://www.gasgovernance.co.uk/sites/default/files/related-files/2025-02/RTSM%20Stakeholder%20Engagement%20v1.0_0.pdf Xoserve RTSM webpage: https://www.xoserve.com/decarbonisation/decarbonising-gas/decarbonisation-knowledge-centre/real-time-settlement-methodology-rtsm/
Hydrogen | GSO | Funding hydrogen infrastructure: The GSO is likely to be introduced in 2027 and may require code changes to enable data sharing and funding arrangements prior to implementation. | Yes | Yes | TBC | Yes | Yes | TBC |  | Impacts on the IGT UNC and UNC are currently being discussed with DESNZ and between the two Code Managers. UNC Modification 0922 - 'CDSP Obligations required for the introduction of the Gas Shipper Obligation' was raised on 7th January 2026. IGT UNC Modification 180 - 'CDSP Obligations required for the introduction of the Gas Shipper Obligation' was raised on 15th January 2026. | The IGT UNC and UNC Modifications will be progressed via a Joint IGT UNC and UNC Workgroup. The First meeting will be held in March while we await Government publications regarding the GSO Scheme. | Yes | Yes | TBC | Yes | TBC | https://www.igt-unc.co.uk/igt180/ https://www.gasgovernance.co.uk/0922

## Cross Code Change
Cross Code Change
Code | Change Number | Related Changes | Title | Proposer | Current Status | Next Stage | Key Date | Other Comments / Useful Context
UNC | 922 | IGT180 | CDSP Obligations required for the introduction of the Gas Shipper Obligation | National Gas Transmission | Workgroup Consideration | Report to Panel | 2026-07-17 | February 2026 Update: This Modification as raised on 7th January 2026. It will be progressed jointly with IGT180. May 2026 Update: The first Joint Workgroup meeting will be communicated to Parties once confirmed.
IGT UNC | 180 | UNC0922 | CDSP Obligations required for the introduction of the Gas Shipper Obligation | BUUK | Workgroup Consideration | Report to Panel | 2026-07-24 | February 2026 Update: This Modification as raised on 15th January 2026. It will be progressed jointly with UNC0922. May 2026 Update: The first Joint Workgroup meeting will be communicated to Parties once confirmed.
IGT UNC | 176 | UNC0887 XRN 5937.3 | Changes to IGT UNC to enable UNC0887 ‘Facilitating Bi-Directional Connections Between IGT Pipelines and the NTS’ | CNG Services | Awaiting Implementation | Implementation | TBC | Apr/May 2025 Update: CNG raised this Modification on 19th March 2025. The Panel considered the Modification at its meeting on 28th March. The Modification was briefly discussed at Workgroup on 10th April. The Workgroup will do further work on the Modification at its 8th May meeting. July 2025 Update: The Workgroup had continued its work on this Modification. We are aiming to agreed the Workgroup Report in July. September 2025 Update: IGT176 was send to the Authority for decision on 2nd September 2025. December 2025 Update: IGT176 has been approved by the Authority. Implementation is TBC.
UNC | 854 | IGT181 | Revision of Virtual Last Resort User and Contingent Procurement of Supplier Demand Event Triggers | National Gas Transmission | Implemented | - | - | Jan 2025 Update: Implemented on 22nd May 2024. IGT UNC Workgroup have agreed that a change to the IGT UNC is required. Waiting on an IGT UNC Modification to be raised. Feb 2025 Update: The IGT UNC Code Administrator has met with Energy Assets to discuss raised the required equivalate Modification. The Proposer will be brining the equivalent Modification to Workgroup on 13th March 2025 for pre-Modification discussion before looking to formally raise the Modification ahead of the February Panel meeting on 28th March 2025. Mar 2025 Update: The Code Administrator is still expecting this Modification to be discussed at an upcoming IGT UNC Workgroup meeting. December 2025 Update: The Code Administrator is currently in talks with a new sponsor for this IGT Modification. If a change is still required we expect it to be raised in early 2026. April 2026 Update: IGT181 was raised on 18th February 2026.
UNC | 887 | IGT176 XRN 5937.3 | Facilitating Bi-Directional Connections Between IGT Pipelines and the NTS | National Gas Transmission | Awaiting Implementation | Implementation | TBC | Mar 2025 Update: An IGT has submitted a draft Modification Proposal form. The Code Administrator expect this Modification to be raised ahead of the March 2025 Panel meeting. Apr/ May 2025 Update: UNC Workgroup Report was presented to the UNC Panel on 17th April. This Modification is currently out for industry Consultation, which will close on 13th May 2025. The Modification will go back to Panel on 16th May 2025. June 2025 Update: FMR for UNC0887 is due to be presented to the UNC Panel in June. July 2025 Update: This Modification was recommended for approval by the UNC Panel in June and was submitted to the Authority for consideration on 20th June 2025. September 2025 Update:UNC0887 was issued to the Authority on 2nd September 2025. December 2025 Update: UNC0887 has been approved by the Authority. Implementation is TBC.
IGT UNC | 181 | UNC0854 | Revision of Virtual Last Resort User and Contingent Procurement of Supplier Demand Event Triggers | ES Pipelines Limited | Workgroup Consideration | Report to Panel | 2026-05-29 | April 2026 Update: This Modification was raised on 18th February 2026. This Modification seeks to align the IGT UNC with the changes implemented into the Uniform Network Code (UNC) under UNC0854 ‘Revision of Virtual Last Resort User and Contingent Procurement of Supplier Demand Event Triggers’ in May 2024. This will ensure that the UNC processes can apply to IGT Supply Meter Points (SMPs) as intended under UNC0854. May 2026 Update: The Workgroup is expected to complete their work and the Workgroup Report at its May meeting.

## Milestone Timeline
IGT UNC Horizon Scanner Timeline
2027
Category |  | MAR | APR | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sep | Oct | Nov | Dec
Code Reform | Code Consolidation | MAR: LINK
| Code Manager Selection | MAR: LINK
| SDS | APR: LINK
| Pre-Consolidation Code Changes | APR: LINK
Xoserve | Project Trident | bar: 2027 Nov
Digitalising the Energy System | DSI (NESO MVP, Ofgem) | APR: RIIO T3/GD3 start
DBP (Ofgem) | bar: MAR to APR
IGT176 (Bidirectional Gas to NTS via IGT) | bar: Aug
UNC0887 (Bidirectional Gas to NTS via IGT) | bar: Aug
UNC0922 (CDSP Changes for GSO) | bar: Aug; Oct
IGT180 (CDSP Changes for GSO) | bar: Aug; Oct
Hydrogen Blending | RTSM Programme | bar: MAR to Aug
GSO | bar: MAR to 2027 Jan
M
M
complete the core MVP development
Target Implementation: TBC
Target Implementation: TBC
M
GSO Expected to be introduced
M
M
Full Business Case
Procurement: RFP
Design, Build, Test commences
M
W
W
W
W
P
P
C
C
P
P
M
M
Modifications issued to Authority
Procurement: PQQ
Feb/Mar/Apr Joint Meetings cancelled
P
C
C
C

## Timeline key
Icon | Description
Consultation Confirmed
Consultation Unconfirmed
Release/Implementation Confirmed
Release/Implementation Unconfirmed
Event/Workgroup/Steering Group/Panel Confirmed
Event/Workgroup/Steering Group/Panel Unconfirmed
Publication Confirmed
Publication Unconfirmed
Milestone Unconfirmed
Milestone Confirmed
Solid Yellow/Solid Grey | Work Ongoing
P
P
R
R
C
E
E
M
M
W
S
W
S
P
P
C
I
I
I

## Acronyms
Acronym | Defined Term
AUGE | Allocation of Unidentified Gas Expert
BEIS | Department for Business, Energy, and Industrial Strategy
BSC | Balancing and Settlement Code
CDSP | Central Data Services Provider
CMA | Competition and Markets Authority
CSS | Central Switching Service
CUSC | Connection and Use of System Code
CV | Calorific Value
DBP | Data Best Practice
DCUSA | Distribution Connection and Use of System Agreement
ECC | Electricity Commercial Code
ESD | Energy System Data
ETC | Electricity Technical Code
FBC | Full Business Case
GEMA | Gas and Electricity Markets Authority
GNC | Gas Network Code
GSO | Gas Shipper Obligation
IGT UNC | Independent Gas Transporters Uniform Network Code
ISOP | Independent System Operator and Planner
MVP | Minimum Viable product
NESO | National Energy System Operator. Named in the Energy Act 2023 as ISOP
NZIP | Government’s Net Zero Innovation Portfolio
PAC | Performance Assurance Committee
PAFA | Performance Assurance Framework Administrator
REC | Retail Energy Code
RTSM | Real Time Settlement Methodology
SAF | Stakeholder Advisory Forum
SDS | Strategic Direction Statement, which will set out Ofgem's vision for how the codes should devolve on an annual basis
SEC | Smart Energy Code
SOS | Secretary of State
SQSS | Security and Quality of Supply Standard
STC | System Operator Transmission Owner Code
UNC | Uniform Network Code