## Sheet1
High Priority Reason: * directly supports key government energy policy actions that require immediate progress and aligns with SDS priorities under the Act Now category; * is highly complex, with a fast approaching deadline, significant implementation challenges, and a requirement for extensive stakeholder; and * addresses a high‑risk or critical issue, making timely action important for stakeholders as it is anticipated to deliver substantial benefits.
Modification Reference Suffix: A - Alternate, S - Self-Governance, FT - Fast Track Self-Governance, V - Varied, R - Review, I - INC Modification
|  | For information on Closed Modifications, please visit the Closed Modifications page. | [5 empty] | *Key Dates are normally an end-date, where shown red this is date sent to Ofgem
Mod Ref |  | Title | Proposing Organisation | Date Raised | Live/ Closed | Category | Priority Category | Priority Reason | UNC Impact | Current Status | Next Stage | Key date*
IGT183 | S | Maintenance criteria for Emergency Contact data held in Central Systems | Centrica | 2026-05-21 | Live | Self-Governance | Standard | No impact to any Prioritisation Criteria | Yes | Allocated to Workgroup | Final Mod Report | 2026-08-28
IGT181 | S | Revision of Virtual Last Resort User and Contingent Procurement of Supplier Demand Event Triggers | ES Pipelines Limited | 2026-02-18 | Live | Self-Governance | Standard | No impact to any Prioritisation Criteria | Yes | Awaiting Implementation | Implemented | 23-Aug-26 (Phase 1) Aug-26 (Phase 2)
IGT180 |  | CDSP Obligations required for the introduction of the Gas Shipper Obligation | BUUK | 2026-01-15 | Live | Authority | Standard | No impact to any Prioritisation Criteria | Yes | Allocated to Workgroup | Final Mod Report | 2027-01-29
IGT176 |  | Changes to IGT UNC to enable UNC0887 ‘Facilitating Bi-Directional Connections Between IGT Pipelines and the NTS’ | CSL | 2025-03-19 | Live | Authority | N/A | N/A | Yes | Awaiting Implementation | Implemented | Aug-26 (Date TBC)
CSL01 | I | Exclusion of Standalone Networks from IGT UNC | CSL | 2026-01-15 | Live | Authority | Standard | No impact to any Prioritisation Criteria | No | Awaiting Ofgem decision | TBC | 2026-06-01
RG008 | R | IGT UNC Code Review in preparation for Code Manager and Code Consolidation | BUUK | 2025-11-20 | Live | N/A | N/A | N/A | No | Allocated to Review Group | Interim Review Report | 2026-07-24
RG009 | R | Introduction of Qualification Requirements for new Shippers | BUUK | 2026-06-23 | Live | N/A | N/A | N/A | No | Allocated to Review Group | Interim Review Report | 2026-10-23
Joint Office
of Gas Transporters