## Introduction
IGT UNC Horizon Scanner
Date | 2026-10-01
Version | v1.20
Purpose | This document provides visibility of IGT UNC impacting industry activities, as well as the progression of Cross Code impacting Modifications. This document is owned by the IGT UNC Workgroup and is refreshed approximately monthly. Please refer to the IGT UNC Horizon Scanner page of the IGT UNC website for the most up to date version.
Contact | If you have any queries or comments about this Horizon Scanner, please contact the IGT UNC Code Administrator via email, IGTUNC@gemserv.com.
Uplift History | Reason for change | Date
v0.1 | Initial draft for Workgroup consideration | 2024-11-07
v1.0 | Uplift to approved working document | 2024-12-05

## Horizon Scanner
IGT UNC Horizon Scanner
|  |  | IMPACTS | [8 empty] | INDUSTRY CHANGE
Category | Activity | Description / Scope | IGT UNC | UNC | Other Codes | IGT | Shipper | Other Party | Risks / Issues | Current Status | Future Milestones / Key Dates | IGT Changes | UNC Changes | Other Code Changes | Central System Changes | Licences | Other Comments / Useful Context
Code Reform | Code Consolidation | Introduction of GNC, which will involve the merging of IGT UNC and UNC. Designation of changes ahead of consolidation is expected. Further information on this will be noted when it is available. | Yes | Yes | CUSC DCUSA SQSS STC | Yes | Yes | All parties to impacted Codes | Introduction of inaccuracies, short notice changes, lack of party engagement. | Ofgem work is ongoing. On 4 September Ofgem published their statutory consultation on proposed modifications to the Retail Energy Code (REC) and affected energy licences. The consultation forms part of the implementation of Energy Code Reform and seeks views on the code and licence changes required to implement the new governance framework established under the Energy Act 2023 and prepare the REC for designation. The proposed modifications implement previously consulted-on policy decisions and are intended to align the REC and affected licences with the code manager licensing framework. https://www.ofgem.gov.uk/consultation/energy-code-reform-statutory-consultation-modifications-retail-energy-code-and-affected-licences | The interim milestones and timings of critical path activities for phase 1 codes are as follows: Spring / Summer 2025: Phase 1 bilateral and workgroups with the industry will be held for targeted policy topics. Later in 2025 / 1H-2026: Ofgem expect to consult on modification proposals for phase 1 codes. Implementation and assurance activities for phase 1 code manager candidates are expected to run during this period. Spring / Summer 2026: Phase 1 code manager appointments are expected. Commencing in 2026-27: Ofgem expected to publish minded-to decisions with respect to the identity of the phase 2 code managers, by the start of the subsequent implementation and assurance period. Below summarises the upcoming code reform publications, planned for 2025/26: • Autumn 2025: Decision on second implementation consultation • Winter 2025/26: Modification proposals consultation • Winter 2025/26: Decision on code manager licence conditions and code modification appeals to the CMA – in collaboration with DESNZ | Directed changes expected (timeline TBC) | Directed changes expected (timeline TBC) | Directed changes expected (timeline TBC) | TBC | Directed changes expected (timeline TBC) | Ofgem identified the following areas where they believed code provisions should be targeted for rationalisation and simplification as part of any Ofgem-led consolidation activity, using the transitional Ofgem powers granted by the Energy Act: • Common contractual framework • Contract boilerplate and defined terms • Party accession and exit • Code objectives • Code modification process • Code compliance • Credit cover arrangements • Dispute processes • Derogation provisions
Code Reform | Pre-Consolidation Code Changes | Ofgem identified the following areas where Ofgem believed code provisions should be targeted for rationalisation and simplification as part of any Ofgem-led consolidation activity, using the transitional powers granted by the Act: • Common contractual framework • Contract boilerplate and defined terms • Party accession and exit • Code objectives • Code modification process • Code compliance • Credit cover arrangements • Dispute processes • Derogation provisions | Yes | Yes | Yes | Yes | Yes | Yes | Risks and issues to be confirmed by Workgroup. | Ofgem work is ongoing. The IGT UNC and UNC Code Administrators have been engaging directly with Ofgem on potential areas of Code Consolidation. This work will continue and industry will be informed of any outputs via Ofgem publications. On 1 September Ofgem published their decision on the phase 1 consultation on transitional measures and code changes. The decision sets out their intention to take forward proposals on the policy areas consulted on in that consultation, namely proposed changes to the BSC and REC, code manager licence terms, and bespoke and transitional licence arrangements for code managers of the BSC and REC. https://www.ofgem.gov.uk/consultation/energy-code-reform-phase-1-code-manager-licence-modifications | The interim milestones and timings of critical path activities for phase 1 codes are as follows: Spring / Summer 2025: Phase 1 bilateral and workgroups with the industry will be held for targeted policy topics. Later in 2025 / 1H-2026: Ofgem expect to consult on modification proposals for phase 1 codes. Implementation and assurance activities for phase 1 code manager candidates are expected to run during this period. Spring / Summer 2026: Phase 1 code manager appointments are expected. Below summarises the upcoming code reform publications, planned for 2025/26: • Winter 2025/26: Modification proposals consultation • Winter 2025/26: Decision on code manager licence conditions and code modification appeals to the CMA – in collaboration with DESNZ | Directed changes expected (timeline TBC) | Directed changes expected (timeline TBC) | Directed changes expected (timeline TBC) | TBC | Directed changes expected (timeline TBC) | Ofgem identified the following areas where they believed code provisions should be targeted for rationalisation and simplification as part of any Ofgem-led consolidation activity, using the transitional powers granted by the Energy Act: • Common contractual framework • Contract boilerplate and defined terms • Party accession and exit • Code objectives • Code modification process • Code compliance • Credit cover arrangements • Dispute processes • Derogation provisions
Code Reform | SDS | Introduction of the Ofgem SDS, which is intended to set the direction of travel for the development of codes, in line with Ofgem's overarching vision for the sector. The SDS is required by the Energy act to contain a strategic assessment of government policy and developments which require modifications to the designated codes, and in preparing the SDS Ofgem must have regard to advice given by the NESO. | Yes | Yes | Yes | Yes | Yes | Yes | Risks and issues to be confirmed by Workgroup when more detail is available. | Ofgem work is ongoing. Second Preliminary SDS Ofgem published their Second Preliminary Strategic Direction Statement on 15 September on the Ofgem website. This will become the first SDS that future code managers will be obliged to consider in delivery plans, upon publication of the conversion letter (or letters) later this year. This should now be the SDS used when undertaking the harmonised approach to code modification prioritisation. This means that code administrators and panels will be required to show consideration of SDS-2 in their prioritisation decisions. https://www.ofgem.gov.uk/sites/default/files/2026-09/Second-preliminary-Strategic-Direction-Statement-for-industry-codes-2026.pdf | The next formal SDS is expected to follow the appointment of code managers in 2026. | Directed changes expected (timeline TBC) | Directed changes expected (timeline TBC) | Directed changes expected (timeline TBC) | TBC | Directed changes expected (timeline TBC) | Ofgem currently do not propose to introduce an obligation to implement the SDS before code managers are in place, however, they have proposed the introduction of a standard prioritisation process for code panels which will support the introduction of the SDS (see 22nd August 2024 decision publication and recently issued consultation on preliminary SDS dated 31st January 2025). Decision on code governance arrangements and SDS: https://www.ofgem.gov.uk/decision/decision-preliminary-strategic-direction-statement-and-governance-arrangements-industry-codes
Code Reform | Code Governance (General & GNC) | Changes to code governance (inc. matters relating to Code Managers, SAF, prioritisation, objectives, transition to new framework) will be done by Ofgem and with the permission of the SOS. | Yes | Yes | Yes | Yes | Yes | Yes | Risks and issues to be confirmed by Workgroup when more detail is available. | Ofgem work is ongoing. On 2 September Ofgem published the energy code reform phase 1: code manager licence modifications. They are consulting on proposed modifications to certain standard conditions of the code manager licences for the Balancing and Settlement Code (BSC) and Retail Energy Code (REC), and the introduction of special conditions. The proposed changes include arrangements to address transitional issues relating to budgets, budget appeals, cost recovery and delivery plans, measures to support further development of the code manager performance framework, as well as special conditions to support the transfer of certain code governance responsibilities to the code managers. https://www.ofgem.gov.uk/consultation/energy-code-reform-phase-1-code-manager-licence-modifications | The interim milestones and timings of critical path activities for phase 1 codes are as follows: Spring / Summer 2025: Phase 1 bilateral and workgroups with the industry will be held for targeted policy topics. Later in 2025 / 1H-2026: Ofgem expect to consult on modification proposals for phase 1 codes. Implementation and assurance activities for phase 1 code manager candidates are expected to run during this period. Spring / Summer 2026: Phase 1 code manager appointments are expected. Below summarises the upcoming code reform publications, planned for 2025/26: • Winter 2025/26: Modification proposals consultation • Winter 2025/26: Decision on code manager licence conditions and code modification appeals to the CMA – in collaboration with DESNZ | Directed changes expected (timeline TBC) | Directed changes expected (timeline TBC) | Directed changes expected (timeline TBC) | TBC | Directed changes expected (timeline TBC) | Recent publications on matters of Code Governance: Consultation on Code Manager Selection: https://www.ofgem.gov.uk/sites/default/files/2024-11/Consultation_on_code_manager_selection.pdf Decision on implementation of Energy Code Reform: https://www.ofgem.gov.uk/decision/implementation-energy-code-reform-decision Decision on code governance arrangements and SDS: https://www.ofgem.gov.uk/decision/decision-preliminary-strategic-direction-statement-and-governance-arrangements-industry-codes Consultation on Code Manger Licence Conditions and Appeals: https://www.gov.uk/government/consultations/energy-code-reform-code-manager-licence-conditions-and-code-modification-appeals-to-the-cma Expressions of interest in Code Manager candidates: https://www.ofgem.gov.uk/call-for-input/expression-interest-invitation-code-manager-candidates Determination pursuant to regulation 3(8) of the code manager selection regulations 2024 of the basis of selection of code managers for the consolidated Electricity Commercial Code and Gas Network Code: https://www.ofgem.gov.uk/decision/determination-basis-selection-code-manager-candidates
Xoserve | Project Trident | Project Trident is an Xoserve project, looking to modernise UK Link, the platform they use to connect information, technology and communications systems for the retail gas market. UK Link is used and managed by Xoserve in its role as CDSP. It ensures the industry operates smoothly, effectively and efficiently, in accordance with the Uniform Network Code and its IGT equivalent. | TBC | TBC | TBC | TBC | TBC | TBC | Risks and issues to be confirmed by Workgroup. | Several updates can be found in the September Tide Newsletter: https://www.xoserve.com/media/yosovxuy/the-tide-23-xoserves-project-trident-newsletter-sept-26.pdf | Standard support for the current version of the SAP platform that supports UK Link ends in 2027, with extended support available until 2030. It is estimated that Project Trident will run until 2028. | TBC | TBC | TBC | TBC | TBC | https://www.xoserve.com/products-services/data-products/uk-link-system/project-trident/ https://www.xoserve.com/media/ekhd0pqx/project-trident_pre-workshop-introductory-webinar-slides_v11.pdf
Xoserve | Service Line Review | Xoserve looking at amendments to the service lines, introduction of a new service line which will include a new charge for IGTs and splitting an element related to AUGE, PAC and PAFA and making it a 50/50 split in respect of charging. | TBC | TBC | TBC | TBC | TBC | TBC | Added by Workgroup - Detail to be confirmed. | No Updates | Added by Workgroup - Detail to be confirmed | TBC | TBC | TBC | TBC | TBC
Digitalising the Energy System | Data Sharing Infrastructure | Introduction of a data sharing infrastructure, which is a minimum set of responsibilities, governance, functions and processes for secure, interoperable data sharing across the energy system. This activity covers the DSI Pilot, DSI MVP and Ofgem Guidance. | TBC | TBC | TBC | TBC | TBC | TBC | Risks and issues to be confirmed by Workgroup. | Ofgem and DESNZ vision for digitalisation of the energy sector, including policy and technical coordination, expected in Q1 2026. | Related Ofgem programme’s name has changed from Energy Data and Digitalisation to Energy System Digitalisation. Ofgem's Energy System Digitalisation page is provided below: https://www.ofgem.gov.uk/energy-policy-and-regulation/policy-and-regulatory-programmes/energy-system-digitalisation Project information for NESO DSI Pilot / MVP: https://smarter.energynetworks.org/projects/nia2_ngeso081/ https://www.neso.energy/document/353696/download Project information for NESO DSI / SSEN-T Component: https://smarter.energynetworks.org/projects/nia_shet_0053/ | TBC | TBC | TBC | TBC | TBC | Related Ofgem programme’s name has changed from Energy Data and Digitalisation to Energy System Digitalisation. Ofgem's Energy System Digitalisation page is provided below: https://www.ofgem.gov.uk/energy-policy-and-regulation/policy-and-regulatory-programmes/energy-system-digitalisation Project information for NESO DSI Pilot / MVP: https://smarter.energynetworks.org/projects/nia2_ngeso081/ Project information for NESO DSI / SSEN-T Component: https://smarter.energynetworks.org/projects/nia_shet_0053/ Digitalising the Energy System: https://www.gov.uk/government/publications/digitalising-the-energy-system Ofgem decision on the definition of ESD and DBP Guidance: https://www.ofgem.gov.uk/decision/decision-definition-energy-system-data-data-best-practice-guidance
Hydrogen | Hydrogen Strategy | The Government sees Hydrogen as a key support for the decarbonisation of the UK economy. In 2021, the UK government published its first Hydrogen Strategy, which aimed for 5GW of low carbon hydrogen production capacity by 2030 for use across the economy. Building on these proposals, the British Energy Security Strategy committed to doubling this 2030 hydrogen production capacity ambition to up to 10GW, with at least half coming from electrolytic production. The Government set out its decision to support the blending of up to 20% hydrogen by volume into the GB gas distribution networks in 2023. | TBC | TBC | TBC | TBC | TBC | TBC | Added by Workgroup - Detail to be confirmed | Added by Workgroup - Detail to be confirmed | Added by Workgroup - Detail to be confirmed | TBC | TBC | TBC | TBC | TBC
Hydrogen | RTSM Programme | In February 2024, a programme was established, to develop a modelling solution that will facilitate the introduction of a fair and equitable billing and settlement framework able to operate in a multi-gas system with varying CVs. The RTSM programme aims to develop an integrated solution for the processes of characterising, settling, and billing gas in a multi-gas energy system. The current challenges highlight the need for a flexible solution that can respond to changes in gas mix and subsequent CVs. The findings of this programme will be applicable and relevant to all gas networks across GB amongst wider energy industry stakeholders. Stakeholder engagement with key industry stakeholder is vital to ensure that all eligibility criteria are thoroughly reviewed and endorsed by all relevant parties. | TBC | TBC | TBC | TBC | TBC | TBC | Added by Workgroup - Detail to be confirmed | Phase 1 Work Packages • WP1: Market research to identify existing solutions: Delivered by BIP: A comprehensive market research study was conducted to identify various solutions that have been developed globally for billing and settlement in multi-energy gas systems. Using these developed solutions as examples, the project sought to understand their technical requirements and how these solutions could be applied to help solve Great Britain's challenge. We found that suitable CV modelling solutions are available and that their adoption is attainable across Great Britain. • WP2: Develop the Basis of Design of a fit-for-purpose modelling solution: Delivered by Correla: This part of the project designed a fit-for-purpose modelling solution that meets the requirements of Great Britain's gas consumers and existing stakeholders whilst effectively addressing the challenges with billing and settlement in a future multi-gas system. A key output of this work package was the Basis of Design of the proposed solution. The Basis of Design outlines the required amendments in the market structures and connection frameworks, the basic architecture of new systems proposed, and considers key essential aspects such as changes in regulation and the interlink between solutions for a seamless transition process. It also encompasses the identification of high-level dependencies and interactions with other industry systems to comprehensively address integration. • WP3: Feasibility study: economic, technical, regulatory, operational, etc: Delivered by BIP: This work package conducted a comprehensive feasibility study that evaluated the viability of each proposed solution by assessing all factors critical to its success - regulatory, technical, economic, scheduling, and operational. This enabled the development of a comprehensive roadmap to inform the strategic implementation of the proposed solution across Great Britain, considering all key aspects and paving the way for successful implementation with minimal disruption. • WP4: Rollout strategy to assess the requirements for a potential demonstration: Delivered by BIP: This work package developed a rollout strategy for a potential demonstration of the solution in a dedicated future Pilot phase. The most feasible Pilot options and locations have been identified, and these will be further analysed in upcoming work. The demonstration activities will also include a trial phase which will be conducted after the Pilot. • WP5: Dissemination: Delivered by BIP and Correla: The dissemination process ensured that all project learnings were successfully shared with key stakeholders. The partners discussed the findings and results from all work packages and tailored them into a detailed technical account that described the work’s methods, analysis, and findings. | Work is currently underway on the next phase of RTSM, Phase 1b - Pilot Options Appraisal (RTSM POA), which focuses on evaluating the options for a future Pilot project. The Pilot will be an important step in testing the RTSM solution on the live gas network, helping to demonstrate how effectively it performs in real-world conditions. In Phase 1, the programme identified a number of potential Pilot options. During Phase 1b, RTSM POA, these options will be assessed in greater detail to better understand their technical, economic, operational, regulatory, social and environmental implications. The Pilot Options Appraisal (RTSM POA) project will also define key aspects of the Pilot's design, including its location on the network, the gases to be used, the software platforms to be tested, and the duration of the trial. The Pilot is expected to assess several critical elements of the solution, including modelling software performance, data collection and processing, and the accuracy of the proposed billing methodology. The insights gained will help inform the next stages of the RTSM Programme and support progress towards nationwide implementation. Therefore, the Phase 1b appraisal will help ensure that the most appropriate and effective approach is selected. Throughout Phase 1b, the programme will continue to work closely with regulators, gas network operators and industry stakeholders to ensure the Pilot is designed for success and provides a strong foundation for the future rollout of the RTSM solution. | TBC | TBC | TBC | TBC | TBC | Phase 1 Methodology Development Presentation: https://www.gasgovernance.co.uk/sites/default/files/related-files/2025-02/RTSM%20Stakeholder%20Engagement%20v1.0_0.pdf Xoserve RTSM webpage: https://www.xoserve.com/decarbonisation/decarbonising-gas/decarbonisation-knowledge-centre/real-time-settlement-methodology-rtsm/
Hydrogen | GSO | Funding hydrogen infrastructure: The GSO is likely to be introduced in 2027 and may require code changes to enable data sharing and funding arrangements prior to implementation. | Yes | Yes | TBC | Yes | Yes | TBC |  | Impacts on the IGT UNC and UNC are currently being discussed with DESNZ and between the two Code Managers. UNC Modification 0922 - 'CDSP Obligations required for the introduction of the Gas Shipper Obligation' was raised on 7th January 2026. IGT UNC Modification 180 - 'CDSP Obligations required for the introduction of the Gas Shipper Obligation' was raised on 15th January 2026. | The IGT UNC and UNC Modifications will be progressed via a Joint IGT UNC and UNC Workgroup. The First meeting will be held in March while we await Government publications regarding the GSO Scheme. | Yes | Yes | TBC | Yes | TBC | https://www.igt-unc.co.uk/igt180/ https://www.gasgovernance.co.uk/0922

## Cross Code Change
Cross Code Change
Code | Change Number | Related Changes | Title | Proposer | Current Status | Next Stage | Key Date | Other Comments / Useful Context
UNC | 922 | IGT180 | CDSP Obligations required for the introduction of the Gas Shipper Obligation | National Gas Transmission | Workgroup Consideration | Report to Panel | 2027-01-21 | February 2026 Update: This Modification as raised on 7th January 2026. It will be progressed jointly with IGT180. May 2026 Update: The first Joint Workgroup meeting will be communicated to Parties once confirmed. June 2026 Update: A update on the GSO Modifications is expected at the June 2026 IGT UNC Workgroup and UNC Distribution Workgroup meetings. August 2026 Update: This Modification has had a 6 month extension approved by the UNC Panel.
IGT UNC | 180 | UNC0922 | CDSP Obligations required for the introduction of the Gas Shipper Obligation | BUUK | Workgroup Consideration | Report to Panel | 2027-01-29 | February 2026 Update: This Modification as raised on 15th January 2026. It will be progressed jointly with UNC0922. May 2026 Update: The first Joint Workgroup meeting will be communicated to Parties once confirmed. June 2026 Update: A update on the GSO Modifications is expected at the June 2026 IGT UNC Workgroup and UNC Distribution Workgroup meetings. August 2026 Update: This Modification has been extended by 6 months to align with the extension approved for UNC09222.
UNC | 926 | IGT183 | Maintenance criteria for Emergency Contact data held in Central Systems | Cadent | Awaiting Implementation | Implementation | TBC | August 2026 Update: The Panel has issues this modification for consultation with responses due back by 8th August. The Panel will make its final decision on 20th August. September 2026: This Modification was approved. Implementation TBC
IGT UNC | 183 | UNC0926 | Maintenance criteria for Emergency Contact data held in Central Systems | Centrica | Report to Panel | Panel Decision | 2026-10-23 | October 2026: The FMR will be considered by Panel on 23rd October 2026.

## Milestone Timeline
IGT UNC Horizon Scanner Timeline
2027
Category |  | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sep | Oct | Nov | Dec
Code Reform | Code Consolidation | bar: Aug to 2027 Apr
| Code Manager Selection | Sep: LINK: Closed 01/10/26
SDS | bar: Aug to 2027 Apr
Pre-Consolidation Code Changes | bar: Aug to 2027 Apr
Xoserve | Project Trident | bar: 2027 Nov
Digitalising the Energy System | DSI (NESO MVP, Ofgem)
DBP (Ofgem)
UNC0922 (CDSP Changes for GSO) | bar: 2027 Jan; 2027 Mar
IGT180 (CDSP Changes for GSO) | bar: 2027 Jan; 2027 Mar
UNC0938R (Qualification Requirements) | bar: 2027 Feb
RG009 (Qualification Requirements) | bar: 2027 Feb
IGT183 (Emergency Contact data) | bar: 2027 Feb
UNC0926 (Emergency Contact data) | bar: 2027 Feb
Hydrogen Blending | RTSM Programme | bar: Aug to 2027 Feb
GSO | bar: Aug to 2027 Jan
M
complete the core MVP development
M
GSO Expected to be introduced in 2027
M
Full Business Case
Procurement: RFP
Design, Build, Test commences
M
W
W
W
W
C
P
P
M
M
P
P
C
C
Joint Workgroup Meetings TBC
W
P
P
C
P
Approved: Impementation TBC
C
W
W

## Timeline key
Icon | Description
Consultation Confirmed
Consultation Unconfirmed
Release/Implementation Confirmed
Release/Implementation Unconfirmed
Event/Workgroup/Steering Group/Panel Confirmed
Event/Workgroup/Steering Group/Panel Unconfirmed
Publication Confirmed
Publication Unconfirmed
Milestone Unconfirmed
Milestone Confirmed
Solid Yellow/Solid Grey | Work Ongoing
P
P
R
R
C
E
E
M
M
W
S
W
S
P
P
C
I
I
I

## Acronyms
Acronym | Defined Term
AUGE | Allocation of Unidentified Gas Expert
BEIS | Department for Business, Energy, and Industrial Strategy
BSC | Balancing and Settlement Code
CDSP | Central Data Services Provider
CMA | Competition and Markets Authority
CSS | Central Switching Service
CUSC | Connection and Use of System Code
CV | Calorific Value
DBP | Data Best Practice
DCUSA | Distribution Connection and Use of System Agreement
ECC | Electricity Commercial Code
ESD | Energy System Data
ETC | Electricity Technical Code
FBC | Full Business Case
GEMA | Gas and Electricity Markets Authority
GNC | Gas Network Code
GSO | Gas Shipper Obligation
IGT UNC | Independent Gas Transporters Uniform Network Code
ISOP | Independent System Operator and Planner
MVP | Minimum Viable product
NESO | National Energy System Operator. Named in the Energy Act 2023 as ISOP
NZIP | Government’s Net Zero Innovation Portfolio
PAC | Performance Assurance Committee
PAFA | Performance Assurance Framework Administrator
REC | Retail Energy Code
RTSM | Real Time Settlement Methodology
SAF | Stakeholder Advisory Forum
SDS | Strategic Direction Statement, which will set out Ofgem's vision for how the codes should devolve on an annual basis
SEC | Smart Energy Code
SOS | Secretary of State
SQSS | Security and Quality of Supply Standard
STC | System Operator Transmission Owner Code
UNC | Uniform Network Code